## Slide 1: VM Performance Review Meeting
September 4, 2020
overall_0_132149625091576866 columns_1_132149625091576866
Rev. 1

## Slide 2: QC Mileage, Sampling and Performance Targets
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
SAMPLING – 100% QC inspection is performed on 2161 circuit miles. These 2161 miles represent ≥ 80% REAX Range and present ≥ 93.87% of the risk
QUALITY: An Acceptable Quality Level of 100% RCD has been established for VM. This is the highest program expectation of all T&D QC Programs
QC inspection is performed on a “circuit mileage” basis. Vegetation within the selected circuit mile is assessed for compliance to UVM Program requirements. Judgmental sampling is performed to select circuit mileage with known adjacent vegetation

## Slide 3: QC Mileage / Productivity HFRA / Non-HFRA / All Miles / WMP
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Lower than expected productivity is attributed to several factors:
QC inspected 634 circuit miles in July which is below the monthly target. Grids/circuits and inventory inspected was more densely populated resulting in lower production
High missed tree rate results in lower production by QC
Survey 123 onboarding process delays of more than 8 weeks issuing new devices
VM Lead: Bill

## Slide 4: YTD VM Performance – Transmission & Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
YTD data reflects work completed in 2020 only. This does not include any January/February report data
VM Lead: Bill

## Slide 5: YTD VM Performance – Transmission
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
July observed a further decline in RCD performance from 91.88% to 74.56%. This was attributed to:
  Issues with Sag/Sway versus LiDAR usage and improper implementation of LiDAR during the Pre-Inspection process
    (lot of missed trees relates to a low RCD) – same circuits that were identified in the June report; addressed in action plan

## Slide 6: Transmission HFRA / Non-HFRA RCD & CCD Breakdown
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 7: YTD VM Performance – Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
YTD data reflects work completed in 2020 only. This does not include any January/February report data
July observed a further decline in RCD performance from 98.59% to 98.10%. At this time it is difficult to determine why we are seeing the decline as most of our contractors’ individual performance also declined. Could be attributed to seasonal growth conditions and line dynamics.
VM Lead: Bill

## Slide 8: Distribution HFRA / Non-HFRA RCD & CCD Breakdown
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 9: T& D RCD Clearance Breakdown
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 10: YTD Contractor Performance Summary (Pruning & PI)
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Reference APPENDIX for Individual Contractor Monthly Performance Trend Data
VM Lead: Bill
Performance from Davey Tree Service is significantly below expectations. Initial discussions were conducted with Davey on 6/2/20 to address performance shortfalls. Compliance continues to work with DTS to develop and implement their internal QC process. DTS has employed DRG to run DTS QC program. DTS performance improved slightly from June to July
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field

## Slide 11: Quality Control for HTMP
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 12: HTMP Inspection Summary
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Reasons for rework can include: (1) work not performed, (2) mitigation not achieved, (3) poor post work site conditions
VM Lead: Bill

## Slide 13: HTMP QC Findings – Program to Date
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Work Performed Discrepancies – denotes work was performed but not per the prescribed mitigation
Work Not Performed – denotes no work was performed but was indicated as performed
  VM QA performed a “deep dive/analysis” of “work not performed” (originally 104); results of review found that:
  2 trees were delisted / no longer needing rework as initial prescription was changed
  62 were originally assigned to Core Tree Service (dropped in 2019) and reassigned to other contractors in 2020
  In some cases crews worked on wrong tree and/or entered incorrect work completion dates into Fulcrum App
  39 pending completion
VM Lead: Bill

## Slide 14: HTMP QC of Risk Assessments 1216 QC risk assessments performed in June; YTD = 4525
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
HTMP Tree Risk Calculator Scores ≥ 50 are classified as P2s and require mitigation. Risk Scores < 50 are P3s and require no mitigation
Risk score variances between HTMP QC and HTMP assessors > 15 initiate a discussion to determine potential resolution
  Changes to the risk assessment job aid have been initiated due to the variance in QC results. Training expected by end of August
YTD – 4525 Risk Assessments (RA) have been performed by QC (April 1 through July 31)
  4248 RAs were selected from P3s (score < 50). 970 of 4248 RAs were risk scored by QC as >50 (should be a P2)
    690 of the 970 had a risk score delta exceeding 15 points
  277 RAs were selected from P2s (score > 50). 74 of 277 RAs were risk scored by QC as < 50 (should be a P3)
    57 of the 277 had a risk score delta exceeding 15 points
VM Lead: Bill

## Slide 15: Compliance – Other
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 16: WMP / WSD-004 Resolution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
CPUC Resolution WSD-004: June 11, 2020 resulted in 22 deficiencies for SCE’s 2020 Wildfire Mitigation Plan
5 deficiencies were specific to Vegetation Management activities
Class A deficiencies are due on July 27, 2020 – Complete
Class B deficiencies are due on September 1, 2020
Class C deficiencies are due at with 2021 WMP update
VM Lead: Bill

## Slide 17: WMP / WSD Deficiency Responses
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Upgraded to Class A

## Slide 18: WMP / WSD Deficiency Responses
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 19: WMP / WSD Deficiency Responses
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 20: WSD WMP Audit
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
WSD has requested VM provide detailed information for the following VM WMP activities
  HTMP Assessments
  HTMP Mitigations
  Pole Brushing
  DRI
  Quality Control
  Routine Vegetation Pre-Inspection (not a WMP VM activity)
  Routine Vegetation Pruning (not a WMP VM activity)
WSD has requested bi-weekly detailed updates for:
  Work performed prior 2 weeks
  Planned work 2 weeks look forward
Detailed information includes: Tree or Pole ID, GIS Lat/Long, Status
As of 8/3/20, no specific feedback has been received from WSD, except for potential excessive foilage adjacent to a pole in Hemet. VM reviewed and determined there was no compliance issue
VM Lead: Bill

## Slide 21: ASD Audits
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
ASD Audit Y20-10104 VM Vendor Cost Review - 3 observations issued
VM Lead: Bill
ASD Audit Y20-53070 follow-up to 2019 Audit. Commenced 7/31/20

## Slide 22: SB-247 – Threshold Reporting to WSD
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Threshold met.
Notification performed
Threshold met.
Notification performed

## Slide 23: Data Requests – GRC
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
3 Data Requests were received in July
PubAdv-SCE-198 MCL
TURN- SCE-118
SBUA –SCE-002
VM Lead: Bill

## Slide 24: APPENDIX – Contractor Performance Trending
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 25: Pruning Contractor – YTD RCD Performance Trend
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
RCD = Regulation Clearance Distance
Note: Rolling Green scores should be blank for March/April – No QC was performed
VM Lead: Bill

## Slide 26: Pruning Contractor – Arborworks
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 27: Pruning Contractor – Davey Tree Experts
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 28: Pruning Contractor – Mowbrays Tree Service
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 29: Pruning Contractor – Rolling Green
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 30: Pruning Contractor – Utility Tree Service
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 31: Inspection Contractor – YTD Missed Tree Trend (Overall)
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field

## Slide 32: Inspection Contractor – ACRT
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field

## Slide 33: Inspection Contractor – CNUC
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field

## Slide 34: Inspection Contractor – Davey
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field

## Slide 35: Inspection Contractor – UPE
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Missed Tree Quantity: Amount of trees identified by QC but not listed in VM tree database
Inventory Inflation Quantity: Amount of trees listed in VM database but not located in the field