## Slide 1: VM Performance Review Meeting
June 3, 2020
overall_0_132149625091576866 columns_1_132149625091576866
Rev. 2

## Slide 2: Quality Control for Routine Compliance
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 3: QC Mileage, Sampling and Performance Targets
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
SAMPLING – 100% QC inspection is performed on 2161 circuit miles. These 2161 miles represent ≥ 80% REAX Range and present ≥ 93.87% of the risk
QUALITY: An Acceptable Quality Level of 100% RCD has been established for VM. This is the highest program expectation of all T&D QC Programs

## Slide 4: QC Mileage / Productivity HFRA / Non-HFRA / All Miles / WMP
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Lower than expected productivity is attributed to several factors:
  (1) QC not yet fully staffed (full staff expected by 6/30/20)
    QC inspected 713 circuit miles in May
  (2) training / implementation for Survey 123 in March
VM Lead: Bill

## Slide 5: YTD* VM Average Performance – Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
*YTD data reflects work completed in 2020 only. This does not include any January/February report data
QC inspection is performed on a “circuit mileage” basis. Vegetation within the selected circuit mile is assessed for compliance to UVM Program requirements. Judgmental sampling is performed to select circuit mileage with known adjacent vegetation
RCD & CCD are performance expectations / GRCD is presented “for information” related to achieving recommended CPUC clearance
ANSI Pass % is related to tree trim quality to ANSI A300 requirements – No AQL has been established for this, but feedback is provided
VM Lead: Bill

## Slide 6: YTD Trend – HFRA Vs Non-HFRA
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
RCD & CCD are performance expectations / GRCD is presented “for information” related to achieving recommended CPUC clearance

## Slide 7: YTD VM Average Performance – Transmission
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
QC inspection is performed on a “circuit mileage” basis. Vegetation within the selected circuit mile is assessed for compliance to UVM Program requirements. Judgmental sampling is performed to select circuit mileage with known adjacent vegetation
RCD & CCD are performance expectations / GRCD is presented “for information” related to achieving recommended CPUC clearance
ANSI Pass % is related to tree trim quality to ANSI A300 requirements – No AQL has been established for this, but feedback is provided

## Slide 8: YTD Contractor Performance Summary
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Reference APPENDIX for Individual Contractor Monthly Performance Trend Data
VM Lead: Bill
Performance from Davey Tree is significantly below expectations
Initial discussions were conducted with Davey on 6/2/20 to address performance shortfalls
Discussions will continue with Davey through June

## Slide 9: Quality Control for HTMP
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 10: HTMP Inspection Summary
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Reasons for rework can include: (1) work not performed, (2) mitigation not achieved, (3) poor post work site conditions
VM Lead: Bill

## Slide 11: HTMP QC Findings – Program to Date
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Work Performed Discrepancies – denotes work was performed but not per the prescribed mitigation
Work Not Performed – denotes no work was performed but was indicated as performed
  VM QA is performing a “deep dive/analysis” on the 104 instances of work not performed
VM Lead: Bill

## Slide 12: HTMP QC of Risk Assessments 792 QC risk assessments performed in MAY
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
HTMP Tree Risk Calculator Scores ≥ 50 are typically classified as P2s and require mitigation. Risk Scores < 50 are typically P3s and
require no mitigation. QC is currently developing the “threshold for action” based on differences in risk scores. Until a threshold
has been determined, risk score variances between HTMP QC and HTMP assessors > 15 will initiate a discussion to determine
next steps in resolving the variance and potential mitigation steps
VM Lead: Bill

## Slide 13: Compliance – Other
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 14: Data Requests – GRC Track 2
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
Five (5) Data Requests received from Public Advocates (all financial)
  PubAdv-SCE-145-MCL (Due 6/2/20)
    4 questions
  PubAdv-SCE-149-MW5 (Due 6/5/20)
    5 questions
  PubAdv-SCE-150-LJL (Due 6/5/20)
    10 questions
  PubAdv-SCE-154-MCL (Due 6/9/20)
    3 questions
  PubAdv-SCE-157-MW5 (Due 6/10/20)
    4 questions
VM Lead: Bill

## Slide 15: SB-247 – Threshold Reporting to WSD
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 16: QC – Compliance & CFVM Staffing
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
SCE’s QC contractor CFVM is currently staffed at 27 FTE
  We had requested CFVM staff to 32 FTE by 3/31/20
    Target was not achieved by 3/31/20
  Staffing Plan was received – CFVM now expects to achieve 32FTE by 6/30/20
    February 29 = 22 FTE (achieved)
    March 31 – 2 additional (Currently at 24)
    April 30 – 2 additional (Currently at 26): 25 active due to COVID
    May 31 – 1 additional (Currently at 27 FTE) 26 active due to COVID
Compliance Positions status
  Senior Advisor, Quality Assurance: Filled – Eric Salazar started 1/6/20
  Advisor – Quality Control: Seth Reid started 4/13/20
  Advisor – Training and Qualifications: Vee Sterling started 4/13/20
  Advisor – Regulation & Compliance: Resume Review
  Advisor – Communications: Posted Resume Review
VM Lead: Bill

## Slide 17: APPENDIX – Contractor Performance Trending
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 18: Pruning Contractor – YTD RCD Performance Trend
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
RCD = Regulation Clearance Distance
Note: Rolling Green scores should be blank for March/April – No QC was performed
VM Lead: Bill

## Slide 19: Pruning Contractor – Arborworks
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 20: Pruning Contractor – Davey Tree
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 21: Pruning Contractor – Mowbrays
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 22: Pruning Contractor – Rolling Green
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 23: Pruning Contractor – Utility Tree Service
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 24: Inspection Contractor – YTD Missed Tree Trend
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 25: Inspection Contractor – ACRT
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 26: Inspection Contractor – CNUC
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 27: Inspection Contractor – Davey
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 28: Inspection Contractor – UPE
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill