## Slide 1: VM Performance Review Meeting
May 6, 2020
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 2: Quality Control for Routine Compliance
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 3: 2020 QC Plan – Effective April 1, 2020
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 4: QC Mileage / Productivity HFRA / Non-HFRA / All Miles / WMP
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Lower than expected productivity is attributed to several factors:
  (1) QC not yet fully staffed (full staff expected by 5/31/20). QC inspected 731 circuit miles in April
  (2) Several “all-hands” training sessions performed in February
  (3) Field staff utilization for field testing of new program enhancements such as Compliance Verification
  (4) HTMP backlog reduction
  (5) training / implementation for Survey 123 in March

## Slide 5: Jan / Feb Performance - Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Note: January / February QC data is for 2019 completed work. No QC was performed on Transmission circuits in January / February and therefore not reported
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation

## Slide 6: YTD* Performance - Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
*YTD data reflects work completed in 2020 only. This does not include any January/February report data. Vegetation QC migrated to Survey123 in March
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation

## Slide 7: Explanation of Decline in April GRCD
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
March Inspections had a larger sample within non-forested service area.
April Inspections included a larger population (by percentage and quantity) of HFRA/heavily forested areas inspected (i.e. Arrowhead & Idyllwild). March = 25% total inspections in Arrowhead/Idyllwild, April = 40% Inspections Arrowhead/Idyllwild. More heavily forested areas are harder to achieve 12’ GRCD. One large Santa Barbara grid was inspected in April that brought this GRCD down as well:
Santa Barbara is well known for customer pushback on achieving 12’ clearances.
Note that the QC GRCD measurements are an “as surveyed” measurement. We are not yet reporting the “documented GRCD deviations” from this score at this time. We are still looking at the data from S123 in this area and determining AQL based on analysis…

## Slide 8: YTD* Performance - Transmission
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation
*YTD data reflects work completed in 2020 only. This does not include any January/February report data. Vegetation QC migrated to Survey123 in March

## Slide 9: Contractor Performance (CP)
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Contractor Performance is for 2020 inspections

## Slide 10: Inspection CP by District
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Contractor Performance is for 2020 inspections

## Slide 11: Acceptable Quality Levels – AQL UVM-07 Version 4, was issued April 1 2020 and incorporates “Table 4” below which identifies the AQL for contractor performance. Performance Action Plans for pruning contractors Davey, UTS and Mowbray were received 12/31/19 and VM QC has been working with these contractors to amend the plans. Based on the lag between implementing actions and QC inspection, we should see performance increases in the May/June reports, contingent on vendor actions
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 12: Quality Control for HTMP
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 13: HTMP Inspection Summary
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Reasons for rework can include: (1) work not performed, (2) mitigation not achieved, (3) poor post work site conditions

## Slide 14: HTMP QC Findings – Program to Date
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
“Work Performed Discrepancies” – denotes work was performed but not per the prescribed mitigation

## Slide 15: HTMP QC of Risk Assessments 722 QC risk assessments performed in April
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
HTMP Tree Risk Calculator Scores ≥ 50 are typically classified as P2s and require mitigation. Risk Scores < 50 are typically P3s and
require no mitigation. QC is currently developing the “threshold for action” based on differences in risk scores. Until a threshold
has been determined, risk score variances between HTMP QC and HTMP assessors > 15 will initiate a discussion to determine
next steps in resolving the variance and potential mitigation steps

## Slide 16: Compliance – Other
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 17: New Regulation Proposal: SB-1448
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 18: Data Requests – 2021 GRC & 2020 WMP
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 19: SB-247 – Threshold Reporting to WSD
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 20: QC – Compliance & CFVM Staffing
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
SCE’s QC contractor CFVM is currently staffed at 24 FTE
  We had requested CFVM staff to 32 FTE by 3/31/20
    Target was not achieved by 3/31/20
  Staffing Plan was received – CFVM now expects to achieve 32FTE by 5/31/20
    February 29 = 22 FTE (achieved)
    March 31 – 2 additional (Currently at 24)
    April 30 – 2 additional (Currently at 26): 25 active due to COVID
    May 31 – target 8 additional (32 FTE)
Compliance Positions status
  Senior Advisor, Quality Assurance: Filled – Eric Salazar started 1/6/20
  Advisor – Quality Control: Seth Reid successful candidate starts 4/13/20
  Advisor – Training and Qualifications: Vee Sterling successful candidate starts 4/13/20
  Advisor – Regulation & Compliance: Posted 4/29/20
  Advisor – Communications: Posted 4/29/20