## Slide 1: 2020 T&D Quality Management Plan
November 2020
PLAN
INITIATE
SCHEDULE
EXECUTE
CLOSE
T&D
Quality Management
QUALITY CONTROL
QUALITY ASSURANCE

## Slide 2: Executive Summary
Mike Eliason | Associated Press
George Rose | Getty Images
Josh Edelson | AFP | Getty Images
Carolyn Cole | Los Angeles Times | Getty Images
Team began design of new quality management plan in 2019 with Accenture
  Plan developed in partnership with ERM, Ethics & Compliance, and T&D
Newly designed 2020 quality management plan incorporates multiple changes:
  Quality of inspection and maintenance programs were risk ranked
  Sample size and threshold levels were determined based on risk
  Expands scope of Quality activities across the asset lifecycle
Design and implementation of high, and very-high risk programs has been the focus for 2020
Objective: Provide overview on T&D’s risk-based quality management plan and provide update on QC program results
Pre-Read

## Slide 3: 2020 quality management plan ranks programs based on the following criteria:
14
Very High
Organizational Complexity
Program Maturity
Process Complexity
Existing quality oversight from C&Q? Internal program control points and QC processes? |  | # of inputs to this program from other parts of the T&D asset lifecycle Complexity of processes in program |  | Size and breadth of the org (centralized, by district, by grid) Utilize contractors or vendors in addition to SCE |  | # of other programs in the T&D asset lifecycle with dependencies on this program
Note: Risk ranking categories and scoring criteria will continue to be key collaborative efforts between ERM and C&Q with recurring, collaborative re-calibration on an ongoing basis.
=
No existing QC checks Some internal control points and QC |  | Inputs from several programs in the asset lifecycle Multiple mapping app’s, paper & electronic data |  | Centralized operations Few contractors utilized |  | Several other programs in the T&D asset lifecycle depend on mapping, e.g. planning, construction, inspections
=
Total Program Risk Score
Risk Scores
VERY HIGH = >14
HIGH = 12 – 13
MED = 11
LOW = <10
4
4
2
4
Value of 1 – 5 per risk category higher value = greater risk
+
+
+
Downstream Impacts
Program Risk Ranking Example: Asset Management - Mapping
+
+
+
Pre-Read

## Slide 4: ERM Engagement
Mike Eliason | Associated Press
George Rose | Getty Images
Josh Edelson | AFP | Getty Images
Carolyn Cole | Los Angeles Times | Getty Images
During 2019 Quality Management Plan development, ERM worked with Quality to establish program requirements that include creating consistent risk ranking criteria for each program, incorporating risk-informed sampling methodologies, and creating actionable corrective action plans
ERM is working with Quality to calibrate/adjust the 2021 risk ranking and sampling criteria based on lessons learned from 2020 implementation, the results of individual quality programs, and findings from the EDFI project
ASD conducted audits of the QC program in 2019 and 2020, which resulted in recommendations, including:
  Implementing risk-based program scoping practices (e.g. what aspect of the program is being QC’d)
  Improvements to how QC inspection feedback is incorporated into related inspection practices (e.g. overhead and underground detail inspectors)
  Ensure to incorporate learnings into newer programs such as Transmission Detailed Inspections program rolling out in the beginning of 2021
For Discussion

## Slide 5
A multi-tiered approach is necessary to drive quality oversight throughout T&D
Internal audits
Conducted by ASD
E&C assessment of QA programs
Conducted by E&C QA group
Program-independent quality oversight
Conducted by T&D Compliance & Quality (CQ) organization
e.g. QA upstream testing of program design or QC downstream testing of controls / results
Field Verification (embedded in organization; in-process quality oversight)
Implemented by program stakeholders in the business line
i.e. ensure individual work follows all relevant controls / processes
External Audits
Conducted by external regulators
Peer reviews & Benchmarking
Conducted by peer utilities
external
Additional reviews do not replace the need for internal quality oversight by program owner(s)
Results from sampling methodology are representative of the overall population.
First line of Defense
Second line of Defense
Third line of Defense
For Discussion

## Slide 6: 2020 QC sampling plan informed by program ranking and geography
 | Risk of Geography |  |  |  |  |  |  |  |  |  |  | 
 | VERY HIGH REAX 98+ %ile (46% of REAX Risk) |  |  | HIGH REAX 90-98 %ile (35% of REAX Risk) |  |  | MEDIUM REAX 0-90 %ile (19% of REAX Risk) |  |  | LOW Non-HFRA |  | 
Risk of Program | CL | CI | TL | CL | CI | TL | CL | CI | TL | CL | CI | TL
Very High | 100.0% | 0.00% | 100.0% | 99.0% | 1.00% | 98.0% | 99.0% | 2.00% | 95.0% | 99.0% | 5.00% | 95.0%
High | 99.0% | 1.00% | 98.0% | 97.0% | 1.00% | 95.0% | 97.0% | 3.00% | 95.0% | 97.0% | 5.00% | 90.0%
Medium | 97.0% | 1.00% | 95.0% | 97.0% | 2.00% | 95.0% | 96.0% | 3.00% | 90.0% | 96.0% | 5.00% | 90.0%
Low | 95.0% | 1.00% | 95.0% | 95.0% | 2.00% | 90.0% | 95.0% | 3.00% | 90.0% | 95.0% | 5.00% | 90.0%
Distribution Construction VERY HIGH
Transmission Construction VERY HIGH
Aerial Inspections VERY HIGH
Transmission Inspections VERY HIGH
Asset Mgmt. – Mapping VERY HIGH
Maintenance Notifications VERY HIGH
Vegetation Management VERY HIGH
Overhead Detail Insp. HIGH
Distribution Planning HIGH
Intrusive Pole Insp. MEDIUM
Pole Loading Prog. MEDIUM
2020 Quality Programs
Note: Review and updating of ranking criteria, scoring, and sampling inputs (CL, CI, TL, CR) will continue to be key collaborative efforts between ERM and C&Q.
For Discussion
 | Vegetation Program Only |  |  |  |  | 
 | REAX 80+ %ile (94% of REAX Risk) |  | REAX 0-80 %ile (6% of REAX Risk) |  | Non-HFRA | 
Risk of Program - Very High | CL | CI | CL | CI | CL | CI
Transmission & Distribution HFRA | 100.0% | 0.00% | 99.0% | 1.7% | N/A | N/A
Distribution Non-HFRA | N/A | N/A | N/A | N/A | 99.0% | 3.6%
Transmission Non-HFRA | N/A | N/A | N/A | N/A | 99.0% | 4.3%

## Slide 7: Sample Size by Program and Status through October
Mike Eliason | Associated Press
George Rose | Getty Images
Josh Edelson | AFP | Getty Images
Carolyn Cole | Los Angeles Times | Getty Images
Note: COVID impacts have limited the ability to obtain field work orders which has caused delays in reaching sampling targets
For Discussion

## Slide 8: Program Performance BI Dashboard - YTD October
Other Programs - Not in BI Dashboard
* Preliminary
For Discussion

## Slide 9: Quality Results (ODI) – YTD October
For Discussion

## Slide 10: Quality Results (Dist. Construction) – YTD October
For Discussion

## Slide 11: Quality Results Dist. Construction – YTD Sept vs October
October MTD 2020
YTD, through Sept.
YTD, inc.
October
September 2020 YTD
NCs falling off the Top 10
Significant Increase in inspections from Sept (+1745)
For Discussion

## Slide 12: October YTD VM Performance – Distribution
YTD data reflects work completed in 2020 only. This does not include any January/February report data
For Discussion

## Slide 13
October YTD VM Performance – Transmission
YTD data reflects work completed in 2020 only. This does not include any January/February report data
For Discussion

## Slide 14
APPENDIX
PLAN
INITIATE
SCHEDULE
EXECUTE
CLOSE
T&D
Quality Management
QUALITY CONTROL
QUALITY ASSURANCE

## Slide 15: Quality Control of ODI
Mike Eliason | Associated Press
George Rose | Getty Images
Josh Edelson | AFP | Getty Images
Carolyn Cole | Los Angeles Times | Getty Images
What’s In Scope:
QC inspects structure in accordance with GO 95 requirements and performs inspections in accordance with ODI Program requirements.
Specifically, QC reviews the completed ODI inspections consistent with the DIMP Manual Overhead Detailed Inspection Guideline covering the condition of following components:
  Equipment, Apparatus, and Hardware
  Pole and Structures
  Conductors and Covered Conductors
  Risers, Climbing Space and General Conditions
Additionally, QC inspects the location/structures for any safety/reliability issues.
What Is Not In Scope:
Construction Standard Adherence

## Slide 16: DIMP Manual Attachment 1–1: Overhead Detailed Inspection Guideline
Mike Eliason | Associated Press
George Rose | Getty Images
Josh Edelson | AFP | Getty Images
Carolyn Cole | Los Angeles Times | Getty Images

## Slide 17
What’s in Scope?
Ignition Risks
Safety & Reliability
Adherence to Distribution Overhead Standards, GO 95
Adherence to Distribution Design Standards, Distribution Underground Standards, Electric Service Requirements* (when applicable)*
What’s NOT in Scope?
  Validation of material ordered, Joint Pole requirements, or customer connectivity (TLM)
Quality Control of Distribution Construction

## Slide 18
Programs risk-ranked in 2019 for 2020 scope consideration
Programs | Maturity Score (1-5) |  | Process Complexity Score (1-5) |  | Organizational Complexity Score (1-5) |  | Downstream Impacts Score (1-5) |  | TOTAL | Program Risk Category
Aerial Inspections | 5 | No existing QC program | 3 | Dependent on inputs from Planning (maps). Some complexity in processes - interviews needed for more information. | 3 | Limited utilization of contractors(?). Centralized effort(?). Need more information to confirm and revise ranking. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 14 | Very High
Asset Management - Mapping | 4 | No existing external QC program. Some internal QC of map updates does occur. | 4 | Dependent on inputs from Construction / Remediation, Inspections, and Maintenance. | 2 | Limited utilization of contractors. Centralized operations. | 4 | Maps are used to plan and assign work for Construction / Remediation, Inspections, and Maintenance | 14 | Very High
Distribution OH Construction | 2 | Existing QC Programs: - Pole Loading QC Inspection - Construction QC Inspection | 5 | Dependent on inputs from Planning (maps), Engineering (standards), Procurement (materials), and Inspections (remediation work). Complex processes. | 5 | Work done at district level. Utilize multiple contractors | 2 | Impacts Planning (asset updates and map updates) | 14 | Very High
Maintenance Notifications | 5 | No existing QC program or known internal controls. Interviews may determine that controls exist. | 3 | Primarily dependent on inputs from several inspection programs, but also come through asset corrections or customer complaints. More investigation needed. | 4 | Several inspection efforts feed into notifications, and remediation is done at the district (distribution) or grid (transmission) level. Contractors utilized. More investigation needed. | 2 | Impacts the accuracy and completeness of remediation work. | 14 | Very High
Transmission OH Construction | 2 | Existing QC Programs: - Pole Loading QC Inspection - Construction QC Inspection | 5 | Dependent on inputs from Planning (maps), Engineering (standards), Procurement (materials), and Inspections (remediation work). Complex processes. | 5 | Work done at district level. Utilize multiple contractors | 2 | Impacts Planning (asset updates and map updates) | 14 | Very High
Transmission Overhead Inspections | 5 | No existing QC program; however, procedures are included in the Quality Manual | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 3 | Work done at the district level. Limited utilization of contractors. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 14 | Very High
Vegetation Management | 3 | Existing QC Program: - Performed by Veg Mgmt * New program without inventory of past QC reports | 4 | Dependent on inputs from Planning (maps). Some complexity in multiple processes and 2-pass approach: inspections then trimmings. | 3 | Work done at the district level. Some utilization of contractors. | 4 | Impacts Planning (asset and map updates) and Maintenance (Veg Mgmt Trimming) | 14 | Very High
Distribution ODI (Overhead Detail Inspections) | 4 | Legacy QC program for previous iteration of ODI; ODI redesign has significant data, software and process changes. * Fewer checks than Construction, but less complexity | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 3 | Work done at the district level. Limited utilization of contractors. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 13 | High
Distribution OH Planning | 5 | No existing QC program | 1 | Main input is changes in Engineering standards - no dependencies in other parts of asset lifecycle | 3 | Both centralized and distributed among districts | 3 | Direct impact on Distribution Construction / Remediation | 12 | High
*Transmission Estimation | 5 | No existing QC program | 1 | Main input is changes in Engineering standards - no dependencies in other parts of asset lifecycle | 3 | Both centralized and distributed among districts | 3 | Direct impact on Distribution Construction / Remediation | 12 | High
*Vendor Qualification | 5 | No existing QC program | 2 | Inputs from Engineer. Potential inputs from Planning (Inspection Results) | 2 | Centralized operations. Procure material from suppliers | 3 | Direct impact on Construction / Remediation | 12 | High
Intrusive Pole Inspections | 2 | Existing QC Programs: - IPI QC Inspection * Fewer checks than Construction, but less complexity | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 3 | Work done at the district level. Utilize contractors. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 11 | Medium
Pole Loading Program | 2 | Existing QC Programs: - PLP / PLNC QC Inspections | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 3 | Work done at the district level. Utilize contractors. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 11 | Medium
Distribution UDI | 2 | Existing QC Programs: - UDI QC Inspection | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 2 | Work done at the district level by SCE resources. | 3 | Impacts Planning (asset and map updates) and Remediation (creation and prioritization of notifications) | 10 | Low
Steel Stub Repair | 2 | Existing QC Programs: - SSR QC Inspection | 3 | Dependent on inputs from Planning (maps). Some complexity in processes. | 3 | Work done at the district level. Utilize contractors. | 2 | Impacts the accuracy and completeness of remediation work. | 10 | Low
*not in scope for 2020