## Slide 1: VM Performance Review Meeting
April 6, 2020
overall_0_132149625091576866 columns_1_132149625091576866

## Slide 2: 2020 QC Plan – Effective April 1, 2020
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Stratification of QC mileage targets to 80%/20% commences with April 1 inspections

## Slide 3: QC Mileage / Productivity HFRA / Non-HFRA / All Miles / WMP
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Lower than expected productivity is attributed to several factors:
  (1) QC not yet fully staffed (full staff expected by 5/31/20)
  (2) Several “all-hands” training sessions performed in February
  (3) Field staff utilization for field testing of new program enhancements such as Compliance Verification
  (4) HTMP backlog reduction
  (5) training / implementation for Survey 123 in March

## Slide 4: Jan / Feb Performance - Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Note: January / February QC data is for 2019 completed work. No QC was performed on Transmission circuits in January / February and therefore not reported
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation

## Slide 5: March Performance - Distribution
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
March data reflects work completed in 2020 only.
Vegetation QC migrated to Survey123 in March
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation

## Slide 6: March Performance - Transmission
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
March data reflects work completed in 2020 only.
Vegetation QC migrated to Survey123 in March
Note: QC inspection is performed on a “circuit mileage” basis and all vegetation within the inspected circuit mile is assessed for
compliance to UVM Program requirements. “Judgmental” sampling is performed to select circuit mileage with known vegetation

## Slide 7: Contractor Performance Summary
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Contractor Performance is for 2020 inspections

## Slide 8: Acceptable Quality Levels – AQL UVM-07 Version 4, was issued April 1 2020 and incorporates “Table 4” below which identifies the AQL for contractor performance. Performance Action Plans for pruning contractors Davey, UTS and Mowbray were received 12/31/19 and VM QC has been working with these contractors to amend the plans. Based on the lag between implementing actions and QC inspection, we should see performance increases in the May/June reports, contingent on vendor actions
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 9: HTMP / Productivity
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
In 2019 HTMP crews performed 6406 mitigations and QC inspected 3444 of 6406 mitigations (54%), leaving a 2019 backlog of 2962 (46%) mitigations.
In 2020, QC focused efforts to reduce remediation backlog. Through 3/31/20, HTMP crews performed 10,033 total mitigations and QC inspected 8793 of 10,033 (87.6%), leaving a backlog of 1,240 (12.3%) mitigations. To achieve this reduction in backlog, QC needed to divert compliances resources.

## Slide 10: Data Requests – 2021 GRC & 2020 WMP The following Vegetation Data Requests were received in March
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 11: SB-247 – Threshold Reporting to WSD
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill

## Slide 12: 2019 WMP Compliance Evidence Status
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
Narrative and Evidence is uploaded to the Compliance WMP SharePoint site for:
  VM-1 Hazard Tree
  VM-2 Pole Brushing
  VM-3 Expanded Clearances
  VM-4 DRI
  VM-5 LiDAR
  VM-6 Quality Control
Narratives and evidence has been reviewed by E&C QA and T&D QA
Comments resolved for all activities except VM-4 (still cleaning up evidence files)

## Slide 13: QC – Compliance & CFVM Staffing
overall_0_132083107041691217 columns_2_132048702459405524 7_1_132048702466692635 10_1_132048702466852189 21_1_132048721872633283 23_1_132049640018006217 26_1_132049645698177263 29_1_132083107019594412 33_1_132083107019594412 13_1_132083204190616292
VM Lead: Bill
SCE’s QC contractor CFVM is currently staffed at 24 FTE
  We had requested CFVM staff to 32 FTE by 3/31/20
    Target was not achieved by 3/31/20
  Staffing Plan was received – CFVM now expects to achieve 32FTE by 5/31/20
    February 29 = 22 FTE (achieved)
    March 31 – 2 additional (Currently at 24)
    May 31 – target 8 additional (32 FTE)
Compliance Positions status
  Senior Advisor, Quality Assurance: Filled – Eric Salazar started 1/6/20
  Advisor – Quality Control: Seth Reid successful candidate starts 4/13/20
  Advisor – Training and Qualifications: Vee Sterling successful candidate starts 4/13/20
  Advisor – Regulations & Compliance: Pending Bill K. Action to Post
  Advisor – Regulations & Compliance: Pending Bill K. Action to Post