## VM Capital Reconciliation
Initiative | Initiative ID (Table 12) | WF 2020 (Table 25) | WF 2021 (Table 12) | Change of HFTD Classification | 2020 WMP |  |  |  | 2021 WMP |  |  |  | Delta (2021 - 2020)
[5 empty] | 2020 | 2021 | 2022 | Total | 2020 | 2021 | 2022 | Total | 2020 | 2021 | 2022 | Total | 2020 WMP Forecast vs. 2020 Actuals | 2020 WMP (Forecast 2021/2022) vs. 2021 WMP (Forecast 2021/2022)
1. Additional efforts to manage community and environmental impacts | 7.3.5.1. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4. Emergency response vegetation management due to red flag warning or other urgent conditions | 7.3.5.4. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
5. Fuel management and reduction of “slash” from vegetation management activities | 7.3.5.5. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. Improvement of inspections | 7.3.5.6. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. LiDAR inspections of vegetation around distribution electric lines and equipment | 7.3.5.7. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.5.9. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.5.10. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Recruiting and training of vegetation management personnel | 7.3.5.14. | HFTD | Non-HFTD | YES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Remediation of at-risk species | 7.3.5.15. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Removal and remediation of trees with strike potential to electric lines and equipment | 7.3.5.16. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Substation inspections | 7.3.5.17. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Substation vegetation management | 7.3.5.18. | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Vegetation inventory system | 7.3.5.19 | HFTD | HFTD | NO | 0 | 0 | 0 | 0 | 16127.8644 | 9940 | 4475 | 30542.8644 | 16127.8644 | 9940 | 4475 | 30542.8644 | Arbora: Increase due to new Arbora Technology Tool investment, emergent program post 2020 WMP filing. Survey 123: Previously Clearion replacement) mapped in 2020 WMP under Assets & Inspections mitigation "EOI Technology Support Tools" Sub-Activity (IN-1), Table 28, Initiative 4. | Arbora: Increase due to new Arbora Technology Tool investment, emergent program post 2020 WMP filing. Survey 123: Previously (Clearion replacement) mapped in 2020 WMP under Assets & Inspections mitigation "EOI Technology Support Tools" Sub-Activity (IN-1), Table 28, Initiative 4.
Total HFTD |  |  |  |  | 0 | 0 | 0 | 0 | 16127.8644 | 9940 | 4475 | 30542.8644 | 16127.8644 | 9940 | 4475 | 30542.8644
Total Non-HFTD |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 16127.8644 | 9940 | 4475 | 30542.8644 | 16127.8644 | 9940 | 4475 | 30542.8644
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## VM O&M Reconciliation
Initiative | Initiative ID (Table 12) | WF 2020 (Table 25) | WF 2021 (Table 12) | Change of HFTD Classification | 2020 WMP |  |  |  | 2021 WMP |  |  |  | Delta (2021 - 2020)
[5 empty] | 2020 | 2021 | 2022 | Total | 2020 | 2021 | 2022 | Total | 2020 | 2021 | 2022 | Total | 2020 WMP Forecast vs. 2020 Actuals | 2020 WMP (Forecast 2021/2022) vs. 2021 WMP (Forecast 2021/2022)
1. Additional efforts to manage community and environmental impacts | 7.3.5.1 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2. Detailed inspections of vegetation around distribution electric lines and equipment | 7.3.5.2 | HFTD | System Wide | YES | 11385.882 | 11396.674 | 11407.062 | 34189.618 | 25755.7217 | 15020.37 | 15470.984 | 56247.0757 | 14369.8397 | 3623.696 | 4063.922 | 22057.4577 | Original 2020 forecasted tree inspections based on lump-sum contracts, with predetermined units. Throughout 2020 inspection counts were revisited and increased, which required changing the terms of original contract, and factoring in T&E to account for incremental inspections. Increases in costs were driven by change in inspection rates, and change in inspection counts. | Reduction in costs in 2021 and 2022 reflects fewer emergent inspections expected compared to 2020. 2021 and 2022 forecasts includes the Non-HFRA of ~$4M annually and reflect rate increases that also apply to 2020.
3. Detailed inspections of vegetation around transmission electric lines and equipment | 7.3.5.3 | HFTD | System Wide | YES | 508.727 | 509.029 | 509.339 | 1527.095 | 1773.7554 | 2752.7 | 2835.281 | 7361.7364 | 1265.0284 | 2243.671 | 2325.942 | 5834.6414 | Original 2020 forecasted tree inspections based on lump-sum contracts, with predetermined units. Throughout 2020 inspection counts were revisited and increased, which required changing the terms of original contract, and factoring in T&E to account for incremental inspections. Increases in costs were driven by change in inspection rates, and change in inspection counts. | Increase in 2021 and 2022 reflect additional expected deeper trims in Transmission corridors to reach full 30' clearance.
4. Emergency response vegetation management due to red flag warning or other urgent conditions | 7.3.5.4 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
5. Fuel management and reduction of “slash” from vegetation management activities | 7.3.5.5 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing | 7.3.5.5.1 | HFTD | HFTD | NO | 4156.9252 | 4208.0555 | 4256.2018 | 12621.1826 | 7459.0831 | 8271.6173 | 6787.1583 | 22517.8587 | 3302.1579 | 4063.5618 | 2530.9564 | 9896.6761 | Expanded Pole Brushing & Removal: In 2020 WMP SCE forecasted 300K (compliance target 200k) units to be completed at a unit cost of $14. 2020 actuals reflect completion of 234K poles minus 75k compliance poles (159k poles). The unit costs recorded higher in 2020, therefore SCE adjusted the 2021 and 2022 forecast based on the revised unit costs of $44. Increase due to higher average costs from the addition of two new vendors necessary to complete scope (competitive). | Expanded Pole Brushing & Removal: Forecast increase due to higher average costs, due to competitively procuring a new vendor with a higher cost per pole
5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities | 7.3.5.5.2 | HFTD | HFTD | NO | 1217.4395 | 1055.9668 | 1088.7505 | 3362.1568 | 0 | 900 | 1089 | 1989 | -1217.4395 | -155.9668 | 0.24946 | -1373.1568 | Generation Expanded Vegetation Buffers: 2020 recorded of $881K, included in Vegetation Line Clearing actuals 7.3.5.20, for reporting purposes.
6. Improvement of inspections | 7.3.5.6 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. LiDAR inspections of vegetation around distribution electric lines and equipment | 7.3.5.7 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. LiDAR inspections of vegetation around transmission electric lines and equipment | 7.3.5.8 | HFTD | HFTD | NO | 1467.4411 | 1485.4906 | 1502.4868 | 4455.4185 | 4092.2315 | 1485.4906 | 1502.4868 | 7080.209 | 2624.7904 | 0 | 0 | 2624.7904 | LiDAR increase driven by Distribution and Transmission remediations, and minor 2019 carry over.
9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.5.9 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 7.3.5.10 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Patrol inspections of vegetation around distribution electric lines and equipment | 7.3.5.11 | HFTD | System Wide | YES | 5060.603 | 0 | 0 | 5060.603 | 0 | 0 | 0 | 0 | -5060.603 | 0 | 0 | -5060.603 | Summer Readiness Dist. cost combined in Line Clearing costs ID 7.3.5.20. | Summer Readiness Distribution forecasts costs were included in the Line Clearing forecast ID 7.3.5.20.
12. Patrol inspections of vegetation around transmission electric lines and equipment | 7.3.5.12 | HFTD | System Wide | YES | 2177.009 | 0 | 0 | 2177.009 | 0 | 0 | 0 | 0 | -2177.009 | 0 | 0 | -2177.009 | Summer Readiness Trans cost combined in Line Clearing costs ID 7.3.5.20. | Summer Readiness Transmission forecasts costs were included in the Line Clearing forecast ID 7.3.5.20.
13. Quality assurance / quality control of inspections: quality control (VM-5) | 7.3.5.13 | HFTD | HFTD | NO | 4000 | 5000 | 5000 | 14000 | 3966.0336 | 5546.7819 | 6158.9773 | 15671.7928 | -33.9664 | 546.7819 | 1158.9773 | 1671.7928 | The Dist./Trans QA Program was included in the 2020 WMP as Non-WF Program, captured in Table 25. Following the 2020 WMP Filing, the Program was expanded and classified as a WF Program driven by the dramatic increase in scope for the Veg Management program in HFRA. In the 2021 WMP Program Filing, Dist. QA was captured in WMP Table 12. | The Dist./Trans QA Program was included in the 2020 WMP as Non-WF Program, captured in Table 25. Following the 2020 WMP Filing, the Program was expanded and classified as a WF Program driven by the dramatic increase in scope for the Veg Management program in HFRA. In the 2021 WMP Program Filing, Dist. QA was captured in WMP Table 12.
14. Recruiting and training of vegetation management personnel | 7.3.5.14 | HFTD | Non-HFTD | YES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. Remediation of at-risk species | 7.3.5.15 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Removal and remediation of trees with strike potential to electric lines and equipment | 7.3.5.16 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 7.3.5.16.1 | HFTD | HFTD | NO | 54097.2977 | 59475.8515 | 72035.267 | 185608.4163 | 46684.7626 | 80722.0319 | 89161.7805 | 216568.575 | -7412.5351 | 21246.1804 | 17126.5135 | 30960.1587 | Hazard Tree Mitigation: Volume lower than forecast - arborist expertise favors removal over trimming mitigation due to risk of trees dying from the amount of trimming required to mitigate risk. Hazard Tree Program Management: Forecast associated with number of mitigations/removals. Forecast underrun due to scope reductions as a result of lower # of mitigations identified. Hazard Tree Removal: SB247 rate increases impacted original forecasts and pricing. Reduced volume of removals from forecast. Hazard Tree Inspection: 2020 Actuals driven by increase in contractor assessments. | Hazard Tree Mitigation: Increase in forecast driven by inclusion of Palm Program ($10M). Adjustments made for SB247 and related rate increases and reduced units of trimming mitigation. Hazard Tree Program Management: Reduced amount commensurate with mitigation volumes. Hazard Tree Removal: Increase in forecast driven by inclusion of SB247 and related rate increases, estimated at roughly 75%. Hazard Tree Inspection: Forecast increases driven by increased contractor assessment costs.
16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 7.3.5.16.2 | HFTD | HFTD | NO | 36470.011 | 36973.531 | 37564.933 | 111008.475 | 37604 | 43444.52 | 44747.8556 | 125796.3755 | 1133.989 | 6470.989 | 7182.9226 | 14787.9005 | In 2020 WMP filing DRI Program was included in WMP as Non-WF activity and not bundled as part of Wildfire Mitigation. DRI Program was captured in Table 25, under initiative activity 16.2, as Non-WF. Rate impacts were unknown in 2020 as noted in section 5.1.14 in the 2020 WMP Filing. 2020 WMP also noted DRI Forecast did not account SB247 rate increases and impacts. Drought was not included in 2021 WMP for the year 2020; 2020 costs will be recovered through CEMA whereas 2021 and 2022 will be part of the 2021 GRC requested VMBA. In 2021 SCE also requested for all of its Vegetation Programs, to be managed in a single balancing account. Note: 2021/2022 Costs were included in 7.3.5.20 in table 12. The costs have been separated, for purposes of this reconciliation to 2020 WMP. | In 2020 WMP filing DRI Program was included in WMP as Non-WF activity and not bundled as part of Wildfire Mitigation. DRI Program was captured in Table 25, under initiative activity 16.2, as Non-WF. Rate impacts were unknown in 2020 as noted in section 5.1.14 in the 2020 WMP Filing, noting DRI Forecast did not account SB247 rate increases and impacts. In 2021 SCE requested for all of its Vegetation Programs, to be managed in a single balancing account. Drought Removal Program (estimated $45M annually).
17. Substation inspections | 7.3.5.17 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Substation vegetation management | 7.3.5.18 | NA | NA | NO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. Vegetation inventory system | 7.3.5.19 | HFTD | HFTD | NO | 1660 | 150 | 50 | 1860 | 1055.6305 | 4152.1774 | 4690.5012 | 9898.3092 | -604.3695 | 4002.1774 | 4640.5012 | 8038.3092 | Arbora: Increase due to new Arbora Technology Tool investment, emergent program post 2020 WMP filing. Survey 123: Previously mapped in 2020 WMP under Assets & Inspections mitigation "EOI Technology Support Tools" Sub-Activity (IN-1), Table 28, Initiative 4. | Arbora: Increase due to new Arbora Technology Tool investment, emergent program post 2020 WMP filing. Survey 123: Previously mapped in 2020 WMP under Assets & Inspections mitigation "EOI Technology Support Tools" Sub-Activity (IN-1), Table 28, Initiative 4.
20. Vegetation management to achieve clearances around electric lines and equipment | 7.3.5.20 | HFTD | HFTD | NO | 76281.452 | 64169.652 | 60868.687 | 201319.791 | 233584.7285 | 187239.9936 | 192594.2755 | 613418.9976 | 157303.2765 | 123070.3416 | 131725.5885 | 412099.2066 | See workpaper 7.3.5.20 reconciliation. | See workpaper 7.3.5.20 reconciliation. SCE identified Pre-Inspections costs in this line item, and has removed the 2021 and 2022. The 2020 recorded and 2021/2022 forecasted costs have been refined to eliminate HFRA (~$11M) annually, accounted for above in 7.3.5.2 and 7.3.5.3.
Total HFTD |  |  |  |  | 198482.7876 | 184424.2504 | 194282.7273 | 577189.7652 | 334446.4699 | 331762.6127 | 346732.0352 | 1012941.1178 | 155095.9033 | 159244.0653 | 164365.7089 | 478705.6776
Total Non-HFTD |  |  |  |  | 0 | 0 | 0 | 0 | 27529.4771 | 17773.07 | 18306.265 | 63608.8121 | 8397.2561 | 5867.367 | 6389.864 | 20654.4871
Total |  |  |  |  | 198482.7876 | 184424.2504 | 194282.7273 | 577189.7652 | 361975.947 | 349535.6827 | 365038.3002 | 1076549.9299 | 163493.1594 | 165111.4323 | 170755.5729 | 499360.1647
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 7.3.5.20. Line Clearing HFRA
WMP Initiative ID 7.3.5.20 | 2020 |  | 2021 |  | 2022 |  | 3-Year | Comments
Line Clearing Reconciliation | 2020 WMP | 2021 WMP | 2020 WMP | 2021 WMP | 2020 WMP | 2021 WMP | Variance
Trims & Removals | 76.281 | 139.4286 | 64.17 | 106.4924 | 60.869 | 109.6161 | -154.2171 | Reduction from 2020 actuals to 2021/2022 forecast reflects fewer deeper trims based on achievement in 2020. 2020 vs. 2021 WMP delta of $154M (see further detail below) due to 2020 WMP forecast of $76M did not include: - System wide trims $12M (2020 only). - Distribution removals $17M (2020 only) - 2019 backlog 35k trims primarily in district 50 driven by weather conditions $12M (2020 only) - Increase in Distribution and Transmission HFRA trims, removals, and maintenance $33M - HFRA roaming $11M driven by increased rates for out-of-area contractors to maintain schedule as necessary - Other costs of $20M see details below. Note: Recorded costs system-wide are difficult to categorize into HFRA and non-HFRA as work is assigned, scheduled and performed in a bundled manner for efficiencies. Crews do not charge their time separately for HFRA and non-HFRA line clearances.
SB 247 | 0 | 83 | 0 | 66.4 | 0 | 68.2 | -217.6 | 2020 WMP does not reflect impact of SB 247, which went into effect on January 1, 2020. SB 247 effectively set higher rates for tree trimmers working on vegetation clearance near power lines for wildfire mitigation and impacts all vegetation management contracts, which needed to be adjusted to reflect the higher rates for the entire crew – from supervisors to safety coordinators.
SCE Labor | 0 | 3.5493 | 0 | 8.207 | 0 | 8.453 | -20.2093 | Costs associated with SCE labor was not included in 2020 WMP forecast. Increasing SCE personnel to enhance planning, reporting, and contractor management to adequately address continued volume and complexity of Line Clearance. Anticipate the team to be fully staffed in 2021.
Emergent Work | 0 | 7.6069 | 0 | 6.1406 | 0 | 6.3251 | -20.0726 | Costs associated with emergent work such as district maintenance or trouble tickets was not included in 2020 WMP
Total Line Clearing | 76.281 | 233.5847 | 64.17 | 187.24 | 60.869 | 192.5943 | -412.099
Scope included in 2020 WMP | [6 empty] | -371.8171
Scope not included in 2020 WMP | [6 empty] | -40.2819
-412.099
Trims & Removals | 2020 | 2021 | 2022 | 3-Year Variance | Additional comments
2020 WMP included only HFRA trims and T removals | 76 | 64 | 61 | 201 | 2020 filing starting point
System wide trims not in 2020 WMP | 12 | 0 | 0 | 12 | Based on methodology for transferring costs into FHPMA, due to inability distinguish some cost categories, estimated portion attributable to Non-HFRA.
D removals for the year 2020 not in 2020 WMP | 17 | 0 | 0 | 17 | 2020 did not include D-Removal rates
2019 backlog $35k primarily in D50 driven by weather conditions not in 2020 WMP | 12 | 0 | 0 | 12 | Did not forecast 2019 cost materializing in 2020
Increased D and T trims, removals, and maintenance incremental to 2020 WMP | 1 | 13.6093 | 18.5349 | 33.1441 | Did more units - increase of the forecasted inventory growth with deeper trims and removals.
HFRA Roaming not in 2020 WMP | 0 | 5.3646 | 5.5251 | 10.8897 | Percentage HFRA driven for work reallocation
Supplemental patrols not in 2020 WMP | 5 | 0 | 0 | 5 | Supp Patrols included in a different line item (7.3.5.11. and 12). 2021 and 2022 forecasted in $64M, and $61M, respectively.
Other costs including environmental, property owner incentives, IVMP, Non-Exempt pole, bark beetle not in 2020 WMP. | 16 | 5.195 | 7.178 | 28.373 | For 2020 includes 4 rows below.
Notifiers (Community Outreach Consultants) | 0 | 1.063 | 1.0949 | 2.1578 | Educate customers on reason for tree mitigation, and obtain approvals for mitigations.
Weed Abatement | 0 | 1.7634 | 1.8163 | 3.5798 | Manage in accordance with local governance requirements.
Allocated costs (Indirect costs) | 0 | 14.5222 | 14.9579 | 29.4801 | Allocated costs are system generated overheads, driven by default rates in the accounting system.
| 139 | 105.5175 | 110.1071 | 354.6246
|  |  | Delta | 153.3046
Note on A3: Vivien Chen: Includes roaming, T&D and others such as allocation and Summer Readiness) 2021&2022 includes pre-inspection but not 2020