## 2022 Ch. 3-2 Narrative Table
Spend in thousands $ of USD
WMP Category | 2020 | [6 empty] | 2021 | [6 empty] | 2022 |  | 2020-2022 Planned (w/2020 and 2021 actuals)
| Capital Planned | Capital Actual | Capital ∆ | O&M Planned | O&M Actual | O&M ∆ | 2020 Total Actual | Capital Planned | Capital Actual | Capital ∆ | O&M Planned | O&M Actual | O&M ∆ | 2021 Total Actual | Capital Planned | O&M Planned | Capital | O&M
Situational Awareness | 13.2 | 12 | 1.3 | 10.4 | 7.8 | 2.6 | 19.8 | 21.4 | 17.5 | 3.9 | 16.1 | 10.9 | 5.2 | 28.4 | 4 | 13.7 | 33.4 | 32.4
Grid Design and System Hardening | 549.1 | 583.2 | -34.1 | 10.4 | 4 | 6.4 | 587.2 | 830.4 | 936.5 | -106.1 | 5.6 | 1.7 | 3.9 | 938.2 | 825 | 11 | 2344.7 | 16.6
Asset Management and Inspections | 244.1 | 149.9 | 94.3 | 268.1 | 173.9 | 94.1 | 323.8 | 216.1 | 114.4 | 101.7 | 136.5 | 115.2 | 21.3 | 229.6 | 99.5 | 107.4 | 363.8 | 396.5
Vegetation Management and Inspections | - | 16.1 | -16.1 | 137.2 | 334.4 | -197.2 | 350.6 | 9.9 | 11 | -1.1 | 343.2 | 319.3 | 23.9 | 330.3 | 6.8 | 402.7 | 33.9 | 1056.5
Grid Operations and Protocols | 2 | 6.8 | -4.8 | 56.7 | 20.1 | 36.6 | 27 | 7.2 | 14.5 | -7.3 | 60.9 | 45 | 15.9 | 59.5 | 20.2 | 46.4 | 41.6 | 111.5
Data Governance | - | 1.8 | -1.8 | - | - | - | 1.8 | 15.7 | 9.3 | 6.4 | 1.1 | - | 1.1 | 9.3 | 16.5 | 4.1 | 27.6 | 4.1
Resource Allocation Methodology | - | - | - | - | 32.9 | -32.9 | 32.9 | - | - | - | 7.9 | 13.2 | -5.3 | 13.2 | - | 10.4 | - | 56.5
Emergency Planning and Preparedness | - | - | - | 12.2 | 5.9 | 6.3 | 5.9 | 0.2 | - | 0.2 | 1.7 | 3.9 | -2.2 | 3.9 | - | 9.1 | - | 19
Stakeholder Cooperation and Community Engagement | - | - | - | - | 7.8 | -7.8 | 7.8 | - | - | - | 23.4 | 27.5 | -4.1 | 27.5 | - | 35.6 | - | 70.9
New Innovations and Technologies | - | - | - | 4.7 | 0.2 | 4.6 | 0.2 | 8.4 | 3 | 5.4 | - | 0 | 0 | 3 | 7 | - | 10 | 0.2
Total | 808.5 | 769.8 | 38.6 | 499.8 | 587.1 | -87.3 | 1356.9 | 1109.4 | 1106.2 | 3.1 | 596.3 | 536.7 | 59.6 | 1643 | 978.8 | 640.4 | 2854.9 | 1764.2

## 2022 WMP-Table 12(v.25.Errata)
Utility | Southern California Edison Company | Notes:
Table No. | 12 | Risk-Spend-Efficiency (RSE) is defined as "An estimate of the cost-effectiveness of initiative, calculated by dividing the mitigation risk reduction benefit by the mitigation cost estimate based on the full set of risk reduction benefits estimated from the incurred costs."
Date Modified | 2022-04-08 | CAPEX = Capital expenditure; OPEX = Operating expenditure. In future submissions update planned spend, line miles treated, RSE, etc. with updated projections and actuals. Additional instructions can be found in QR information. | [26 empty] | 354055.2189 | -233030.9599
|  | Regarding the Territory and HFTD split requested per the 2022 WMP Update Guidelines, SCE has taken three approaches. (1) Wildfire activities – SCE deploys its wildfire activity spend to mitigate risk in the HFTD. Accordingly, spend for wildfire activities is shown as entirely within HFTD (i.e., Territory spend = HFTD spend). (2) Vegetation management to achieve clearances around electric lines and equipment – SCE is complying with the 2022 WMP Update Guidelines by setting forth these costs broken down by HFTD and Non-HFTD. SCE notes, however, that this estimate reflects SCE’s attempt to reasonably allocate these costs across its service area pursuant to respective tree counts and trim cadences in the HFTD and Non-HFTD areas, respectively. From an operational perspective, though, the same vegetation management contract crews often work in both HFTD and Non-HFTD areas, sometimes on the same days, making it difficult to precisely calculate the costs incurred in different areas. SCE further notes that from a regulatory cost recovery perspective, the CPUC’s SCE 2021 General Rate Case Final Decision (D.21-08-036) authorized a Vegetation Management Balancing Account (VMBA) that does not differentiate between HFTD and Non-HFTD areas. Accordingly, SCE records all vegetation management line clearance costs in the VMBA, irrespective of where the trims take place. (3) Non-wildfire activities – SCE does not track the HFTD vs. Non-HFTD split of its non-wildfire activities. Accordingly, all spend for these activities is simply shown in the Territory column, though this is not to imply that no spend occurs in the HFTD areas. | [16 empty] | Actual | [13 empty] | Actuals | [6 empty] | Projected | [6 empty] | Projected
[19 empty] | 1112295.703 | 649079.703 | 772975.0578 | 591817.0947 |  |  |  | 1150909.8236 | 769836.8236 | 797303.2027 | 587086.1787 |  |  |  | 1708651.9954 | 1106246.9954 | 746690.4691 | 536732.8231 | 0 |  |  | 1622314.0953 | 978848.9743 | 800279.8596 | 640402.6179 |  |  |  | 1608661.6049 | 962950.7299 | 777169.2858 | 628454.1354
Table 12: Mitigation initiative financials | [18 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | Line miles treated |  | Alternative units (if used) | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | Line miles treated |  | Alternative units (if used) | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | Line miles treated |  | Alternative units (if used) | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | Line miles to be treated |  | Alternative units (if used) | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | Line miles to be treated |  | Alternative units (if used)
[19 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD |  | Territory | HFTD | Territory | HFTD | Territory | HFTD |  | Territory | HFTD | Territory | HFTD | Territory | HFTD |  | Territory | HFTD | Territory | HFTD | Territory | HFTD |  | Territory | HFTD | Territory | HFTD | Territory | HFTD
Metric type | WMP Table # / Category | 2022 WMP Initiative # | Initiative activity | 2022 WMP ID | Primary driver targeted | Secondary driver targeted | Year initiated | Estimated RSE territory-wide | Estimated RSE in non-HFTD region | Estimated RSE in HFTD Zone 1 | Estimated RSE in HFTD Tier 2 | Estimated RSE in HFTD Tier 3 | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2019 | [6 empty] | 2020 | [6 empty] | 2021 | [6 empty] | 2022 | [6 empty] | 2023
Other | Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Risk Assessment & Mapping | 7.3.1.2 | Climate-driven risk map and modelling based on various relevant weather scenarios |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Risk Assessment & Mapping | 7.3.1.3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Risk Assessment & Mapping | 7.3.1.4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Risk Assessment & Mapping | 7.3.1.5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations | SA-1 | PSPS - for sectionalization, etc. |  | 2018 | 1.2257 | 0.54806 | N/A | 1.7263 | 1.5341 |  | GSRPBA |  |  |  |  | 4282 | 4282 | 1244.1383 | 1244.1383 |  |  | 352 | 7508.8599 | 7508.8599 | 2073.4879 | 2073.4879 |  |  | 593 | 5607.2372 | 5607.2372 | 2022.9986 | 2022.9986 |  |  | 406 | 3020.6941 | 3020.6941 | 3369.244 | 3369.244 |  |  | 175 | 1445.4262 | 1445.4262 | 3394.1187 | 3394.1187 |  |  | 95
Other | Situational Awareness & Forecasting | 7.3.2.2.1 | Continuous monitoring sensors | SA-9 |  |  | 2018 | N/A | N/A | N/A | N/A | N/A |  | GSRPBA; WMPMA |  |  |  |  | 3445 | 3445 | 154.0196 | 154.0196 |  |  | 60 | 260.4045 | 260.4045 | 215.1821 | 215.1821 |  |  | 60 | 8362.0962 | 8362.0962 | 134.7077 | 134.7077 |  |  | 130 | 100 | 100 | 299 | 299 | [5 empty] | 294.1401 | 294.1401
Other | Situational Awareness & Forecasting | 7.3.2.2.2 | Continuous monitoring sensors | SA-10 | PSPS - for sectionalization, etc. |  | 2018 | 585.6398 | 599.9016 | N/A | 551.72 | 595.7085 |  | NA |  |  |  |  | 970 | 970 | 469.0158 | 469.0158 |  |  |  | 94.0863 | 94.0863 | 2235.2265 | 2235.2265 | [5 empty] | 2993.755 | 2993.755 |  |  |  | 127.5 | 127.5 | 3906 | 3906 |  |  | 20 Additional HD Cameras | 128.9584 | 128.9584 | 4403.8691 | 4403.8691 |  |  | 20 Additional HD Cameras
Other | Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  | NA
Other | Situational Awareness & Forecasting | 7.3.2.3.2 | Forecast of a fire risk index, fire potential index, or similar | SA-8 | PSPS - for sectionalization, etc. |  | 2019 | 104.6514 | 94.2322 | N/A | 104.9088 | 113.9598 |  | NA | [6 empty] | 870.7121 | 870.7121 |  |  |  | 0 | 0 | 1635.9169 | 1635.9169 | [5 empty] | 2755.2893 | 2755.2893 | [5 empty] | 2872.801 | 2872.801 | [5 empty] | 2850.4007 | 2850.4007
Other | Situational Awareness & Forecasting | 7.3.2.4.1 | Forecast of a fire risk index, fire potential index, or similar |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Situational Awareness & Forecasting | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar |  |  |  | 2019 | N/A | N/A | N/A | N/A | N/A |  | FRMMA
Other | Situational Awareness & Forecasting | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar |  |  |  | 2020 | N/A | N/A | N/A | N/A | N/A |  | WMPMA
Other | Situational Awareness & Forecasting | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | WMPMA | [16 empty] | 14000
Other | Situational Awareness & Forecasting | 7.3.2.5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | SA-3 | PSPS - for sectionalization, etc. |  | 2018 | 114.5239 | 103.1218 | N/A | 114.8056 | 124.7104 |  | NA |  |  |  |  | 6486.703 | 6486.703 | 1384.3314 | 1384.3314 |  |  |  | 4105.9963 | 4105.9963 | 1657.6793 | 1657.6793 |  |  |  | 3500.3805 | 3500.3805 | 3014.4564 | 3014.4564 |  |  | 2 High Performance Computing Clusters (HPCC) | 703 | 703 | 3234.714 | 3234.714 |  |  | 500 Weather Stations with ML Capability |  |  | 2748.8362 | 2748.8362 |  |  | TBD
Other | Situational Awareness & Forecasting | 7.3.2.6 | Weather forecasting and estimating impacts on electric lines and equipment |  |  |  | 2018 | N/A | N/A | N/A | N/A | N/A |  | GSRPBA; WMPMA | [16 empty] | 14000
Other | Situational Awareness & Forecasting | 7.3.2.6 | Weather forecasting and estimating impacts on electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | FRMMA | [16 empty] | 14000
Grid hardening | Grid Design & System Hardening | 7.3.3.1 | Capacitor maintenance and replacement program |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | NA |  |  |  | Costs for this initiative are included as part of 7.3.4.9.1
Grid hardening | Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | SH-6 | Equipment failure | Other contact with object | 2018 | 17872.8816 | N/A | N/A | 14360.7511 | 20374.1527 |  | GSRPBA |  |  |  |  | 839 | 839 | 419.7767 | 419.7767 |  |  | 156 | 9785.6956 | 9785.6956 | -9.2988 | -9.2988 |  |  | 109 | 5152.9578 | 5152.9578 | 13.6472 | 13.6472 |  |  | 95 | 10193.0328 | 10193.0328 |  |  |  |  | 125 | 3312.2523 | 3312.2523 | 3522.5414 | 3522.5414 |  |  | 114
Grid hardening | Grid Design & System Hardening | 7.3.3.3.1 | Covered conductor installation | SH-1 | Other contact with object | Wire-to-wire contact | 2018 | WCCP: 7,884 FR Poles: 3,725 | N/A | N/A | WCCP: 6,741 FR Poles: 3,758 | WCCP: 8,630 FR Poles: 3,708 |  | GSRPBA |  |  |  | Recorded spend reflects WCCP program only, while miles also include covered conductor installed in HFTD under other programs (95, 185, and 77 miles of non-WCCP in 2019, 2020, and 2021, respectively) | 239911 | 239911 | 0 | 0 |  |  | 372 | 546151.289 | 546151.289 | 0 | 0 |  |  | 982 | 897599.925 | 897599.925 | 544.928 | 544.928 |  |  | 1504 | 719109.567 | 719109.567 | 1450 | 1450 |  |  | 1250 | 765804.9358 | 765804.9358 | 857.0888 | 857.0888 |  |  | 1250
Grid hardening | Grid Design & System Hardening | 7.3.3.3.2 | Covered conductor installation | SH-10 | Equipment failure | Other contact with object | 2018 | 12847.1478 | 9794.5596 | N/A | 8369.8423 | 15264.6716 |  | GSRPBA |  |  |  |  | 9378 | 9378 |  |  |  |  | 101 | 9653.5501 | 9653.5501 | 0 | 0 |  |  | 405 | 21939.7977 | 21939.7977 |  |  |  |  | 527 | 16552.088 | 16552.088 |  |  |  |  | 700 | 16265.4667 | 16265.4667 |  |  |  |  | 500
Grid hardening | Grid Design & System Hardening | 7.3.3.3.3 | Covered conductor installation | SH-16 | Other contact with object | Wire-to-wire contact | 2022 | 537.9277 | N/A | N/A | N/A | 537.9277 |  | NA | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 108.096 | 108.096 |  |  |  |  | 115 | 388.6209 | 388.6209 |  |  |  |  | 402
Grid hardening | Grid Design & System Hardening | 7.3.3.4 | Covered conductor maintenance |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.4.9.1
Grid hardening | Grid Design & System Hardening | 7.3.3.5 | Crossarm maintenance, repair, and replacement |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.4.9.1
Grid hardening | Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | NA |  |  |  |  | 359296 | [6 empty] | 283684 | [6 empty] | 503097 | [6 empty] | 544811.836 | [6 empty] | 544462.377
Grid hardening | Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement | SH-4 | Equipment failure | Other contact with object | 2018 | 3766.9299 | 1143.1756 | N/A | 2917.6174 | 4213.3582 |  | GSRPBA |  |  |  |  | 70298 | 70298 | 258.1237 | 258.1237 |  |  | 7765 | 8955.266 | 8955.266 | 3261.7993 | 3261.7993 |  |  | 3025 | -478.5509 | -478.5509 | 35.8273 | 35.8273 |  |  | 352 |  |  | 1402.0359 | 1402.0359 |  |  | 483 |  |  | 1662.1433 | 1662.1433 |  |  | 574
Grid hardening | Grid Design & System Hardening | 7.3.3.8.1 | Grid topology improvements to mitigate or reduce PSPS events | SH-7 |  |  | 2020 | N/A | N/A | N/A | N/A | N/A | [5 empty] | This activity entails evaluating circuits highly impacted by PSPS to develop targeted plans for grid hardening and circuit modifications to reduce PSPS impact; cost resulting from this evaluation appear in 7.3.3.3.1, 7.3.3.9 and 7.3.2.1. | [7 empty] | 0 | 0 | 0 | 0 | [9 empty] | 140 Circuits identified for scoping | [6 empty] | 70 Circuits identified for scoping | [6 empty] | TBD
Grid hardening | Grid Design & System Hardening | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events | SH-12 |  |  | 2021 | N/A | N/A | N/A | N/A | N/A |  | MGOIR | [11 empty] | 0 | 0 | 0 | 0 | [10 empty] | 5393.1033 | 5393.1033 | [5 empty] | 5742.9355 | 5742.9355
Grid hardening | Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment | SH-5 | Equipment failure | Other contact with object | 2018 | RAR: 4,946 RCS: 2,981 | RAR: 581 RCS: 2,237 | N/A | RAR: 2,889 RCS: 1,406 | RAR: 7,810 RCS: 4,597 |  | GSRPBA; FHPMA |  |  |  |  | 11112 | 11112 | 0 | 0 |  |  | 71 | 5866.6214 | 5866.6214 | 0 | 0 |  |  | 49 | 2135.5269 | 2135.5269 |  |  |  |  | 23 | 3615.3046 | 3615.3046 |  |  |  |  | 31 | TBD | TBD |  |  |  |  | TBD
Grid hardening | Grid Design & System Hardening | 7.3.3.10 | Maintenance, repair, and replacement of connectors, including hotline clamps |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.4.9.1
Grid hardening | Grid Design & System Hardening | 7.3.3.11 | Mitigation of impact on customers and other residents affected during PSPS event |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs associated with mitigation of impact on customers during PSPS events are included in 7.3.6.6
Grid hardening | Grid Design & System Hardening | 7.3.3.12 | Other corrective action | SH-14 | Wire-to-wire contact | Equipment failure | 2019 | 3496.2075 | N/A | N/A | 2085.8154 | 4922.8943 |  | WMPMA |  |  |  | Additional 2021 recorded spend for this activity is included in 7.3.3.3.1 and 7.3.4.9.1 |  |  | 0 | 0 |  |  |  | 0 | 0 | 554.1823 | 554.1823 |  | 9715 |  | 91.6682 | 91.6682 |  |  |  |  | 361 | 4931.4948 | 4931.4948 | 5815.2757 | 5815.2757 |  |  | 1800 | 7617.1841 | 7617.1841 | 10479.2622 | 10479.2622 |  |  | 3586.8749
Grid hardening | Grid Design & System Hardening | 7.3.3.12.2 | Other corrective action | SH-17 | Other contact with object | Equipment failure | 2020 | 28789.4625 | 0 | N/A | N/A | 29617.8791 |  | NA | [11 empty] | 1854.5692 | 1854.5692 | 0 | 0 |  |  |  | 2707.16 | 2707.16 |  |  |  |  | 1GFN | 10596.2 | 10596.2 |  |  |  |  | 1 Iso Bank | 23917.0802 | 23917.0802 |  |  |  |  | 1 GFN
Grid hardening | Grid Design & System Hardening | 7.3.3.13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | NA |  |  |  | This is captured on Initiative 7.3.3.6.; under Distribution Pole Remediations
Grid hardening | Grid Design & System Hardening | 7.3.3.14 | Transformers maintenance and replacement |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | NA |  |  |  |  | 102432 |  | 1162.8619 |  |  |  |  | 96432 |  | 1399.415 |  |  |  |  | 97069 |  | 1274.8208 |  |  |  |  | 98653.285 |  | 1482.3676 |  |  |  |  | 101248.498 |  | 1521.144
Grid hardening | Grid Design & System Hardening | 7.3.3.15 | Transmission tower maintenance and replacement | SH-13 | Contamination | Equipment failure | 2020 | 40.8334 | N/A | N/A | 2.3353e-14 | 64.1668 |  | WMPMA |  |  |  | Recorded 2021 spend for this activity is included in 7.3.4.10 |  |  | 0 | 0 | [16 empty] | 52 |  |  | 250 | 250 |  |  | 21 | 0 | 0 |  |  |  |  | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment | SH-2 | Other contact with object | Wire-to-wire contact | 2019 | 1182 | N/A | N/A | 1783.8319 | 1374.8826 |  | WMPMA | [11 empty] | 961.3883 | 961.3883 | 0 | 0 |  |  |  | 6585.8 | 6585.8 |  |  |  |  | 5.8 | 51960 | 51960 |  |  |  |  | 13 | 42664.2434 | 42664.2434 |  |  |  |  | 11
Grid hardening | Grid Design & System Hardening | 7.3.3.17.1 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-8 | Equipment failure | Vandalism / Theft | 2019 | 0 | N/A | N/A | 24.5338 | 904.6407 |  | WMPMA | [6 empty] | 0 | 0 |  |  | 1 | 0 | 0 | 124.6627 | 124.6627 |  |  | 6 |  |  | 945.9043 | 945.9043 |  |  | 10 |  |  | 1384 | 1384 |  |  | 11 | TBD | TBD |  |  |  |  | TBD
Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-11 | Equipment failure | Other contact with object | 2019 | 202.6623 | N/A | N/A | 55.3253 | 286.8549 |  | WMPMA | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 73.8882 | 73.8882 |  | 9715 |  | 189.9301 | 189.9301 | 132.4202 | 132.4202 |  |  | 2 Projects, 17 Assessments | 1925 | 1925 | 660 | 660 |  |  | 8 Projects, 13 Assessments | 1799.5693 | 1799.5693 | 199.185 | 199.185 |  |  | TBD
Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-15 | Equipment failure |  | 2019 | 5.3458 | N/A | N/A | 0 | 14.5099 |  | WMPMA | [6 empty] | 0 | 0 | [10 empty] | 602.3923 | 602.3923 |  |  |  |  | 16 | 570.1921 | 570.1921 |  |  |  |  | 25 | 374.6638 | 374.6638 |  |  |  |  | 7
Asset inspection | Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment |  |  |  | NA | N/A | N/A | N/A | N/A | N/A | [8 empty] | 21681 | [6 empty] | 26362 | [6 empty] | 26522
Asset inspection | Asset Management & Inspections | 7.3.4.2 | Detailed inspections of transmission electric lines and equipment |  |  |  | NA | N/A | N/A | N/A | N/A | N/A | [8 empty] | 3599 | [6 empty] | 5957 | [6 empty] | 5759
Asset inspection | Asset Management & Inspections | 7.3.4.3 | Improvement of inspections | IN-8 |  |  | 2021 | Enabling | Enabling | Enabling | Enabling | Enabling |  | WMPMA |  |  |  |  | 13391 | 13391 | 1978.5651 | 1978.5651 |  |  |  | 28718.5992 | 28718.5992 | 14972.098 | 14972.098 |  | 9715 |  | 18586.3693 | 18586.3693 | 3727.0452 | 3727.0452 |  |  |  | 9504 | 9504 | 3954.7 | 3954.7 |  |  |  | 4700 | 4700 | 3146.7 | 3146.7
Asset inspection | Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment | IN-3 | Equipment failure |  | 2017 | 560.4208 | N/A | N/A | 534.6492 | 567.4494 |  | Previously GSRPBA, Currently WMPMA | [6 empty] | 0 | 0 |  |  | 4962 | 0 | 0 | 790.7734 | 790.7734 |  | 4416 | 5900 |  |  | 464.0306 | 464.0306 |  |  | 4410 |  |  | 426.559 | 426.559 |  |  | 4400 |  |  | 430.1154 | 430.1154 |  |  | 4425
Asset inspection | Asset Management & Inspections | 7.3.4.5 | Infrared inspections of transmission electric lines and equipment | IN-4 | Equipment failure |  | 2019 | 0 | N/A | N/A | 0 | N/A |  | WMPMA | [6 empty] | 0.58991 | 0.58991 |  |  | 6700 | 0 | 0 | 383.5504 | 383.5504 |  | 1005 |  |  |  | 93.6193 | 93.6193 |  |  | 1046 |  |  | 208.687 | 208.687 |  |  | 1000 |  |  | 219.4712 | 219.4712 |  |  | 1000
Asset inspection | Asset Management & Inspections | 7.3.4.5.1 | Transmission Conductor & Splice Assessment | IN-9 | Equipment failure |  | 2022 | 0 | N/A | N/A | 0 | N/A |  | NA | [6 empty] | 0 | 0 | [19 empty] | 1500 | 1500 |  |  | 150 spans w/ Line Vue, 70 splices with X-Ray, 15 Conductor Samples |  |  | 1493.8875 | 1493.8875 |  |  | 150 spans w/ Line Vue, 70 splices with X-Ray, 15 Conductor Samples
Asset inspection | Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | Base O&M | [6 empty] | 5915.0898 |  |  |  | 147770 |  |  | 6133.0551 |  |  |  | 146621 |  |  | 5966.1738 |  |  |  | 144122 |  |  | 6951.5021 |  |  |  | 143600 |  |  | 7143.9993 |  |  |  | 143600
Asset inspection | Asset Management & Inspections | 7.3.4.7 | LiDAR inspections of distribution electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.5.7
Asset inspection | Asset Management & Inspections | 7.3.4.8 | LiDAR inspections of transmission electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.5.8
Asset inspection | Asset Management & Inspections | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | IN-1.1 | Equipment failure | Other contact with object | 2018 | Distribution Ground: 2,668 Distribution Aerial: 856 | N/A | N/A | Distribution Ground: 2,712 Distribution Aerial: 921 | Distribution Ground: 2,643 Distribution Aerial: 818 |  | Previously FRMMA; GSRPBA; Currently WMPMA |  |  |  |  | 229992 | 229992 | 238512.2349 | 238512.2349 |  |  | 499192 | 85218.9688 | 85218.9688 | 105553.2628 | 105553.2628 |  |  | 367067 | 82457.7078 | 82457.7078 | 85924.8595 | 85924.8595 |  |  | 359947 | 67995.0849 | 67995.0849 | 78699.7743 | 78699.7743 |  |  | 359988 | 61871.5271 | 61871.5271 | 78274.4968 | 78274.4968 |  |  | 360000
Asset inspection | Asset Management & Inspections | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | IN-5 | Equipment failure | Other contact with object | 2019 | See IN-1.1 | See IN-1.1 | See IN-1.1 | See IN-1.1 | See IN-1.1 |  | NA | [6 empty] | 642.6569 | 642.6569 |  |  | 449 | 0 | 0 | 402.545 | 402.545 |  |  | 268 |  |  | 149.3921 | 149.3921 |  |  | 238 |  |  | 70 | 70 |  |  | 190 |  |  | 68.8622 | 68.8622 |  |  | 190
Asset inspection | Asset Management & Inspections | 7.3.4.10 | Other discretionary inspection of transmission electric lines and | IN-1.2 | Equipment failure | Other contact with object | 2018 | Transmission Ground: 1,076 Transmission Aerial: 579 | N/A | N/A | Transmission Ground: 1,045 Transmission Aerial: 572 | Transmission Ground: 1,117 Transmission Aerial: 583 |  | Previously FRMMA; GSRPBA; Currently WMPMA |  |  |  |  | 52990 | 52990 | 58418.4023 | 58418.4023 |  |  | 89581 | 35934.3099 | 35934.3099 | 51820.2961 | 51820.2961 |  |  | 66942 | 13380.4806 | 13380.4806 | 24801.6854 | 24801.6854 |  |  | 41614 | 21962.6197 | 21962.6197 | 22559.69 | 22559.69 |  |  | 38000 | 11952.8662 | 11952.8662 | 21044.8234 | 21044.8234 |  |  | 37994.6685
Asset inspection | Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment |  |  |  | NA | N/A | N/A | N/A | N/A | N/A | [8 empty] | 23849 | [6 empty] | 25218 | [6 empty] | 27315
Asset inspection | Asset Management & Inspections | 7.3.4.12 | Patrol inspections of transmission electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2733 | [6 empty] | 3567 | [6 empty] | 4561
Asset inspection | Asset Management & Inspections | 7.3.4.13 | Pole loading assessment program to determine safety factor |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | PLP Balancing Account | [6 empty] | 21259.9617 |  |  |  | 189565 |  |  | 15132.5628 |  |  |  | 125714 |  |  | 3741.5518 |  |  |  | 20066 |  |  | 496.5345 |  |  |  | 2000
Asset inspection | Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs for this initiative are included as part of 7.3.4.9.1 and 7.3.4.10
Asset inspection | Asset Management & Inspections | 7.3.4.15 | Substation inspections |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | NA | [6 empty] | 5452 | [6 empty] | 5704 | [6 empty] | 4209
Vegetation management project | Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | 0 | 0 | 0 | [5 empty] | 20598.7345 | 20598.7345 | [5 empty] | 16709.557 | 16709.557 | [5 empty] | 16641.4651 | 16641.4651
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections and management practices for vegetation clearances around distribution electrical lines and equipment. |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | Previously Na, Currently VMBA | [6 empty] | 58597.893 | [6 empty] | 25755.7217 | 16432.1505 |  |  | 470k (Trees in HFTD) |  |  | 24943.457 | 15913.9256 |  |  | 600k (Trees in HFTD) |  |  | 23241.523 | 14828.0917 |  |  | 600k (Trees in HFTD) |  |  | 23740.1568 | 15146.22 |  |  | 600k (Trees in HFTD)
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.3 | Detailed inspections and management practices for vegetation clearances around transmission electrical lines and equipment |  |  |  | NA | N/A | N/A | N/A | N/A | N/A |  | Previously Na, Currently VMBA | [6 empty] | 34355.169 | [6 empty] | 1773.7554 | 1131.6559 |  |  | 180k (Trees in HFTD) |  |  | 2345.2406 | 1496.2635 |  |  | 190k (Trees in HFTD) |  |  | 4675.155 | 2982.7489 |  |  | 100k (Trees in HFTD) |  |  | 4594.117 | 2931.0466 |  |  | 100k (Trees in HFTD)
Vegetation management project | Vegetation Management & Inspections | 7.3.5.4 | Emergency response vegetation management due to red flag warning or other urgent weather conditions |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | This activity is not individually tracked. Associated costs and units are captured in VM-2
Vegetation management project | Vegetation Management & Inspections | 7.3.5.5.1 | Fuel management (including all wood management) and management of “slash” from vegetation management activities | VM-2 | Contact with vegetation | Equipment failure | 2019 | 2925 | N/A | N/A | 6232.686 | 6127.2228 |  | Previously WMPMA, Currently VMBA |  |  |  | Cost forecasts also include some transmission poles |  |  | 1654.651 | 1654.651 |  |  | 160000 | 0 | 0 | 7459.0831 | 7459.0831 |  |  | 230000 |  |  | 11026.1923 | 11026.1923 |  |  | 163100 |  |  | 20589 | 20589 |  |  | 170k Exempt Distribution Poles, 55k Non-Exempt Distribution Poles |  |  | 21240 | 21240 |  |  | 170k Exempt Distribution Poles, 55k Non-Exempt Distribution Poles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.5.2 | Fuel management (including all wood management) and management of “slash” from vegetation management activities | VM-3 | Contact with vegetation |  | 2019 | 0.023026 | N/A | N/A | 0.0056821 | 0.031321 |  | Previously FHPMA, Currently VMBA | [11 empty] | 0 | 0 | 0 | 0 |  |  | 61 |  |  | 349.1998 | 349.1998 |  |  | 62 |  |  | 1185 | 1185 |  |  | 32 |  |  | 280.3676 | 280.3676
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.6 | Improvement of inspections |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.7 | Remote sensing inspections of vegetation around distribution electric lines and equipment. |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [22 empty] | 1180.9259 | 1180.9259 |  |  | 90 Circuit Miles |  |  | 3182 | 3182 |  |  | 500 Circuit Miles |  |  | 3224.1885 | 3224.1885 |  |  | 500 Circuit Miles
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.8 | Remote sensing inspections of vegetation around transmission electric lines and equipment |  |  |  | 2019 | N/A | N/A | N/A | N/A | N/A |  | Previously WMPMA, Currently VMBA | [6 empty] | 4532.306 | 4532.306 |  |  | 1570 Circuit Miles | 0 | 0 | 4092.2315 | 4092.2315 |  | 1227 | 1700 Circuit Miles |  |  | 3180.2748 | 3180.2748 |  |  | 1590 Circuit Miles |  |  | 2048.254 | 2048.254 |  |  | 1600 Circuit Miles |  |  | 1902.8011 | 1902.8011 |  |  | 1600 Circuit Miles
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.9 | Other discretionary inspections of vegetation around distribution electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspections of vegetation around transmission electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | Previously Na, Currently VMBA | [27 empty] | 18283.2 | 18283.2 | [5 empty] | 18831.7 | 18831.7
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.12 | Patrol inspections of vegetation around transmission electric lines and equipment |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | Previously Na, Currently VMBA | [20 empty] | 29 | 29 | [5 empty] | 962.27 | 962.27 | [5 empty] | 991.14 | 991.14
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation management | VM-5 |  |  | 2019 | [6 empty] | Previously WMPMA, Currently VMBA | [6 empty] | 989.08 | 989.08 |  |  |  | 0 | 0 | 3966.0336 | 3966.0336 |  | 14000 |  |  |  | 3221.2003 | 3221.2003 | [5 empty] | 6158.977 | 6158.977 |  |  | 8000 Circuit Miles |  |  | 6571.2834 | 6571.2834 |  |  | 8000 Circuit Miles
Vegetation management project | Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Recruiting costs for Vegetation Management activities are captured in general labor.
Vegetation management project | Vegetation Management & Inspections | 7.3.5.15 | Identification and remediation of “at-risk species” |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Vegetation management project | Vegetation Management & Inspections | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment | VM-1 | Contact with vegetation |  | 2018 | 2818.4725 | N/A | N/A | 2944.4437 | 2568.3354 |  | Previously GSRPBA, Currently VMBA | [6 empty] | 15271.118 | 15271.118 |  |  | 130,000 trees assessed | 0 | 0 | 46684.7626 | 46684.7626 |  |  | 100,000 trees assessed |  |  | 32431.8218 | 32431.8218 |  |  | 131,400 trees assessed |  |  | 42636.0585 | 42636.0585 |  |  | 330 circuits assessed |  |  | 45358.9017 | 45358.9017 |  |  | 200 circuits assessed
Vegetation management project | Vegetation Management & Inspections | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment | VM-4 | Contact with vegetation |  | NA | 8915.2333 | N/A | N/A | 9307.0233 | 8805.5321 | [8 empty] | 31157.755 | 30413.385 |  |  | 13,500 removals identified | 0 | 0 | 37604 | 37604 |  |  | 9,000 removals identified |  |  | 16165.0627 | 16165.0627 |  |  | 1,301 circuits assessed |  |  | 31257.625 | 31257.625 |  |  | 900 circuits assessed |  |  | 36212.075 | 36212.075 |  |  | 900 circuits assessed
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.17 | Substation inspection |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Vegetation management project | Vegetation Management & Inspections | 7.3.5.18 | Substation vegetation management |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Associated costs are captured in 7.3.5.2 | [27 empty] | 169 Substations Inspected
Vegetation management project | Vegetation Management & Inspections | 7.3.5.19 | Vegetation management enterprise system | VM-6 |  |  | 2021 | Enabling | Enabling | Enabling | Enabling | Enabling |  | Previously WMPMA; GSRPBA, Currently VMBA |  |  |  |  | 4219 | 4219 | [5 empty] | 16127.8644 | 16127.8644 | 1055.6305 | 1055.6305 |  |  |  | 11005.183 | 11005.183 | 634.5483 | 634.5483 |  |  |  | 6800 | 6800 | 3500 | 3500 |  |  |  | 2300 | 2300 | 3800 | 3800
Vegetation management project | Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment |  | Contact with vegetation |  | NA | 269.7944 | N/A | N/A | 280.9216 | 262.7166 |  | Previously FHPMA, Currently VMBA | [6 empty] | 169222.954 | 167414.3362 | [5 empty] | 326799.0489 | 216020.7285 | [5 empty] | 333802.071 | 213071.48 | [5 empty] | 379262.2695 | 238421.2695 | [5 empty] | 347246.4857 | 217453.4857
Vegetation management project | Vegetation Management & Inspections | 7.3.5.21 | Vegetation management activities post-fire |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Grid Operations & Operating Protocols | 7.3.6.1 | Automatic recloser operations |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [6 empty] | 1488 | [6 empty] | 957 | [6 empty] | 2239
Other | Grid Operations & Operating Protocols | 7.3.6.2 | Protective equipment and device settings. |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | NA
Other | Grid Operations & Operating Protocols | 7.3.6.3 | Crew-accompanying ignition prevention and suppression resources and services |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Grid Operations & Operating Protocols | 7.3.6.4 | Personnel work procedures and training in conditions of elevated fire risk |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Grid Operations & Operating Protocols | 7.3.6.5 | Protocols for PSPS re-energization |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [8 empty] | 1375.062 | 1375.062 |  |  |  | 0 | 0 | 111.1972 | 111.1972 | [5 empty] | 393.8326 | 393.8326 | [5 empty] | 708.984 | 708.984 | [5 empty] | 737.9008 | 737.9008
Other | Grid Operations & Operating Protocols | 7.3.6.6 | PSPS events and mitigation of PSPS impacts | PSPS-2 | PSPS - for sectionalization, etc. |  | 2018 | 211 Partnership: 35 Rebates: 4 CCBB: 2 CRC/CCV: 1 | 211 Partnership: 31 Rebates: 4 CCBB: 3 CRC/CCV: 1 | N/A | 211 Partnership: 35 Rebates: 5 CCBB: 2 CRC/CCV: 1 | 211 Partnership: 38 Rebates: 3 CCBB: 2 CRC/CCV: 1 |  | Previously GSRPBA; FRMMA; WMPMA, Currently FRMMA; WMPMA |  |  |  |  | 585 | 585 | 1905.71 | 1905.71 |  |  | 13 CRCs | 6843.2439 | 6843.2439 | 11092.3173 | 11092.3173 |  | 14000 | 56 CRCs, 720 CCBB Batteries, 1041 Rebates | 3284.8591 | 3284.8591 | 25631.7746 | 25631.7746 |  |  | 64 CRCs, 6021 CCBB Batteries, 2427 Rebates | 7560 | 7560 | 28130.8715 | 28130.8715 |  |  | 2,750 CCBB Customers, 4,000 Battery Rebates |  |  | 22894.2379 | 22894.2379 |  |  | 2,750 CCBB Customers, 4,000 Battery Rebates
Other | Grid Operations & Operating Protocols | 7.3.6.6.1 | PSPS Incident Management Team | [10 empty] | NA | [6 empty] | 5774.3076 | 5774.3076 |  |  |  | 0 | 0 | 8934.7569 | 8934.7569 |  |  |  | 11217.1415 | 11217.1415 | 14811.9333 | 14811.9333 |  |  |  | 12650 | 12650 | 14952.5984 | 14952.5984 |  |  |  | 4550 | 4550 | 15986.77 | 15986.77
Other | Grid Operations & Operating Protocols | 7.3.6.6.2.1.2 | Customer Resiliency Programs | [10 empty] | NA | [6 empty] | 0 | 0 | [12 empty] | 37.4229 | 37.4229
Other | Grid Operations & Operating Protocols | 7.3.6.6.2.1.3 | Customer Resiliency Equipment | [10 empty] | NA | [6 empty] | 11.2441 | 11.2441 |  |  |  | 0 | 0 | 4.0456 | 4.0456 | [5 empty] | 4138.2079 | 4138.2079 | [5 empty] | 2595.461 | 2595.461 | [5 empty] | 1999.707 | 1999.707
Other | Grid Operations & Operating Protocols | 7.3.6.7 | Stationed and on-call ignition prevention and suppression resources and services |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Data Governance | 7.3.7.1 | Centralized repository for data | DG-1 |  |  | 2021 | Enabling | Enabling | Enabling | Enabling | Enabling |  | Previously GSRPBA, Currently WMPMA |  |  |  |  | 1181 | 1181 | 0 | 0 |  |  |  | 1796.1108 | 1796.1108 | 0 | 0 |  | 14000 |  | 9340.933 | 9340.933 | [5 empty] | 16487 | 16487 | 4132 | 4132 |  |  |  | 8115 | 8115 | 5660 | 5660
Other | Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Data Governance | 7.3.7.3 | Documentation and disclosure of wildfire-related data and algorithms |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Data Governance | 7.3.7.4 | Tracking and analysis of near miss data |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Resource Allocation Methodology | 7.3.8.1 | Allocation methodology development and application |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | Previously FRMMA; WMPMA, Currently WMPMA | [6 empty] | 42643.8299 | 42643.8299 |  |  |  | 0 | 0 | 32860.3867 | 32860.3867 |  | 14000 |  |  |  | 13245.9608 | 13245.9608 | [5 empty] | 10371.72 | 10371.72 | [5 empty] | 10644.1792 | 10644.1792
Other | Resource Allocation Methodology | 7.3.8.2 | Risk reduction scenario development and analysis |  |  |  | 2018 | N/A | N/A | N/A | N/A | N/A
Other | Resource Allocation Methodology | 7.3.8.3 | Risk spend efficiency analysis |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration | DEP-2 | PSPS - for sectionalization, etc. |  | 2018 | UAS: 2,119 IMT/ Field Training: 262 | UAS: 2,322 IMT/ Field Training: 236 | N/A | UAS: 3,225 IMT/ Field Training: 263 | UAS: 1,872 IMT/ Field Training: 285 |  | WMPMA | [6 empty] | 1444.9391 | 1444.9391 |  |  |  | 0 | 0 | 615.6675 | 615.6675 |  |  | 44 UAS Operators Trained |  |  | 376.5885 | 376.5885 |  |  | 60 UAS Operators Trained |  |  | 1776.801 | 1776.801 |  |  | 50 UAS Operators Trained |  |  | 1862.7654 | 1862.7654 |  |  | 50 UAS Operators Trained
Other | Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs included in 7.3.10.1.2
Other | Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs included in 7.3.10.1.2
Other | Emergency Planning & Preparedness | 7.3.9.4 | Disaster and emergency preparedness plan |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [5 empty] | Costs included in 7.3.6.6.1
Other | Emergency Planning & Preparedness | 7.3.9.5 | Preparedness and planning for service restoration |  |  |  | 2018 | N/A | N/A | N/A | N/A | N/A |  | Previously GSRPBA, Currently WMPMA | [6 empty] | 9414.0643 | 9414.0643 |  |  |  | 0 | 0 | 5327.909 | 5327.909 |  | 14000 |  |  |  | 3529.6374 | 3529.6374 | [5 empty] | 7336.548 | 7336.548 | [5 empty] | 7386.3799 | 7386.3799
Other | Emergency Planning & Preparedness | 7.3.9.6 | Protocols in place to learn from wildfire events |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.1 | Community engagement | DEP-1.2 |  |  | 2018 | Enabling | Enabling | Enabling | Enabling | Enabling |  | Previously GSRPBA, Currently WMPMA | [6 empty] | 754.5978 | 754.5978 |  |  | 13 | 0 | 0 | 141.9413 | 141.9413 |  |  | 9 |  |  | 10.7665 | 10.7665 |  |  | 11 |  |  | 109.9585 | 109.9585 |  |  | 9 |  |  | 111.9378 | 111.9378 |  |  | 9
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.2 | Community engagement | DEP-1.3 |  |  | 2018 | Enabling | Enabling | Enabling | Enabling | Enabling |  | Previously FRMMA; GSRPBA, Currently WMPMA | [6 empty] | 4515.6467 | 4515.6467 |  |  |  | 0 | 0 | 5489.5082 | 5489.5082 |  | 14000 |  |  |  | 9100 | 9100 | [5 empty] | 11443.008 | 11443.008 | [5 empty] | 11489.2529 | 11489.2529
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.3 | Community engagement | DEP-4 |  |  | 2018 | N/A | N/A | N/A | N/A | N/A |  | Previously FRMMA, Currently WMPMA | [6 empty] | -650.8003 | -650.8003 |  |  |  | 0 | 0 | 0 | 0 |  |  | 5 |  |  | 856.0773 | 856.0773 |  |  | 9 |  |  | 6038.135 | 6038.135 |  |  | 6 |  |  | 6298.9579 | 6298.9579 |  |  | 6
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.3 | Cooperation with suppression agencies | DEP-5 |  |  | 2020 | 8478.0353 | N/A | N/A | 6557.2567 | 9845.9764 |  | WMPMA | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 2158 | 2158 |  |  | 1 |  |  | 17545 | 17545 |  |  | 3 MOUs |  |  | 18000 | 18000 |  |  | 5 |  |  | 17707.43 | 17707.43 |  |  | 5
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.4 | Forest service and fuel reduction cooperation and joint roadmap |  |  |  |  | N/A | N/A | N/A | N/A | N/A
Other | Alternative Technologies | 7.1.E | Alternative Technology Pilot Programs |  | Wire-to-wire contact | Equipment failure | 2018 | 9169.466 | N/A | N/A | 7058.7556 | 10321.2707 |  | Previously GSRPBA; Currently WMPMA |  |  |  | Drivers and RSEs reflective of Early Fault Detection only |  |  | 1.0507 | 1.0507 |  |  |  | 0 | 0 | 158.9205 | 158.9205 |  | 14000 |  | 2978 | 2978 | 2.4257 | 2.4257 |  |  |  | 6984.997 | 6984.997
Note on AK79: Jen Medina: 2/15/22: Cost missed in original Table 12 Filing 2/14/22. Included in ARC Report filed 3/31/2022.
Note on AL79: Jen Medina: 2/15/22: Cost missed in original Table 12 Filing 2/14/22. Included in ARC Report filed 3/31/2022.