## WP Schedule 10 FERC CWIP
Project | Description | Operating Date | TOTAL Jan 2026 - Dec 2027 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | Total 2026 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | Total 2027
8169 | Colorado River Substation Expansion
902519003 | Colorado River Sub - Install SPS | 2021-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CRS Expansion |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6902 | Calcite Substation (formerly Jasper; part of South of Kramer)
900295954 | Calcite: LGIA Engineer and construct a new interconnection facility | 2029-01-23 | 16342.896 | 18.794 | 45.842 | 68.26 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 600 | 2812.896 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1430 | 13530
Total Calcite Substation |  |  | 16342.896 | 18.794 | 45.842 | 68.26 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 600 | 2812.896 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1100 | 1430 | 13530
6420 | West of Devers Upgrade Project
901460764 | Rebuild Devers-El Casco & El Casco-San Bernardino 220kV | 2021-05-19 | 550 | 7.881 | 14.368 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 77.751 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
802120834 | Condemnation | 2026-06-30 | 0.313 | 0.378 | -0.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total West of Devers |  |  | 550.313 | 8.259 | 14.303 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 77.751 | 550.313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6092 | Alberhill System
800063633 | Licensing Phase - Site Selection, PEA/Application Preparation, Environmental Surveys and CPUC Licensing Review. | 2028-12-29 | 51866.1911 | 171.949 | 108.7787 | 736.9693 | 90.9088 | 95.7222 | 3695.75 | 97.2439 | 199.9201 | 399.9875 | 98.4287 | 80.6829 | 919.2457 | 6695.587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45170.6041 | 45170.6041
800796373 | Alberhill Real Properties Acquisition | 2030-04-12 | 5338.0823 | 0.65954 | 0.40572 | 5.782 | 5.782 | 5.782 | 8.673 | 8.673 | 14.455 | 14.455 | 14.455 | 17.346 | 24.954 | 121.4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5216.6601 | 5216.6601
900502072 | Alberhill-Serrano 500kV: Form the Alberhill-Serrano 500 kV line by looping the existing Serrano-Valley 500 kV line into Alberhill Sub. | 2030-04-12 | 15244.181 | 52.396 | 0 | 0.59 | 19.151 | 114.08 | 165.043 | 235.608 | 255.209 | 235.608 | 165.043 | 114.08 | 59.786 | 1416.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13827.587 | 13827.587
900502073 | Alberhill-Valley 500kV: Form the Alberhill-Valley 500 kV line by looping the existing Serrano-Valley 500 kV line into Alberhill Substation | 2030-03-29 | 9789.771 | 26.198 | 0 | 0.59 | 45.349 | 114.08 | 165.043 | 235.608 | 255.209 | 235.608 | 165.043 | 114.08 | 59.786 | 1416.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8373.177 | 8373.177
Total Alberhill |  |  | 82238.2254 | 251.2026 | 109.1845 | 743.9313 | 161.1908 | 329.6642 | 4034.509 | 577.1329 | 724.7931 | 885.6585 | 442.9697 | 326.1889 | 1063.7717 | 9650.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72588.0282 | 72588.0282
7546 | Eldorado-Lugo-Mohave Upgrade
801648460 | ELMSC Real Properties Acquisition | 2022-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901056467 | Eldorado Sub: Upgrade Terminal Equipment | 2025-06-04 | 1072 | 9.485 | 22.088 | 6 | 902 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 90.427 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901056468 | Lugo Sub: Upgrade Terminal Equipment and | 2025-06-02 | 1003 | 13.254 | 6.887 | 2 | 888 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 77.859 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901490550 | Mohave Sub:Install CBs, Disc.&series cap | 2024-11-13 | 1094 | 15.957 | 3.892 | 2 | 980 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 78.151 | 1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901624163 | Mid-Line Cap: Install Series Capacitors on Eldorado-Lugo T/L | 2024-04-30 | 1252 | 7.215 | 14.537 | 18 | 985 | 18 | 18 | 18 | 18 | 18 | 18 | 10 | 109.248 | 1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901826564 | Inst Eldo-Lug-Mhve Series Caps at Ludlow | 2024-07-02 | 1291 | 39.063 | 16.261 | 18 | 986 | 18 | 18 | 18 | 18 | 18 | 18 | 10 | 113.676 | 1291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901904770 | Eldorado-Mohave T/L: Instal OPGW, splice | 2021-12-30 | 70 | 4.328 | 0.085 | 6 | 6 | 6 | 6 | 7 | 5 | 6 | 6 | 5 | 12.587 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901904772 | Lugo-Mohave T/L(CA): Instal OPGW, splice | 2025-12-14 | 147 | 20.334 | 15.085 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 5 | 5 | 24.581 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901904773 | Lugo-Mohave T/L(NV): Instal OPGW, splice | 2025-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901904774 | Eldorado-Lugo T/L(CA): Clear infractions | 2025-12-14 | 0 | -0.053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904539746 | Lugo-Mohave_Socal Gas Pipeline AC Mtgtn | 2026-06-30 | 24323 | 112.25 | 63.615 | 11300 | 150 | 150 | 150 | 150 | 150 | 150 | 200 | 300 | 1985.135 | 14861 | 10 | 10 | 10 | 10 | 10 | 15 | 15 | 15 | 15 | 15 | 19 | 9318 | 9462
7546-1 | Potential Change Orders | 2026-06-30 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Eldorado-Lugo-Mohave |  |  | 30629 | 221.833 | 142.45 | 11363 | 4908 | 213 | 214 | 214 | 212 | 213 | 257 | 340 | 2868.717 | 21167 | 10 | 10 | 10 | 10 | 10 | 15 | 15 | 15 | 15 | 15 | 19 | 9318 | 9462
7555 | Mesa Substation
900959223 | Build new Mesa 230/66/16 kV substation. Install an L90 relay, since an L90 relay is being added at Walnut Substation. | 2019-12-31 | 0.33133 | 0.33133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
902178838 | Mesa: Upgrade to a 500/230/66/16kV sub | 2022-05-27 | 339.699 | 45.295 | 23.594 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 25.81 | 339.699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
902472308 | Mira Loma Subs | 2022-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901197441 | FIP-Mesa Area Phase2: Relocate various lines | 2020-06-24 | 1.979 | 3.464 | -1.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
903814003 | FIP- Landscaping/Habitat Restoration | 2027-03-07 | 550 | 6.861 | 16.337 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 346.802 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Mesa |  |  | 892.0093 | 55.9513 | 38.446 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 20 | 20 | 372.612 | 892.0093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5450 | Riverside Transmission Reliability Project
800062516 | I: 4518-5003--Mira Loma-Vista # 1 230kv: | 2029-11-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
800062777 | WILDLIFE: Engineer, design, a 220kV Interconnection Facility to loop the existing Mira Loma–Vista | 2029-11-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
801979678 | RTRP-Real Property | 2022-12-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901487150 | Vista Sub: Upgrade the line protection on the existing | 2029-10-31 | 190 | 0 | 0 | 0 | 5.833 | 15.833 | 15.833 | 15.833 | 15.833 | 15.833 | 15.833 | 31.666 | 57.503 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901487151 | Mira Loma Sub: Upgrade line protection on the existing | 2027-10-29 | 140 | 0 | 0 | 0 | 5.667 | 11.667 | 11.667 | 11.667 | 11.667 | 11.667 | 11.667 | 17.334 | 46.997 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
902220349 | Mira Loma-Vista No. 1 220kV T/L UG: Engineer and construct approximately 2 miles of new 220kV underground double circuit line. | 2029-10-31 | 152980.245 | 8590.591 | 11173.31 | 8594.93 | 8029.771 | 9467.178 | 9590.936 | 11878.611 | 13536.658 | 14903.034 | 14521.801 | 8725.54 | 7308.114 | 126320.474 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.648 | 2221.643 | 26659.771
903112093 | MIRA LOMA-VISTA NO.1 Subtation | 2029-11-15 | 69113.931 | 2312.244 | 768.417 | 2068.226 | 817.902 | 1008.061 | 4670.027 | 4475.068 | 14987.088 | 5827.031 | 7943.061 | 2508.827 | 3166.242 | 50552.194 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1558.061 | 1423.066 | 18561.737
903112254 | WILDLIFE -Sub SCE -CAISO Controlled facilities | 2029-10-29 | 7478.743 | 25.425 | 45.472 | 45.601 | 60.918 | 60.918 | 60.918 | 60.918 | 578.451 | 60.918 | 60.918 | 91.684 | 96.45 | 1248.591 | 519.183 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 519.179 | 6230.152
802386271 | ACQ: RTRP FIP PROJE | 2029-11-15 | 36242.652 | 29.027 | 830.848 | 56.859 | 500 | 1750 | 1750 | 1750 | 1750 | 2462.293 | 2520.973 | 3350 | 4250 | 21000 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 1270.221 | 15242.652
Total Riverside Transmission Reliability Project |  |  | 266145.571 | 10957.287 | 12818.047 | 10765.616 | 9420.091 | 12313.657 | 16099.381 | 18192.097 | 30879.697 | 23280.776 | 25074.253 | 14725.051 | 14925.306 | 199451.259 | 5569.113 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5569.109 | 5434.109 | 66694.312
8575 | Mesa-Del Amo-Serrano 500kV Upgrade
904192914 | Serrano Substation: Install an appropriate number of 500 kV transmission structures including insulator/hardware assemblies and appropriate number of spans of conductor needed to equip the newly formed Del Amo - Serrano 500 kV Line into Serrano Substation | 2035-01-15 | 187.836 | 12.448 | 5.388 | 20 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 187.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904192915 | Mesa Substation: Install facilities for a new 500 kV switchrack position to terminate the newly formed Del Amo - Mesa 500 kV line (dead-end switchyard structure, support structures, lines drops) and install one 500 kV line position (circuit breakers, disc | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904192916 | Serrano Substation: Install facilities for a new 500 kV switchrack position to terminate the newly formed Del Amo - Serrano 500 kV line (dead-end switchyard structure, support structures, lines drops) and install one 500 kV line position (circuit breakers | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904192913 | Mesa Substation: Install an appropriate number of 500 kV transmission structures including insulator/hardware assemblies and appropriate number of spans of conductor needed to equip the newly formed Del Amo - Mesa 500 kV Line into Mesa substation | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904192917 | Del Amo Substation: Expand the Del Amo substation by installing new 500 kV buses and associated equipment to support 500 kV Operation Install three (3) new 500/230 kV AA Bank Transformers ( three - single phase) Equip three (3) 500 kV positions to insta | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Mesa-Del Amo-Serrano 500kV Upgrade |  |  | 187.836 | 12.448 | 5.388 | 20 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 187.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8600 | Lugo: Install single phase transformer
904187434 | New Lugo 3AA 500/230 kV Bank | 2029-08-28 | 32210.926 | 9.815 | 8.608 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 2245.237 | 2423.41 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 29787.516
Total Lugo: Install single phase transformer |  |  | 32210.926 | 9.815 | 8.608 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 17.75 | 2245.237 | 2423.41 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 2482.293 | 29787.516
8610 | Lugo-Victor-Kramer 115kV to 230kV Rebuild
904220880 | Kramer-Victor 230 kV No. 3 line | 2028-03-03 | 11554.346 | 17.188 | 14.847 | 9.646 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 378 | 1259.681 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 570.665 | 724 | 10294.665
904220884 | Kramer Sub - Equip two new 230 kV positions at Kramer..Remove equipment at existing Kramer 115 kV switchrack terminating positions for Kramer-Victor 115 .kV and Kramer-Roadway-Victor 115 kV lines | 2031-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904220885 | Victor Sub - Equip two new 230 kV positions at Victor 230 kV | 2031-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Lugo-Victor-Kramer 115kV to 230kV Rebuild |  |  | 11554.346 | 17.188 | 14.847 | 9.646 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 378 | 1259.681 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 570.665 | 724 | 10294.665
8631 | Lugo-Victor 230 kV Lines Reconductor
904267127 | Lugo-Victor No. 1 Reconductor approximately 10.8 miles of existing Lugo-Victor No. 2 230 lines with a high temperature low sag (HTLS) conductor | 2027-04-27 | 18389 | 3.064 | 7.739 | 91.665 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 4718 | 370.532 | 5478 | 230 | 241 | 264 | 322 | 322 | 322 | 317 | 1352 | 3646 | 3646 | 1346 | 903 | 12911
904413132 | Lugo-Victor No.2: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 2 230 lines with a high temperature low sag (HTLS) conductor. | 2027-04-27 | 11329 | 0.585 | 2.802 | 114.09 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 1984.523 | 2422 | 173 | 1876 | 173 | 173 | 230 | 230 | 224 | 224 | 679 | 2979 | 1254 | 692 | 8907
904413133 | Lugo-Victor No.3: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 3 230 lines with a high temperature low sag (HTLS) conductor. | 2027-12-20 | 16489 | 0.433 | 0.676 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 62.891 | 200 | 196 | 5281 | 253 | 253 | 253 | 253 | 707 | 707 | 1851 | 3576 | 2081 | 878 | 16289
904413134 | Lugo-Victor No.4: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 4 230 lines with a high temperature low sag (HTLS) conductor. | 2027-12-20 | 11918 | 0.433 | 0.676 | -0.297 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 63.188 | 200 | 173 | 3847 | 173 | 173 | 230 | 230 | 339 | 339 | 679 | 2979 | 1829 | 727 | 11718
Total Lugo-Victor 230 kV Lines Reconductor |  |  | 58125 | 4.515 | 11.893 | 205.458 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 4792 | 2481.134 | 8300 | 772 | 11245 | 863 | 921 | 1035 | 1035 | 1587 | 2622 | 6855 | 13180 | 6510 | 3200 | 49825
Grand Total |  |  | 498876.1227 | 11557.2929 | 13209.0085 | 23298.6613 | 15142.0318 | 13509.0712 | 21000.64 | 19585.9799 | 32419.2401 | 24982.1845 | 26341.9727 | 20635.9899 | 25012.5287 | 246694.6015 | 10833.406 | 21306.402 | 10924.402 | 10982.402 | 11096.402 | 11101.402 | 11653.402 | 12688.402 | 16921.402 | 23246.402 | 16251.067 | 95176.4302 | 252181.5212