## WP Schedule 10 Summary of ISO
|  |  | High/ Low |  | Project Total (ISO & non-ISO) |  |  |  | ISO Portion
PIN | Project Title | Order # | Voltage | OD | Prior | 2026 | 2027 | Total | Prior | 2026 | 2027 | Total
Incentive Transmission Projects includes only Direct Installation Expenditures
08169 | Colorado River Substation Expansion (CRSE)
08169 | Colorado River Substation: Installation of the 2nd AA 1120MVA 500/220kV transformer bank | 902519003 | High | 2021-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08169 | Total CRSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06902 | Calcite Substation (formerly Jasper; part of South of Kramer)
06902 | Calcite Substation (SCE Funded): Construct new Calcite 220kV Substation (switching station) to interconnect the Ord Mountain gen-tie and the Sorrel I Solar Farm gen-tie | 900295954 | High | 2029-01-23 | 5387.3733 | 2812.896 | 13530 | 21730.2693 | 5387.3733 | 2812.896 | 13530 | 21730.2693
06902 | Total Calcite |  |  |  | 5387.3733 | 2812.896 | 13530 | 21730.2693 | 5387.3733 | 2812.896 | 13530 | 21730.2693
06420 | West of Devers
06420 | Rebuild Devers-El Casco & El Casco-San Bernardino 220 kV lines with 2B-1590 ACSR on double circuit towers | 901460764 | High | 2021-05-19 | 0 | 550 | 0 | 550 | 0 | 550 | 0 | 550
06420 | Condemnation | 802120834 | High | 2026-06-30 | 7236.7998 | 0.313 | 0 | 7237.1128 | 7236.7998 | 0.313 | 0 | 7237.1128
06420 | Total West of Devers |  |  |  | 7236.7998 | 550.313 | 0 | 7787.1128 | 7236.7998 | 550.313 | 0 | 7787.1128
06092 | Alberhill System
06092 | Licensing Phase - Site Selection, PEA/Application Preparation, Environmental Surveys and CPUC Licensing Review. | 800063633 | High | 2028-12-29 | 44418.3333 | 12777.8377 | 86203.443 | 143399.614 | 23275.2066 | 6695.587 | 45170.6041 | 75141.3977
06092 | Alberhill Real Properties Acquisition | 800796373 | High | 2030-04-12 | 104.0088 | 247.8004 | 10646.245 | 10998.0542 | 50.9643 | 121.4222 | 5216.6601 | 5389.0466
06092 | Alberhill-Serrano 500kV: Form the Alberhill-Serrano 500 kV line by looping the existing Serrano-Valley 500 kV line into Alberhill Sub. | 900502072 | High | 2030-04-12 | 241.0943 | 1416.594 | 13827.587 | 15485.2753 | 241.0943 | 1416.594 | 13827.587 | 15485.2753
06092 | Alberhill-Valley 500kV: Form the Alberhill-Valley 500 kV line by looping the existing Serrano-Valley 500 kV line into Alberhill Substation | 900502073 | High | 2030-03-29 | 59.7551 | 1416.594 | 8373.177 | 9849.5261 | 59.7551 | 1416.594 | 8373.177 | 9849.5261
06092 | Total Alberhill System |  |  |  | 44823.1915 | 15858.8262 | 119050.452 | 179732.4697 | 23627.0204 | 9650.1972 | 72588.0282 | 105865.2457
07546 | Eldorado-Lugo-Mohave Upgrade
07546 | ELMSC Real Properties Acquisition | 801648460 | High | 2022-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07546 | Eldorado Sub: Upgrade Terminal Equipment | 901056467 | High | 2025-06-04 | 0 | 1072 | 0 | 1072 | 0 | 1072 | 0 | 1072
07546 | Lugo Sub: Upgrade Terminal Equipment and | 901056468 | High | 2025-06-02 | 0 | 1003 | 0 | 1003 | 0 | 1003 | 0 | 1003
07546 | Mohave Sub:Install CBs, Disc.&series cap | 901490550 | High | 2024-11-13 | 0 | 1094 | 0 | 1094 | 0 | 1094 | 0 | 1094
07546 | Mid-Line Cap:Inst cap on Eldor Lugo T/L | 901624163 | High | 2024-04-30 | 0 | 1252 | 0 | 1252 | 0 | 1252 | 0 | 1252
07546 | Inst Eldo-Lug-Mhve Series Caps at Ludlow | 901826564 | High | 2024-07-02 | 0 | 1291 | 0 | 1291 | 0 | 1291 | 0 | 1291
07546 | Eldorado-Mohave T/L: Instal OPGW, splice | 901904770 | High | 2021-12-30 | 0 | 70 | 0 | 70 | 0 | 70 | 0 | 70
07546 | Lugo-Mohave T/L(CA): Instal OPGW, splice | 901904772 | High | 2025-12-14 | 0 | 147 | 0 | 147 | 0 | 147 | 0 | 147
07546 | Lugo-Mohave T/L(NV): Instal OPGW, splice | 901904773 | High | 2025-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07546 | Eldorado-Lugo T/L(CA): Clear infractions | 901904774 | High | 2025-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07546 | Lugo-Mohave_Socal Gas Pipeline AC Mtgtn | 904539746 | High | 2026-06-30 | 23174.7058 | 14861 | 9462 | 47497.7058 | 23174.7058 | 14861 | 9462 | 47497.7058
07546 | Potential Change Orders | 7546-1 | High | 2026-06-30 | 0 | 377 | 0 | 377 | 0 | 377 | 0 | 377
07546 | Total Eldorado-Lugo-Mohave Upgrade |  |  |  | 23174.7058 | 21167 | 9462 | 53803.7058 | 23174.7058 | 21167 | 9462 | 53803.7058
07555 | Mesa Substation
07555 | Build new Mesa 230/66/16 kV substation. Install an L90 relay, since an L90 relay is being added at Walnut Substation. | 900959223 | High | 2019-12-31 | 0 | 0.65172 | 0 | 0.65172 | 0 | 0.33133 | 0 | 0.33133
07555 | Mesa: Upgrade Mesa from a 230/66/16kV substation to a 500/230/66/16kV substation | 902178838 | High | 2022-05-27 | 0 | 339.699 | 0 | 339.699 | 0 | 339.699 | 0 | 339.699
07555 | Mira Loma 500kV T/L: Install (1) L90 relay. Install (2) SEL-411L relays. Install (2) RFL-9745 channels. | 902472308 | High | 2022-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07555 | FIP-Mesa Area Phase2: Relocate various lines | 901197441 | High | 2020-06-24 | 0 | 1.979 | 0 | 1.979 | 0 | 1.979 | 0 | 1.979
07555 | FIP- Landscaping/Habitat Restoration | 903814003 | High | 2027-03-07 | 2331.9639 | 550 | 0 | 2881.9639 | 2331.9639 | 550 | 0 | 2881.9639
07555 | Total Mesa Substation |  |  |  | 2331.9639 | 892.3297 | 0 | 3224.2936 | 2331.9639 | 892.0093 | 0 | 3223.9732
05450 | Riverside Transmisison Riability Project (RTRP)
05450 | Mira Loma-Vista No. 1 220 kV T/L: Engineer and construct approximately 10 miles of new line | 800062516 | High | 2029-11-15 | 11449.0667 | 0 | 0 | 11449.0667 | 11449.0667 | 0 | 0 | 11449.0667
05450 | WILDLIFE (FORMERLY JURUPA 5057-5001): Engineer, design, a 220kV Interconnection Facility to loop the existing Mira Loma–Vista | 800062777 | High | 2029-11-15 | 6983.9624 | 0 | 0 | 6983.9624 | 6983.9624 | 0 | 0 | 6983.9624
05450 | RTRP-Real Property | 801979678 | High | 2022-12-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05450 | Vista Sub: Upgrade the line protection on the existing | 901487150 | High | 2029-10-31 | 3.9331 | 190 | 0 | 193.9331 | 3.9331 | 190 | 0 | 193.9331
05450 | Mira Loma Sub: Upgrade line protection on the existing | 901487151 | High | 2027-10-29 | 7.3283 | 140 | 0 | 147.3283 | 7.3283 | 140 | 0 | 147.3283
05450 | Mira Loma-Vista No. 1 220kV T/L UG: Engineer and construct approximately 2 miles of new 220kV underground double circuit line. | 902220349 | High | 2029-10-31 | 65545.0228 | 126320.474 | 26659.771 | 218525.2678 | 65545.0228 | 126320.474 | 26659.771 | 218525.2678
05450 | MIRA LOMA-VISTA NO.1 Subtation | 903112093 | High | 2029-11-15 | 2976.6089 | 50552.194 | 18561.737 | 72090.5399 | 2976.6089 | 50552.194 | 18561.737 | 72090.5399
05450 | WILDLIFE -Sub SCE -CAISO Controlled facilities | 903112254 | High | 2029-10-29 | 1275.8332 | 1248.591 | 6230.152 | 8754.5762 | 1275.8332 | 1248.591 | 6230.152 | 8754.5762
05450 | ACQ: RTRP FIP PROJE | 802386271 | High | 2029-11-15 | 5986.2589 | 21000 | 15242.652 | 42228.9109 | 5986.2589 | 21000 | 15242.652 | 42228.9109
05450 | Total Riverside Transmisison Riability Project |  |  |  | 94228.0143 | 199451.259 | 66694.312 | 360373.5853 | 94228.0143 | 199451.259 | 66694.312 | 360373.5853
08575 | Mesa-Del Amo-Serrano 500kV Upgrade
08575 | Serrano Substation (Del Amo - Serrano 500 kV Line into Serrano Substation) | 904192914 | High | 2035-01-15 | 3055.3365 | 187.836 | 0 | 3243.1725 | 3055.3365 | 188 | 0 | 3243.3365
08575 | Mesa Substation: Install facilities for a new 500 kV switchrack position to terminate the newly formed Del Amo - Mesa 500 kV line | 904192915 | High | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08575 | Serrano Substation: Install facilities for a new 500 kV switchrack position to terminate the newly formed Del Amo - Serrano 500 kV line | 904192916 | High | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08575 | Mesa Substation: Install an appropriate number of 500 kV transmission structures including insulator/hardware assemblies and appropriate number of spans of conductor needed to equip the newly formed Del Amo - Mesa 500 kV Line into Mesa substation | 904192913 | High | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08575 | Del Amo Substation: Expand the Del Amo substation by installing new 500 kV buses and associated equipment to support 500 kV Operation Install three (3) new 500/230 kV AA Bank Transformers ( three - single phase) Equip three (3) 500 kV positions to insta | 904192917 | High | 2035-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08575 | Total Mesa-Del Amo-Serrano 500kV Upgrade |  |  |  | 3055.3365 | 187.836 | 0 | 3243.1725 | 3055.3365 | 188 | 0 | 3243.3365
08600 | New Lugo 3AA 500/230 kV Transformer Bank
08600 | New Lugo 3AA 500/230 kV Bank | 904187434 | High | 2029-08-28 | 339.6881 | 2423.41 | 29787.516 | 32550.6142 | 339.6881 | 2423.41 | 29787.516 | 32550.6142
08610 | Kramer-Victor 115 kV to 230 kV Rebuild
08610 | Kramer-Victor 230 kV No. 3 line | 904220880 | High | 2028-03-03 | 1620.5088 | 1259.681 | 10294.665 | 13174.8548 | 1620.5088 | 1259.681 | 10294.665 | 13174.8548
08610 | Kramer Sub - Equip two new 230 kV positions at Kramer | 904220884 | High | 2031-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08610 | Victor Sub - Equip two new 230 kV positions at Victor 230 kV | 904220885 | High | 2031-03-31 | 1.7804 | 0 | 0 | 1.7804 | 1.7804 | 0 | 0 | 1.7804
08610 | Total Kramer-Victor 115 kV to 230 kV Rebuild |  |  |  | 1622.2892 | 1259.681 | 10294.665 | 13176.6352 | 1622.2892 | 1259.681 | 10294.665 | 13176.6352
08631 | Lugo-Victor 230 kV Lines Reconductor
08631 | Lugo-Victor No. 1 Reconductor approximately 10.8 miles of existing Lugo-Victor No. 2 230 lines with a high temperature low sag (HTLS) conductor | 904267127 | High | 2027-04-27 | 697.6878 | 5478 | 12911 | 19086.6878 | 697.6878 | 5478 | 12911 | 19086.6878
08631 | Lugo-Victor No.2: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 2 230 lines with a high temperature low sag (HTLS) conductor. | 904413132 | High | 2027-04-27 | 537.3266 | 2422 | 8907 | 11866.3266 | 537.3266 | 2422 | 8907 | 11866.3266
08631 | Lugo-Victor No.3: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 3 230 lines with a high temperature low sag (HTLS) conductor. | 904413133 | High | 2027-12-20 | 446.1407 | 200 | 16289 | 16935.1407 | 446.1407 | 200 | 16289 | 16935.1407
08631 | Lugo-Victor No.4: Reconductor approximately 10.8 miles of existing Lugo-Victor No. 4 230 lines with a high temperature low sag (HTLS) conductor. | 904413134 | High | 2027-12-20 | 414.7389 | 200 | 11718 | 12332.7388 | 414.7389 | 200 | 11718 | 12332.7388
08631 | Total Lugo-Victor 230 kV Lines Reconductor |  |  |  | 2095.8939 | 8300 | 49825 | 60220.8939 | 2095.8939 | 8300 | 49825 | 60220.8939
| Total Incentive Transmission Projects |  |  |  | 184295.2562 | 252903.5509 | 298643.945 | 735842.7521 | 163099.0851 | 246694.7655 | 252181.5212 | 661975.3718
| Total Incentive Transmission Projects (Closing by Dec 2027) |  |  |  | 34846.6916 | 31049.6427 | 59287 | 125183.3343 | 34846.6916 | 31049.3223 | 59287 | 125183.0139