## Instructions
California Public Utilties Commission
Annual Report Electric Rule 20 Programs (A-D)
GENERAL
BACKGROUND: As directed in Decision 21-06-013, electric utilities shall annually report to the Commission information about all of the projects, expenditures, and work credit balances for all communities in their service territories. This annual report template is designed for reporting all Rule 20A, 20B, 20C, and 20D projects in the reporting period. The first sheet is for project level data and the second sheet is for community level data. The utilities shall meet with Energy Division upon request to further refine the template prior to the submission deadline of April 1, 2022. Therefore, this template may be subject to change. INSTRUCTIONS: Complete the spreadsheet, listing all Electric Rule 20 programs' project and community level data from January 1, 2019 to December 31, 2021. Please include all projects from planning phase to close out phase. The annual report is split into three tranches in order of importance of the data. Staff requests that the utilities make data available as they complete each tranche. Data provided should include everything up to December 31st, 2021 (i.e., data recorded after this data should NOT be included in this year's report). Do not leave cells blank; if a column is not applicable to a specific project please indicate this using "N/A" and if a value for a column is unknown indicate this using "Unknown." Additionally, the utilities shall work with staff regarding the availability of project files in GIS format. GIS data should be provided in a shape file and should include project boundary, path of overhead infrastructure to be converted to underground, and path of trench where underground equipment is to be placed. The attribute table for each project should include all data in the project tab. If the report contains confidential information, provide two separate versions via through KiteWorks: a redacted version for public distribution and an unredacted version. The files must be searchable and filterable. If you have questions, contact Jessica Tse at Jessica.Tse@cpuc.ca.gov and Julian Enis at Julian.Enis@cpuc.ca.gov. This is the current template as of 03/10/2021.
DEFINITIONS
Definitions of urban areas, urban clusters, and rural areas are per the US Census Bureau's 2010 definitions, which can be found here: https://www.census.gov/programs-surveys/geography/guidance/geo-areas/urban-rural/2010-urban-rural.html Urban Area: Areas meeting minimum population density requirements and encompassing more than 50,000 people. Urban Cluster: Areas meeting minimum population density requirements and encompassing more than 2,500 people and less than 50,000 people. Rural Area: All areas not defined as either urban areas or urban clusters.

## Project - By Tranche
Public Version Redacted
Rule 20 Project Data
| Tranche 1 (High Priority) | [28 empty] | Tranche 3 (Lower Priority)
| Project Sponsor | Other Project Sponsors | County | Project City | Utility Undergrounding District | Project Name/Identifier | Project Address (Street, City, ZIP Code) | R20 Project Type (A/B/C/D) | Applicant Type | Project Status (Active/Hold/Cancelled) | Project Stage | Project Completion Date (PCD) | PCD, Forecast or Actual? | Trench Length (ft) | Length, Estimated or Design? | Project Cost (Actual, Non-Adjusted) | Actual Cost/ Current Estimated At Completion (EAC)* | Current/ Actual Cost/ Ft | Explanation for Outlier Costs | Centerline Footage of Primary OH Line Converted | Line Footage of Primary UG Circuit | Number of Meters Converted to UG Service | Project Spend to Date (ITD) | Project Spend, Report Year (YTD) | Joint Trench Participants? | Public Interest Criteria Met By Project (Rule 20A Only) | Is this project being performed in top 25% DAC per CalEnviroScreen 4.0? | Environmental Mitigations required? | Storm Water Pollution Prevention Plan (SWPPP) required? | Project in Urban/Urban Cluster/Rural (Defined in the American Community Survey) | # of Poles Removed as Part of Project Scope | Projected/Final Cost to Non-Ratepayers | Non-Ratepayer Funding Source
|  | n/a | San Bernardino | Adelanto | n/a | TD1877048/TD1877051 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Adelanto | n/a | TD2063454/TD2063456 |  | B | Contractor | Active | Estimating/Design | 2023-12-01 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | Unknown | TBD | 0 | 806.98 | 806.98 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Agoura Hills | n/a | TD1460754/TD1460755 |  | B | Individual | Cancelled |  | n/a |  | n/a |  | 5000 | EAC | Unknown | n/a | Unknown | n/a | 2 | -1492.2 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Agoura Hills | n/a | TD1712870/TD1712871 |  | C | Individual | Active | Estimating/Design | 2024-07-24 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| Government Agency | n/a | Los Angeles | Agoura Hills | 22-2003 | TD1989613/ TD1989599 | Cornell Road -- 140' S/O CL Agoura Rd to Cornell Way | A | Government Agency | Active | Estimating/Design | 2024-10-16 | Forecast | 2027 | Design | 1300000 | EAC | 600 | n/a | TBD | 2027 | 0 | 55752.24 | 55752.24 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic |  | No | No | Urban Cluster | 10 | n/a | n/a
| Government Agency | n/a | Los Angeles | Alhambra | R2M19-10 | n/a | Chapel Ave/ Los Higos St to Mission Road | A | Government Agency | Hold | Planning | TBD |  | 8212 | Preliminary | 5800000 | EAC | 650 | n/a | TBD | 8212 | - | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Alhambra | R2M19-10 | n/a | Chapel Ave/San Marino Ave to Linda Vista Avenue | A | Government Agency | Hold | Planning | TBD |  | 3750 | Preliminary | 2600000 | EAC | 650 | n/a | TBD | 3750 | - | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Alhambra | R2M19-10 | TD1786964/TD1786963 | Commonwealth/Palm Ave to Olive Ave | A | Government Agency | Active | Estimating/Design | 2024-11-09 | Forecast | 5565 | Design | 8600000 | EAC | 650 | n/a | TBD | 5565 | 6 | 433609.16 | 224509.06 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Alhambra | n/a | TD1471482/TD1471483 |  | B | Contractor | Active | Closed | 2020-08-06 | Actual | 1805 | Design | 325998.76 | Actual | 180.6087 | n/a | 976 | 1805 | 33 | 325998.76 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
| ANAHEIM, CITY OF | n/a | Orange | Anaheim | n/a | TD1224338/TD1474090 | BEACH BLVD FROM LINCOLN TO BALL RD ANAHEIM CA 92833 | B | Government Agency | Active | Estimating/Design | 2023-06-02 | Forecast | TBD | Preliminary | 1719052.14 | EAC | TBD | n/a | TBD | TBD | 4 | 36590.36 | 13605.27 | Unknown | n/a | No | No | No | Urban Cluster | 38 | n/a | n/a
|  | n/a | San Bernardino | Apple Valley | n/a | TD1946441/TD1946442 |  | C | Contractor | Active | Closing | 2022-12-13 | Actual | 652 | Design | 254481.07 | Actual | 390.3084 | n/a | 1005 | 652 | 14 | 254481.07 | 254481.07 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Apple Valley | n/a | TD1950959/TD1950960/TD1957304/TD1957305 |  | C | Contractor | Active | Estimating/Design | 2023-06-01 | Forecast | 615 | Design | 101894 | EAC | 165.6813 | n/a | TBD | 615 | 3 | 2227.73 | 2227.73 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| TOWN OF APPLE VALLEY | n/a | San Bernardino | Apple Valley | n/a | TD1644569/TD1644570 | HIGHWAY 18 & APPLE VALLEY RD APPLE VALLEY CA 92307 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Arcadia | n/a | TD1780774/TD1780779 |  | C | Individual | Active | Estimating/Design | 2023-12-20 | Forecast | 131 | Design | 26516 | EAC | 202.4122 | n/a | TBD | 131 | 2 | 111.65 | 111.65 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Arcadia | n/a | TD1544851/TD1544853 |  | C | Contractor | Active | Estimating/Design | 2020-06-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Arcadia | n/a | TD1467168/TD1538509 |  | C | Contractor | Active | Closed | 2020-11-12 | Actual | 284 | Design | 416983.3 | Actual | 1468.2511 | n/a | 424 | 284 | 11 | 416983.3 | 71 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Los Angeles | Artesia | 19-2778 | TD1685810/TD1685803/TD1685828/TD1685826/ TD1365713/ TD1375980 | Pioneer Blvd /166th Street to Arkansas Street | A | Government Agency | Active | Estimating/Design | 2023-09-01 | Forecast | 2235 | Design | 1200000 | EAC | 700 | n/a | TBD | 2235 | 25 | 787733.92 | 124300.15 | Yes | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| Government Agency | n/a | Los Angeles | Baldwin Park | 2016-110 | TD1116315/TD1116314 | Baldwin Park Blvd/ Kenmore to Bresee | A | Government Agency | Active | Closing | 2021-12-07 | Actual | 3291 | Design | 2132591.54 | Actual | 648 | n/a | 4230 | 3291 | 107 | 2132591.54 | 1528.17 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | San Bernardino | Barstow | n/a | TD1797171/TD1797188 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Barstow | n/a | TD1797199 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Barstow | n/a | TD1723704 | STR# 187917E to 1847916E BARSTOW CA 92311 | C |  | Active | Estimating/Design | 2022-07-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 23095.22 | -1247.57 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Barstow | n/a | TD1723702 | STR# 2308449s and 4495026E BARSTOW CA 92311 | C |  | Active | Estimating/Design | 2022-07-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 17856.59 | 8795.91 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Barstow | n/a | TD1731654 | STR# 328703S AND STR# 2268526E BARSTOW CA 92311 | C |  | Active | Estimating/Design | 2022-08-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 19039.11 | 11346.61 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Barstow | n/a | TD1731635 | STR# 330503S AND STR# 330502S BARSTOW CA 92311 | C |  | Active | Estimating/Design | 2022-08-03 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 17351.87 | 6810.17 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Barstow | n/a | TD1731646 | STR#80833S AND 4660004E BARSTOW CA 92311 | C |  | Active | Estimating/Design | 2022-08-04 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 20303.84 | 14332.82 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Barstow | 4769-2014 | TD990503/TD990501/TD1980346 | Rimrock Rd./ Rushmore Dr. and Higgins Rd | A | Government Agency | Active | Estimating/Design | 2025-05-03 | Forecast | 4412 | Design | 2000000 | EAC | 500 | n/a | TBD | 4412 | 17 | 112229.42 | -170092.97 | Yes | Arterial Street or Major Collector | Yes | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | San Bernardino | Barstow | n/a | TD2053926/TD2053927/TD2066237 |  | C | Business | Active | Estimating/Design | 2023-03-27 | Forecast | 219 | Design | 54061.6 | EAC | 246.8566 | n/a |  | 219 | 2 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| UNKNOWN | n/a | Riverside | Beaumont | n/a | TD1951552/TD1951553/TD1951616 | 1396 DESERT LAWN DRIVE BEAUMONT CA 92223 | C |  | Active | Estimating/Design | 2023-06-22 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 355.55 | 355.55 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Beaumont | n/a | TD1923136/TD1923137 |  | C | Contractor | Active | Closing | 2022-11-21 | Actual | 185 | Design | 82852.48 | Actual | 447.8512 | n/a | 184 | 185 | - | 82852.48 | 82852.48 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Beaumont | n/a | TD2037816/TD2012944 |  | C | Business | Active | Estimating/Design | 2023-06-02 | Forecast | 149 | Design | 167293 | EAC | 1122.7718 | n/a |  | 149 | 9 | 634.23 | 634.23 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Bell Gardens | n/a | TD1717965/TD1717966 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Bell Gardens | n/a | TD1578083/TD1578084 |  | C | Contractor | Active | Estimating/Design | 2020-02-18 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Beverly Hills | n/a | TD1818531/TD1936049 |  | C | Individual | Active | Estimating/Design | 2022-12-20 | Forecast | 599 | Design | 47220 | EAC | 78.8314 | n/a | TBD | 599 | 7 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Beverly Hills | n/a | TD1745596/TD1745597 |  | C | Contractor | Active | Estimating/Design | 2023-12-08 | Forecast | 214 | Design | 132193 | EAC | 617.7243 | n/a | TBD | 214 | 19 | 2920.83 | 2920.83 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Bradbury | n/a | TD1781699/TD1781700 |  | C | Contractor | Active | Closed | 2021-11-18 | Actual | 469 | Design | 44035.58 | Actual | 93.8925 | n/a | 235 | 469 | 5 | 44035.58 | 4804.86 | Unknown | n/a | Yes | No | No | Rural | 4 | n/a | n/a
| Government Agency | n/a | Orange | Buena Park | 14466 | TD1976684/TD1976683 | Orangethorpe Ave. from 500 ' West of Knott to West of Holder- PHII | A | Government Agency | Active | Estimating/Design | 2024-08-30 | Forecast | 3165 | Design | 2600000 | EAC | 725 | n/a | TBD | 3165 | 11 | 154415.7 | 154415.7 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 18 | n/a | n/a
|  | n/a | Orange | Buena Park | n/a | TD1496081/TD1496082 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Buena Park | n/a | TD1496112/TD1496120 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes |  |  | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Buena Park | n/a | TD1419925/TD1419926 |  | C | Contractor | Active | Closed | 2021-02-23 | Actual | 446 | Design | 124472.56 | actual | 279.0865 | n/a | 375 | 446 | 8 | 124472.56 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Orange | Buena Park | n/a | TD1477348/TD1477350/TD1687377 |  | C | Contractor | Active | Estimating/Design | 2023-06-23 | Forecast | 418 | Design | 161792.03 | EAC | 387.0623 | n/a | TBD | 418 | 32 | 59773.83 | 43970.32 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Calabasas | n/a | TD1461916/TD1461917 | 5583 JED SMITH CALABASAS CA 91302 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 21741 | EAC | Unknown | n/a | Unknown | unknown | 6 | 0 | -4963.62 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Calabasas | n/a | TD1699903/TD169904 |  | C | Contractor | Active | Estimating/Design | 2025-12-26 | Forecast | 526 | Design | 112263 | EAC | 213.4278 | n/a | TBD | 526 | 0 | 2473.26 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Calabasas | n/a | TD1821809/TD1821819 |  | C | Business | Active | Estimating/Design | 2023-05-25 | Forecast | 693 | Design | 190910.23 | EAC | 275.4837 | n/a | TBD | 693 | 14 | 5506.46 | 4963.68 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Kern | California City | 2443-11-11 | n/a | Redwood Blvd/ 98th St to 500ft e/o Conklin Blvd | A | Government Agency | Hold | Planning | TBD |  | 1550 | Preliminary | 600000 | EAC | 350 | n/a | TBD | 1550 | - | 0 | 0 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Calimesa | n/a | TD1378530/TD1378531/TD1483811 |  | B | Business | Active | Closed | 2022-04-19 | Actual | 720 | Design | 281509.28 | Actual | 390.9851 | n/a | 736 | 720 | - | 281509.28 | -3305.55 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Calimesa | n/a | TD1938514/TD1938519 |  | C | Individual | Active | Construction | 2022-12-21 | Forecast | 367 | Design | 155910 | EAC | 424.8229 | n/a | TBD | 367 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Calimesa | n/a | TD1567183/ TD1510144 |  | C | Individual | Active | Closed | 2020-03-18 | Actual | 1751 | Design | 140044.37 | Actual | 79.9797 | n/a | 1385 | 1751 | 4 | 140044.37 | 0 | Unknown | n/a | No | No | No | Rural | 10 | n/a | n/a
| Government Agency | n/a | Ventura | Camarillo | 2015-114 | TD1077218/TD1077213 | Las Posas/ Marco Dr to Antonio Ave | A | Government Agency | Active | Estimating/Design | 2023-09-19 | Forecast | 2406 | Design | 1800000 | EAC | 700 | n/a | TBD | 2406 | 21 | 78321.66 | 9256.89 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 12 | n/a | n/a
|  | n/a | Ventura | Camarillo | n/a | TD2058195/TD2058196 |  | B | Contractor | Active | Estimating/Design | 2024-03-07 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | Unknown | TBD | 0 |  |  | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Ventura | Camarillo | n/a | TD1807844/TD1807846 | 5969 - S LEWIS RD/PLEASANT VALLEY RD CAMARILLO CA 93012 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown |  | Unknown | n/a | n/a
| UNKNOWN | n/a | Ventura | Camarillo | n/a | TD1865432/TD1865437 | 5969 - S LEWIS RD/PLEASANT VALLEY RD CAMARILLO CA 93012 | B |  | Active | Estimating/Design | 2022-05-27 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| UNKNOWN | n/a | Ventura | Camarillo | n/a | TD1807927/TD1807928 | 5969 - S LEWIS RD/PLEASANT VALLEY RD CAMARILLO CA 93012 | B |  | Active | Estimating/Design | 2022-02-01 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Santa Barbara | Camarillo | n/a | TD1625287/ TD1625289 |  | C | Contractor | Active | Estimating/Design | 2023-06-02 | Forecast | TBD | Preliminary | 103321 | EAC | TBD | n/a | TBD | TBD | 0 | 7481.67 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1125532/TD1125533 |  | B | Business | Active | Closed | 2020-08-20 | Actual | 1498 | Design | 830951.14 | Actual | 554.707 | n/a | 685 | 1498 | 9 | 830951.14 | -2126.99 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1813282/ TD1813315 |  | C | Business | Active | Closed | 2022-05-18 | Actual | 232 | Design | 103170.71 | Actual | 444.7013 | n/a | 460 | 232 | 13 | 103170.71 | 103170.71 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1395628/ TD1395629 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| CARPINTERIA, CITY OF | n/a | Santa Barbara | Carpinteria | n/a | TD1654052/TD1654056 | CACTUS LANE & CARPINTERIA AVE. CARPINTERIA CA 93117 | C | Government Agency | Active | Estimating/Design | 2023-06-14 | Forecast | 433 | Design | 35715 | EAC | 82.4827 | n/a | TBD | 433 | 19 | 621.4 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1575684/ TD1580319 |  | C | Business | Active | Closed | 2021-11-30 | Actual | 641 | Design | 2183544.36 | Actual | 3406.4655 | n/a | 63 | 641 | 1 | 2183544.36 | 765794.23 | Unknown | n/a | No | No | Yes | Urban Cluster | 5 | n/a | n/a
| UNKNOWN | n/a | Santa Barbara | Carpinteria | n/a | TD1580307/TD1580325 | CRAMER CIR CARPINTERIA CA 93118 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Santa Barbara | Carpinteria | n/a | TD1598511 | LILLIE AVE CARPINTERIA CA 93118 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| UNKNOWN | n/a | Santa Barbara | Carpinteria | n/a | TD948289 | NIPOMO DR & HIGHWAY 101 CARPINTERIA CA 93013 | C |  | Active | Estimating/Design | 2022-12-30 | Forecast | TBD | Preliminary | 35392 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1580441/TD1580446 |  | C | Business | Active | Closed | 2021-09-21 | Actual | 347 | Design | 379736.03 | Actual | 1094.3401 | n/a | 221 | 347 | 7 | 379736.03 | -29779.62 | Unknown | n/a | No | No | Yes | Urban Cluster | 2 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1525738/TD1580334 |  | C | Business | Active | Closed | 2021-09-17 | Actual | 868 | Design | 1611106.77 | Actual | 1856.1138 | n/a | 806 | 868 | 11 | 1611106.77 | 30022.49 | Unknown | n/a | Yes | No | Yes | Urban Cluster | 3 | n/a | n/a
|  | n/a | Santa Barbara | Carpinteria | n/a | TD1580415/TD1580421 |  | C | Business | Active | Closed | 2021-08-31 | Actual | 1378 | Design | 1516105.67 | Actual | 1100.2218 | n/a | 1115 | 1378 | 1 | 1516105.67 | -68844.37 | Unknown | n/a | No | No | Yes | Urban Cluster | 7 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Carson | n/a | TD1875104/TD1875105 | S Main Street and Lenardo Drive CARSON CA 90745 | C |  | Active | Estimating/Design | 2022-03-10 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Cathedral City | n/a | TD1722289/TD1722298 |  | B | Contractor | Active | Construction | 2022-10-07 | Actual | 155 | Design | 315179 | EAC | 2033.4129 | n/a | TBD | 155 | 10 | 402220.35 | 136213.71 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Riverside | Cathedral City | n/a | TD1506287/TD1506288 |  | C | Contractor | Active | Closed | 2020-07-01 | Actual | 1244 | Design | 577301.35 | Actual | 464.0686 | n/a | 2106 | 1244 | 9 | 577301.35 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 15 | n/a | n/a
|  | n/a | Riverside | Cathedral City | n/a | TD1679964/TD1691428 |  | C | Contractor | Active | Closed | 2021-12-27 | Actual | 2162 | Design | 958970.86 | Actual | 443.5573 | n/a | 1626 | 2162 | 6 | 958970.86 | -316.24 | Unknown | n/a | No | No | No | Urban Cluster | 12 | n/a | n/a
| CATHEDRAL CITY, CITY OF | n/a | Riverside | Cathedral City | n/a | TD1918937 | E. PALM CANYON & GOLF CLUB AND CANYON PL CATHEDRAL CITY CA 92234 | C | Government Agency | Active | Estimating/Design | 2023-06-15 | Forecast | TBD | Preliminary | 4200 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Cathedral City | n/a | TD2007990/TD2007991 |  | C | Business |  | Estimating/Design | 2023-09-29 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 3 | 232.23 | 232.23 | Unknown | n/a | No | No | No | Rural | 4 | n/a | n/a
| Government Agency | n/a | Los Angeles | Cerritos | 2014-1 | TD872800/TD872804 | Shoemaker/Droxford-183rd | A | Government Agency | Active | Construction | 2023-12-29 | Forecast | 2211 | Design | 1850000 | EAC | 700 | n/a | TBD | 2211 | 4 | 285182.7 | 54291.63 | No | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 11 | n/a | n/a
| Government Agency | n/a | San Bernardino | Chino | 2007-030 | TD1914350/TD1914461 | Ramona Avenue - Flood Control to Chino Hills Parkway | A | Government Agency | Active | Estimating/Design | 2024-04-11 | Forecast | 1580 | Design | 1200000 | EAC | 700 | n/a | TBD | 1580 | 8 | 116408.6 | 104456.69 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1451996 |  | B | Contractor | Active | Closed | 2020-01-17 | Actual | 0 |  | 111883.05 | Actual |  | n/a | 564 | 0 | 1 | 111883.05 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Chino | n/a | TD1689343/TD1689386 | CHINO CORONA RD & CUCAMONGA AVE CHINO CA 91708 | B |  | Active | Estimating/Design | 2022-05-10 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 10225.04 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1689234/TD1689241 |  | B | Contractor | Active | Estimating/Design | 2022-10-03 | Forecast | 3139 | Design | 454186 | EAC | 144.6913 | n/a | TBD | 3139 | - | 762.74 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 17 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1674752/TD1674753/TD1808789 |  | B | Contractor | Active | Closing | 2022-12-20 | Actual | 2696 | Design | 991796.15 | Actual | 367.8769 | n/a | 2135 | 2696 | 11 | 991796.15 | 970214.75 | Unknown | n/a | No | No | No | Urban Cluster | 13 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1240182/TD1240183 |  | B | Contractor | Active | Closed | 2020-11-18 | Actual | 1238 | Design | 270293.71 | Actual | 218.3309 | n/a | 943 | 1238 | 4 | 270293.71 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1796215/TD1796216 |  | C | Business | Active | Construction | 2022-07-29 | Forecast | 1335 | Design | 163728 | EAC | 122.6427 | n/a | TBD | 1335 | 6 | 117091 | 116741.21 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1447331/TD1447332 |  | C | Individual | Active | Closed | 2020-02-18 | Actual | 304 | Design | 56754.2 | Actual | 0 | n/a | 479 | 304 | - | 56754.2 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1829777/TD1829778 |  | C | Individual | Active | Estimating/Design | 2022-11-17 | Forecast | 445 | Design | 179521 | EAC | 403.418 | n/a | TBD | 445 | 23 | 818.77 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Chino | n/a | TD1334654/TD1334655 |  | C | Contractor | Active | Closed | 2021-11-24 | Actual | 1164 | Design | 346541.21 | Actual | 297.7158 | n/a | 844 | 1164 | 15 | 346541.21 | -1001.85 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Los Angeles | Claremont | n/a | TD1629370/TD1638606 |  | B | Business | Active | Estimating/Design | 2024-08-16 | Forecast | 1626 | Design | 483986.51 | EAC | 297.6547 | n/a | TBD | 1626 | 4 | 17537.92 | 2136.24 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Los Angeles | Claremont | n/a | TD1546874/TD1591221 |  | B | Business | Active | Estimating/Design | 2023-12-21 | Forecast | 2607 | Design | 565479 | EAC | 216.9079 | n/a | TBD | 2607 | 1 | 1232.38 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 12 | n/a | n/a
| Government Agency | n/a | Los Angeles | Commerce | 22-32 | TD1983483/ TD1983481 | Harbor Street / Commerce Way to Entrada Street | A | Government Agency | Active | Estimating/Design | 2025-01-27 | Forecast | 1930 | Preliminary | 1600000 | EAC | 750 | n/a | TBD | 1930 | 10 | 52103.97 | 52103.97 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | Los Angeles | Commerce | n/a | TD1820833/TD1820834 |  | C | Contractor | Active | Estimating/Design | 2023-06-07 | Forecast | 443 | Design | 129511 | EAC | 292.3499 | n/a | TBD | 443 | - | 1987.84 | 1987.84 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Corona | n/a | TD1755885/TD1755886 |  | B | Contractor | Active | Construction | 2023-01-30 | Forecast | 1512 | Design | 629476.19 | EAC | 416.3202 | n/a | TBD | 1512 | - | 9108.01 | 7402.57 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Corona | n/a | TD1608218/TD1608221 |  | B | Contractor | Active | Estimating/Design | 2022-12-30 | Forecast | 877 | Design | 112603.33 | EAC | 128.396 | n/a | TBD | 877 | - | 0 | 0 | Unknown | n/a |  | Unknown | Unknown |  | 1 | n/a | n/a
|  | n/a | Riverside | Corona | n/a | TD1755819 |  | C | Contractor | Active | Estimating/Design | 2021-08-21 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Corona | n/a | TD1591167/TD1591168 |  | C | Contractor | Active | Closed | 2020-06-08 | Actual | 1351 | Design | 162411.27 | Actual | 120.2156 | n/a | 1578 | 1351 | 8 | 162411.27 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Corona | n/a | TD1665822/TD1666287 |  | C | Contractor | Active | Closed | 2021-10-06 | Actual | 430 | Design | 195131.92 | Actual | 453.7952 | n/a | 354 | 430 | 5 | 195131.92 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Riverside | Corona | Unknown | TD1505236/TD1505235 | Harrington St and Lincoln St | A | Government Agency | Active | Closed | 2020-08-04 | Actual | 970 | Design | 768427.99 | Actual | 792 | n/a | 683 | 970 | 2 | 768427.99 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Orange | Costa Mesa | n/a | TD1904907 |  | A | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 |  | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | Orange | Costa Mesa | 2021-32 | TD1924116 /TD1924114 | Adams Ave/ Mesa Verde Dr. - Placeenta Ave | A | Government Agency | Active | Estimating/Design | 2024-12-08 | Forecast | 2378 | Design | 3700000 | EAC | 725 | n/a | TBD | 2378 | 18 | 67487.28 | 67487.28 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 0 | n/a | n/a
| COSTA MESA, CITY OF | n/a | Orange | Costa Mesa | n/a | TD1948416 | ADAMS AVE AND PLACENTIA COSTA MESA CA 92683 | B | Government Agency | Active | Estimating/Design | 2023-02-01 | Forecast | TBD | Preliminary | 130000 | EAC | TBD | n/a | TBD | TBD | 0 | 58735.06 | 58735.06 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Costa Mesa | n/a | TD1806096/TD1806124 |  | C | Contractor | Active | Estimating/Design | 2023-06-30 | Forecast | 330 | Preliminary | 88696.3 | EAC | 268.7767 | n/a | TBD | 330 | 63 | 422.63 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Covina | n/a | TD1283860/TD1283861 |  | C | Contractor | Active | Closed | 2020-07-21 | Actual | 1425 | Design | 355332.21 | Actual | 249.3559 | n/a | 668 | 1425 | 9 | 355332.21 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
| Government Agency | n/a | Los Angeles | Covina | n/a | TD1753723/ TD1753731 | 82874: 1060 W. SAN BERNARDINO RD COVINA CA 91722 | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 |  | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Covina | n/a | TD2076503/TD2076508 | TR83343 155 E COVINA BLVD COVINA CA 91722 | C |  | Active | Estimating/Design | 2023-07-27 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Cudahy | 04 23 | TD550984/TD550987 | Wilcox Ave/Santa Ana-Elizabeth | A | Government Agency | Cancelled | Estimating/Design | n/a |  | n/a |  | 1700000 | EAC | 350 | n/a | Unknown | Unknown | Unknown | 163240.46 | -110665.01 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | Culver City | 2015-R012 | TD1208657/TD1208661 | Culver Blvd s/o Sepulveda-Commonwealth Ave | A | Government Agency | Active | Closing | 2022-09-26 | Actual | 1778 | Design | 2104185.19 | Actual | 700 | n/a | 955 | 1778 | 11 | 2104185.19 | 1341388.81 | Yes | Heavy Concentration of OH Facilities | No | No | No | Rural | 10 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1330704 |  | C | Contractor | Active | Closed | 2020-01-28 | Actual | 720 | Design | 188299.13 | Actual | 261.5266 | n/a | 0 | 720 | 0 | 188299.13 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | los Angeles | Culver City | n/a | TD1442309 |  | C | Contractor | Active | Closed | 2020-06-04 | Actual | 0 | Design | 3709.74 | Actual | Unknown | n/a | 213 | 0 | 0 | 3709.74 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1463842/TD1614434 |  | C | Contractor | Active | Closed | 2022-08-28 | Actual | 1246 | Design | 324855.58 | actual | 260.7188 | n/a | 1081 | 1246 | 8 | 324855.58 | 6579.68 | Unknown | n/a | Yes | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1621573 |  | C | Contractor | Active | Closed | 2021-07-19 | Actual | 428 | Design | 11232.9 | Actual | 0 | n/a | 0 | 428 | 0 | 11232.9 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1675009 |  | C | Contractor | Active | Closed | 2021-07-19 | Actual | 0 | Design | 5922.9 | Actual | Unknown | n/a | 393 | 0 | 4 | 5922.9 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1697098 |  | C | Contractor | Active | Construction | 2022-09-06 | Forecast | 0 | Preliminary | 17985 | EAC | 0 | n/a | TBD | 0 | 1 | 10648.76 | 10648.76 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD1521105 |  | C | Contractor | Active | Construction | 2022-10-12 | Forecast | 1474 | Design | 453767 | EAC | 307.8474 | n/a | TBD | 1474 | 16 | 578099.96 | 541557.37 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Culver City | n/a | TD2009305/ TD1984870 |  | C | Individual | Active | Estimating/Design | 2023-06-21 | Forecast | 615 | Design | 120805.57 | EAC | 196.4318 | n/a |  | 615 | 0 | 870.18 | 870.18 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1427249/TD1427250 |  | B | Business | Active | Closing | 2022-08-25 | Actual | 1315 | Design | 39466.63 | Actual | 30.0126 | n/a | TBD | 1315 | - | 39466.63 | 25600.46 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1482355/TD1482358 |  | B | Contractor | Active | Closed | 2020-04-20 | Actual | 1291 | Design | 193456.2 | Actual | 149.8499 | n/a | 1026 | 1291 | - | 193456.2 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1898156/TD1898160 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1937578/TD1937579 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1441718/TD1441719 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1735705/TD1735706 |  | C | Business | Active | Estimating/Design | 2023-01-06 | Forecast | 1968 | Design | 110040 | EAC | 55.9146 | n/a | TBD | 1968 | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| CITY OF DELANO | n/a | Kern | Delano | n/a | TD1708418/TD1708419 | 707 MAIN DELANO CA 93215 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| DELANO, CITY OF | n/a | Kern | Delano | n/a | TD2042102/TD2042101 | ALBANY/GARCES DELANO CA 93215 | C | Government Agency | Active | Estimating/Design | 2023-04-03 | Forecast | 1534 | Design | 196792.1 | EAC | 128.2869 | n/a |  | 1534 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
| CITY OF DELANO | n/a | Kern | Delano | n/a | TD1400849/TD1400909 | AUSTIN ST & 3RD AVE DELANO CA 93215 | C | Government Agency | Active | Closed | 2020-04-03 | Actual | 235 | Design | 14699.8 | Actual | 62.5523 | n/a | 0 | 235 | - | 14699.8 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1213833/TD1213834 |  | C | Contractor | Active | Closed | 2020-11-05 | Actual | 1133 | Design | 236077 | Actual | 208.3645 | n/a | 985 | 1133 | - | 236077 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1899877/TD1899881/TD1924825/TD1924836 |  | C | Contractor | Active | Construction | 2022-12-22 | Forecast | 1718 | Design | 387739 | EAC | 225.6921 | n/a | TBD | 1718 | 1 | 361378.53 | 361378.53 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
| DELANO, CITY OF | n/a | Kern | Delano | n/a | TD1845825/TD1845826 | HIGH ST AND 18TH AVE DELANO CA 93215 | C | Government Agency | Active | Closing | 2022-08-31 | Actual | 2848 | Design | 64448 | Actual | 22.6292 | n/a | 3034 | 2848 | 3 | 64448 | 61353 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Kern | Delano | n/a | TD1979265/TD1979264 |  | C | Business | Active | Estimating/Design | 2023-06-01 | Forecast | 1728 | Design | 401291.97 | EAC | 232.2291 | n/a |  | 1728 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Desert Hot Springs | n/a | TD1697275 |  | B | Contractor | Cancelled | [5 empty] | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | Diamond Bar | 2021-53 | TD1933973/TD1933916/ TD1970783/ TD1985428 | Brea Canyon Road - Cold Spring Lane to Cool Springs Drive | A | Government Agency | Active | Estimating/Design | 2024-05-12 | Forecast | 2226 | Design | 1600000 | EAC | 700 | n/a | TBD | 2226 | 9 | 85358.52 | 83532.22 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 11 | n/a | n/a
|  | n/a | Los Angeles | Duarte | n/a | TD1778008/TD1778009 |  | C | Business | Active | Closed | 2021-08-10 | Actual | 403 | Design | 141108 | Actual | 350.1439 | n/a | 330 | 403 | 8 | 141108 | 42.83 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Duarte | n/a | TD1814284/TD1814285 |  | C | Business | Active | Estimating/Design | 2024-01-26 | Forecast | 946 | Design | 136598 | EAC | 144.3953 | n/a | TBD | 946 | 4 | 5475.46 | 1468.86 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Eastvale | n/a | TD1539152/TD1539157/TD1651067/TD1651068 |  | B | Contractor | Active | Closed | 2021-01-08 | Actual | 1007 | Design | 218317 | Actual | 216.7994 | n/a | 889 | 1007 | - | 218317 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
| Government Agency | n/a | Riverside | Eastvale | 21-52 | TD1940147/TD1940142 | Schleisman Road and Hamner Avenue | A | Government Agency | Active | Estimating/Design | 2023-11-14 | Forecast | 358 | Design | 500000 | EAC | 700 | n/a | TBD | 358 | 5 | 188039.27 | 188039.27 | No | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 2 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | El Monte | n/a | TD1678357 | 3480 - 11707 GARVEY AVE & 3100 BASEBALL EL MONTE CA 91732 | B |  | Active | Estimating/Design | 2022-09-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 946.98 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | El Monte | n/a | TD1678331 | 3480 - 11707 GARVEY AVE & 3100 BASEBALL EL MONTE CA 91732 | B |  | Active | Estimating/Design | 2021-04-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | El Monte | n/a | TD1490914/TD1519994 |  | C | Contractor | Active | Closed | 2020-08-13 | Actual | 3320 | Design | 741423 | Actual | 223.3202 | n/a | 8986 | 3320 | 19 | 741423 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 18 | n/a | n/a
|  | n/a | Los Angeles | El Monte | n/a | TD1438109/TD1438112 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Tulare | Farmersville | 2008-18 | n/a | Walnut Ave/ Freedom to Farmersville | A | Government Agency | Hold | Planning | TBD |  | 2120 | Preliminary | 935000 | EAC | 400 | n/a | TBD | 2120 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Ventura | Fillmore | 21-3844 | TD1934610/TD1934575 | Santa Clara Street/ Fillmore Street to Saratoga Street | A | Government Agency | Active | Estimating/Design | 2024-04-27 | Forecast | 828 | Design | 500000 | EAC | 700 | n/a | TBD | 828 | 6 | 35933.47 | 35933.47 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 4 | n/a | n/a
| Government Agency | n/a | San Bernardino | Fontana | 2006-267 | n/a | Baseline/ Sierra Ave-Juniper Ave | A | Government Agency | Hold | Planning | TBD |  | 1500 | Preliminary | 530000 | EAC | 353 | n/a | TBD | 1500 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Fontana | 2006-266 | n/a | Juniper Ave/Baseline Ave-Highland Ave | A | Government Agency | Hold | Planning | TBD |  | 4800 | Preliminary | 1440000 | EAC | 300 | n/a | TBD | 4800 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Fontana | 2017-04 | TD1408941/TD1408878 | Sierra Ave/ Miller Ave to Paine St N/O Foothill Blvd | A | Government Agency | Active | Construction | 2023-07-10 | Forecast | 8599 | Design | 3300000 | EAC | 550 | n/a | TBD | 8599 | 75 | 145907.62 | 88030.71 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 23 | n/a | n/a
| Government Agency | n/a | San Bernardino | Fontana | 2006-263 | n/a | South Highland/ Juniper Ave-Sierra Ave | A | Government Agency | Hold | Planning | TBD |  | 1600 | Preliminary | 480000 | EAC | 300 | n/a | TBD | 1600 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Fontana | 2006-265 | n/a | Walnut Ave/ Juniper Ave-Sierra Ave | A | Government Agency | Hold | Planning | TBD |  | 1500 | Preliminary | 2226000 | EAC | 1484 | n/a | TBD | 1500 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1788469/TD1847210 |  | B | Contractor | Active | Construction | 2022-09-06 | Forecast | 1491 | Design | 316594 | EAC | 212.3367 | n/a | TBD | 1491 | - | 433404.3 | 419020.13 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1681187/TD1681190 |  | B | Contractor | Active | Closed | 2022-08-09 | Actual | 1274 | Design | 661567.2 | Actual | 519.2835 | n/a | 6394 | 1274 | - | 661567.2 | 67422.97 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1917211/TD1917212 | 7325 SIERRA AVE FONTANA CA 92335 | B |  | Active | Estimating/Design | 2022-12-16 | Forecast | 1435 | Design | 158388 | EAC | 110.3749 | n/a | TBD | 1435 | 16 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 13 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1672177/TD1672183 |  | B | Contractor | Active | Estimating/Design | 2023-02-27 | Forecast | 862 | Design | 274748.86 | EAC | 318.7342 | n/a | TBD | 862 | 3 | 10058.82 | 8955.98 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1600519/TD1600520/TD1667310/TD1667314/TD1667396/TD1667398 | CITRUS AVE / VALLEY BLVD FONTANA CA 92335 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1910196 | SOUTH HIGHLAND AVE FONTANA CA 92336 | B |  | Active | Estimating/Design | 2024-12-27 | Forecast | n/a |  | - | EAC | Unkown | n/a |  | - | - | - | - | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1796747/TD1796749 |  | B | Contractor | Active | Closed | 2022-03-18 | Actual | 716 | Design | 461468.3 | Actual | 644.5088 | n/a | 1800 | 716 | 1 | 461468.3 | 441690.77 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD2030749/TD2030751 | 10317 CALABASH AVE FONTANA CA 92337 | C |  | Active | Estimating/Design | 2023-03-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 937.29 | 937.29 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1621386/TD1652916 |  | C | Contractor | Active | Closed | 2020-11-02 | Actual | 643 | Design | 266730 | Actual | 414.8212 | n/a | 1082 | 643 | 9 | 266730 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1515647/TD1515654 |  | C | Contractor | Active | Closed | 2021-02-11 | Actual | 538 | Design | 109970.78 | Actual | 204.4067 | n/a | 429 | 538 | - | 109970.78 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1626140/TD1675379 |  | C | Contractor | Active | Closed | 2021-03-22 | Actual | 683 | Design | 244126 | Actual | 357.4319 | n/a | 945 | 683 | 3 | 244126 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1798821/TD1798825 |  | C | Contractor | Active | Closed | 2022-05-19 | Actual | 1582 | Design | 998489 | Actual | 631.1561 | n/a | 1683 | 1582 | 2 | 998489 | -12030.31 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1765695/TD1765699 |  | C | Individual | Active | Closed | 2022-04-05 | Actual | 1499 | Design | 299655 | actual | 199.9033 | n/a | 1618 | 1499 | 21 | 299655 | 291746 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD2032106/TD2032105 |  | C | Business | Active | Estimating/Design | 2023-07-13 | Forecast | 1564 | Design | 478253 | EAC | 305.7884 | n/a |  | 1564 | 12 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1876174/TD1890434 |  | C | Contractor | Active | Closed | 2022-12-19 | Actual | 1179 | Design | 269864 | Actual | 228.8923 | n/a | 670 | 1179 | 6 | 269864 | 268117 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1626729/TD1627355 |  | C | Contractor | Active | Closed | 2021-01-04 | Actual | 744 | Design | 184604 | Actual | 248.1237 | n/a | 639 | 744 | 12 | 184604 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD2026422/ TD2060178/ TD2026427 | 14817 FOOTHILL BLVD FONTANA CA 92335 | C |  | Active | Estimating/Design | 2023-05-18 | Forecast | 747 | Design | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1920806/TD1920807 |  | C | Contractor | Active | Estimating/Design | 2023-03-06 | Forecast | 996 | Design | 110202 | EAC | 110.6446 | n/a | TBD | 996 | 26 | 4156.91 | 4156.91 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1778920/TD1778926 |  | C | Individual | Active | Estimating/Design | 2023-04-19 | Forecast | 3828 | Design | 658903 | EAC | 172.1272 | n/a | TBD | 3828 | 14 | 8432.88 | 4489.15 | Unknown | n/a | Yes | No | No | Urban Cluster | 16 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1535090 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unkown | n/a | Unknown | n/a | Unknown | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1847053/TD1852730 |  | C | Contractor | Active | Construction | 2022-12-05 | Forecast | 1213 | Design | 320367 | EAC | 264.1113 | n/a | TBD | 1213 | 5 | 448192 | 448192 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1624494/TD1624499 |  | C | Contractor | Active | Closed | 2021-05-13 | Actual | 1185 | Design | 221826 | Actual | 187.1949 | n/a | 1198 | 1185 | 18 | 221826 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1920815/ TD1920817 |  | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | 1083 | Design | 349325 | EAC | 322.5531 | n/a |  | 1083 | 1 | 6657.53 | 6657.53 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1372867/TD1372868 |  | C | Contractor | Active | Closed | 2020-12-14 | Actual | 229 | Design | 33830.39 | Actual | 147.731 | n/a | 0 | 229 | - | 33830.39 | 10739.62 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1815943/TD1815945 |  | C | Contractor | Active | Closed | 2022-09-13 | Actual | 1503 | Design | 260546 | Actual | 173.3506 | n/a | 1326 | 1503 | 4 | 260546 | 256617 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1968187/TD1968197 |  | C | Business | Active | Estimating/Design | 2024-02-06 | Forecast | 110 | Design | 92387.21 | EAC | 839.8837 | n/a |  | 110 | 2 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1587264/TD1587267 |  | C | Contractor | Active | Closed | 2021-07-08 | Actual | 610 | Design | 285685.91 | Actual | 468.3376 | n/a | 1195 | 610 | 6 | 285685.91 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1941935/TD1956913 |  | C | Business | Active | Estimating/Design | 2023-08-01 | Forecast | 2499 | Design | 0 | EAC | 0 | n/a |  | 2499 | 10 | 289.47 | 289.47 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1975441/TD1975443 |  | C | Business | Active | Estimating/Design | 2023-01-27 | Forecast | 2516 | Design | 513549.36 | EAC | 204.1134 | n/a |  | 2516 | 0 | 3881.09 | 3881 | Unknown | n/a | No | No | No | Urban Cluster | 13 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD2028511/TD2043910 |  | C | Business | Active | Estimating/Design | 2023-02-24 | Forecast | 759 | Design | 323684 | EAC | 426.4611 | n/a |  | 759 | 2 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1832426/TD1832429 |  | C | Contractor | Active | Closed | 2022-06-20 | Actual | 928 | Design | 359936 | Actual | 387.8621 | n/a | 863 | 928 | - | 359936 | 358287 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1971021/TD1971022 | BASELINE ROAD & ALDER AVE S/W CORNER FONTANA CA 92376 | C |  | Active | Estimating/Design | 2023-01-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 5382 | 5382 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1826888/TD1826889 |  | C | Contractor | Active | Estimating/Design | 2023-06-30 | Forecast | 5254 | Design | 1249431 | EAC | 237.8057 | n/a | TBD | 5254 | 16 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 22 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1913956/TD1915025 | CALABASH AVE & JURUPA FONTANA CA 92337 | C |  | Active | Estimating/Design | 2023-06-30 | Forecast | 507 | Design | 203249 | EAC | 400.8856 | n/a | TBD | 507 | 3 | 1346.75 | 1346.75 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1785228/TD1785230 |  | C | Contractor | Active | Closed | 2021-10-14 | Actual | 455 | Design | 148599 | Actual | 326.5912 | n/a | 582 | 455 | 8 | 148599 | 7901.79 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Fontana | n/a | TD1920183 | Highland Ave. and Catawba Ave. FONTANA CA 92336 | C |  | Active | Estimating/Design | 2023-01-19 | Forecast | 1370 | Design | 0 | EAC | TBD | n/a | TBD | 1370 | 5 | 332.26 | 332.26 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1894790/TD1894805 |  | C | Contractor | Active | Construction | 12//27/22 | Forecast | 2912 | Design | 633394 | EAC | 217.5117 | n/a | TBD | 2912 | 9 | 849453 | 848835 | Unknown | n/a | No | No | No | Urban Cluster | 21 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1621185/TD1621188 |  | C | Contractor | Active | Closed | 2020-12-30 | Actual | 1093 | Design | 97037.5 | Actual | 88.7809 | n/a | 698 | 1093 | 11 | 97037.5 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1683472/TD1716310 |  | C | Individual | Active | Closed | 2021-09-22 | Actual | 447 | Design | 85135 | Actual | 190.4586 | n/a | 103 | 447 | 2 | 85135 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Fontana | n/a | TD1432541/TD1491347 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Fontana | n/a | TD1608875/TD1608878 |  | C | Contractor | Active | Closed | 2020-04-08 | Actual | 1919 | Design | 476193 | Actual | 248.1464 | n/a | 612 | 1919 | 6 | 476193 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
| Government Agency | n/a | Orange | Garden Grove | 9448-17 | TD1293742/TD1293746 | Magnolia/ Garden Grove Blvd to n/o Orangewood Ave | A | Government Agency | Active | Estimating/Design | 2023-11-05 | Forecast | 10526 | Design | 5800000 | EAC | 550 | n/a | TBD | 10526 | 107 | 467927.56 | 29586.61 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 51 | n/a | n/a
|  | n/a | Los Angeles | Gardena | n/a | TD1707958/TD1707960 |  | C | Contractor | Active | Construction | 2022-12-05 | Forecast | 1186 | Design | 316385 | EAC | 266.7664 | n/a | TBD | 1186 | 8 | 82675 | 77237 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Gardena | n/a | TD1952511/TD1952512 | 2129 W ROSECRANS AVE GARDENA CA 90249 | C |  | Active | Estimating/Design | 2023-07-21 | Forecast | 47 | Design | 9319 | EAC | 198.2766 | n/a | TBD | 47 | 4 | 1987.85 | 1987.85 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
| Government Agency | n/a | Los Angeles | Glendora | 2015-27 | TD1027101/TD1027098 | Foothill Blvd/ Valencia St and W/O Grand Ave | A | Government Agency | Active | Closed | 2020-04-29 | Actual | 2883 | Design | 1522295.55 | Actual | 528 | n/a | 1605 | 2883 | 32 | 1522295.55 | 0 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 16 | n/a | n/a
|  | n/a | Santa Barbara | Goleta | n/a | TD1771122/TD1771123 |  | C | Contractor | Active | Estimating/Design | 2024-05-31 | Forecast | 227 | Design | 71429 | EAC | 314.6652 | n/a | TBD | 227 | 3 | 303.22 | 0 | Unknown | n/a | No | No | No | Rural | 2 | n/a | n/a
|  | n/a | Santa Barbara | Goleta | n/a | TD1505952/TD1520031 |  | C | Individual | Active | Estimating/Design | 2023-07-28 | Forecast | 137 | Design | 19918 | EAC | 145.3869 | n/a | 128 | 137 | 7 | 471.16 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Goleta | n/a | TD1776159/TD11776160 |  | C | Contractor | Active | Estimating/Design | 2023-04-14 | Forecast | 577 | Design | 159587 | EAC | 276.5806 | n/a | TBD | 577 | 0 | 18048.6 | 16645.36 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Santa Barbara | Goleta | n/a | TD2053377/ TD2054684 |  | C | Individual | Active | Estimating/Design | 2024-02-28 | Forecast | 155 | Design | 11220.3 | EAC | 72.389 | n/a |  | 155 | 2 | 737.5 | 737.5 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
| Government Agency | n/a | Kings | Hanford | n/a | TD1699486/ TD1699487 | 12191 LACEY BLVD HANFORD CA 93230 | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown |  | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Kings | Hanford | n/a | TD1853476/TD1853477 |  | B | Contractor | Active | Estimating/Design | 2023-05-05 | Forecast | 1037 | Design | 0 | EAC | TBD | n/a | TBD | 1037 | 1 | 2123.14 | 2123.14 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | King | Hanford | n/a | TD2025643/TD2025644 |  | C | Business | Active | Estimating/Design | 2023-08-18 | Forecast | 836 | Design | 550601 | EAC | 658.6136 | n/a |  | 836 | 1 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | King | Hanford | n/a | TD2028901/TD2028913 |  | C | Business | Active | Estimating/Design | 2023-08-28 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Hawaiian Gardens | 097-2019 | TD1667969/TD1667967 | Norwalk Blvd/ Tilbury St to 215th St | A | Government Agency | Active | Estimating/Design | 2023-10-27 | Forecast | 1674 | Design | 1050000 | EAC | 690 | n/a | TBD | 1674 | 8 | 173258.27 | 3105.26 | Yes | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Hawthorne | n/a | TD1385919/TD1385920 |  | C | Contractor | Active | Closed | 2020-03-25 | Actual | 2000 | Design | 934250 | Actual | 467.125 | n/a | 998 | 2000 | 112 | 934250 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Hemet | n/a | TD1573721/TD1573732 |  | B | Contractor | Active | Closed | 2021-06-13 | Actual | 938 | Design | 319254.03 | Actual | 340.3561 | n/a | 762 | 938 | 5 | 319254.03 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Hemet | n/a | TD1679914/TD1679917 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Hemet | n/a | TD1969847/TD1969848 |  | B | Contractor | Active | Estimating/Design | 2023-06-19 | Forecast | 1635 | Design | 20378.96 | EAC | 12.4642 | n/a | TBD | 1635 | - | 816.62 | 816.62 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Riverside | Hemet | n/a | TD1544137/TD1544142 |  | C | Contractor | Active | Closed | 2020-08-17 | Actual | 210 | Design | 71215 | Actual | 339.119 | n/a | 220 | 210 | 0 | 71215 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Hemet | n/a | TD1695002/TD1695003/TD1695060 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| The City of Hemet | n/a | Riverside | Hemet | n/a | TD1859491/TD1859493 | TR33824; MCSWEENY PKWY (R/20C) HEMET CA 92543 | C | Government Agency | Active | Closing | 2022-11-08 | Actual | 291 | Design | 192656.91 | Actual | 662.0512 | n/a | TBD | 291 | 4 | 192656.91 | 192656.91 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| HERMOSA BEACH, CITY OF | n/a | Los Angeles | Hermosa Beach | n/a | TD1805249/TD1805252 | HERMOSA AVE, 34TH TO 26TH ST HERMOSA BEACH CA 99999 | B | Government Agency | Active | Estimating/Design | 2023-08-04 | Forecast | 2736 | Design | 210507.61 | EAC | 76.9399 | n/a | TBD | 2736 | 101 | 117332.04 | 28440.75 | Unknown | n/a | No | No | No | Urban Cluster | 21 | n/a | n/a
|  | n/a | Los Angeles | Hermosa Beach | n/a | TD1584211/TD1637996/TD1603401/TD1637995 |  | C | Contractor | Active | Estimating/Design | 2022-12-15 | Forecast | 505 | Design | 60034 | EAC | 118.8792 | n/a | TBD | 505 | 17 | 0 | -930.89 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
|  | n/a | Los Angeles | Hermosa Beach | n/a | TD1466691/TD1466698 |  | C | Individual | Active | Closed | 2021-03-31 | Actual | 86 | Design | 16220.59 | Actual | 188.6115 | n/a | 0 | 86 | 0 | 16220.59 | 22625.83 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Hermosa Beach | n/a | TD1341334/TD1468508 |  | C | Individual | Active | Closed | 2021-04-01 | Actual | 783 | Design | 270442 | Actual | 345.3921 | n/a | 440 | 783 | 18 | 270442 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| Government Agency | n/a | San Bernardino | Hesperia | n/a | TD1731486 | DURANGO 7TH STREET AND RANCHERO HESPERIA CA 92345 | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | San Bernardino | Hesperia | 2021-045 | TD1893735/TD1893734 | N/W Corner of 7th St & Ranchero Rd | A | Government Agency | Active | Estimating/Design | 2024-03-16 | Forecast | 564 | Design | 800000 | EAC | 1000 | n/a | TBD | 564 | 2 | 8851.95 | 8490.92 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Hesperia | n/a | TD1897671/TD1897681/TD1954033 |  | B | Contractor | Active | Estimating/Design | 2023-02-03 | Forecast | 1032 | Design | 0 | EAC | TBD | n/a | TBD | 1032 | 1 | 463.89 | 131.59 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | Hesperia | n/a | TD1810954/TD1894387 |  | B | Contractor | Active | Construction | 2022-11-20 | Forecast | 2279 | Design | 306424 | EAC | 134.4555 | n/a | TBD | 2279 | 3 | 399966.38 | 397650.99 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Hesperia | n/a | TD1804802 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Hesperia | n/a | TD1892727/TD1892735 |  | C | Contractor | Active | Estimating/Design | 2023-08-14 | Forecast | 549 | Preliminary | 239016 | EAC | 435.3661 | n/a | TBD | 549 | 3 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Hidden Hills | n/a | TD1458912/TD1458913 | 24402 LITTLE HOLLOW LN HIDDEN HILLS CA 91302 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 5000 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Hidden Hills | n/a | TD1458833/TD1458835 | 24507 LONG VALLEY HIDDEN HILLS CA 91302 | B | Government Agency | Active | Closed | 2021-09-30 | Actual | 2400 | Design | 826752.87 | Actual | 344.4804 | n/a | 1311 | 2400 | 14 | 826752.87 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
|  | n/a | Los Angeles | Hidden Hills | n/a | TD1461939 |  | B | Individual | Active | Estimating/Design | 2025-07-18 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Hidden Hills | n/a | TD1459060/TD149062 | 5750 JED SMITH RD HIDDEN HILLS CA 91302 | B | Government Agency | Active | Estimating/Design | 2024-12-20 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | - | 7030.36 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Hidden Hills | n/a | TD1565238/TD1565241 | 23973 LONG VALLEY RD HIDDEN HILLS CA 91302 | C | Government Agency | Active | Estimating/Design | 2023-12-29 | Forecast | 304 | Design | 249253 | EAC | 819.9112 | n/a | TBD | 304 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Hidden Hills | n/a | TD1803474/TD1803475 |  | C | Individual | Active | Closed | 2022-09-07 | Actual | 238 | Design | 53854.41 | Actual | 226.279 | n/a | 214 | 238 | 1 | 53854.41 | 52029.16 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Hidden Hills | n/a | TD1816229/TD1816230 |  | C | Contractor | Active | Closed | 2021-09-30 | Actual | 624 | Design | 32098.1 | Actual | 51.4393 | n/a | 255 | 624 | 2 | 32098.1 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Hidden Hills | n/a | TD1618761/TD1618762 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| HIDDEN HILLS, CITY OF | n/a | Los Angeles | Hidden Hills | n/a | TD1947126/TD1947127 | 5695 ROUND MEADOW RD HIDDEN HILLS CA 91302 | C | Government Agency | Active | Estimating/Design | 2024-07-18 | Forecast | 758 | Preliminary | 125051.7 | EAC | 164.9759 | n/a | TBD | 758 | 6 | 839.14 | 839.14 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| CITY OF HIGHLAND | n/a | San Bernardino | Highland | n/a | TD1375540/TD1375541 | VICTORIA AVE / 6TH STREET HIGHLAND CA 92346 | B | Government Agency | Cancelled |  | n/a |  | 1193 | Design | 202913.54 | EAC | Unknown | n/a | Unknown | Unknown | 10 | 2033.99 | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Highland | n/a | TD1276697 |  | C | Individual | Active | Closed | 2021-04-21 | Actual | 1686 | Design | 224609.79 | Actual | 133.2205 | n/a | 0 | 1686 | 7 | 224609.79 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Highland | n/a | TD1909585/TD1909586 |  | C | Contractor | Active | Estimating/Design | 2023-10-05 | Forecast | 183 | Design | 111442.73 | EAC | 608.9767 | n/a | TBD | 183 | 2 | 426.75 | 426.75 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Orange | Huntington Beach | n/a | TD1759516/ TD1759523 |  | C | Contractor | Active | Estimating/Design | 2023-12-29 | Forecast | 434 | Design | 159695 | EAC | 367.9608 | n/a | TBD | 434 | 9 | 1962.88 | 924.68 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Orange | Huntington Beach | n/a | TD1999484/TD1999481 |  | C | Business | Active | Estimating/Design | 2024-01-17 | Forecast | 179 | Design | 101429.28 | EAC | 566.644 | n/a |  | 179 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Orange | Huntington Beach | n/a | TD1977608/TD1977604 |  | C | Business | Active | Estimating/Design | 2023-05-31 | Forecast | 115 | Design | 0 | EAC | TBD | n/a |  | 115 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Los Angeles | Huntington Park | 2021-30 | TD1950448/TD1950446 | Bickett Street - Slauson Avenue to North City Limits Distribution Conversion Only | A | Government Agency | Active | Estimating/Design | 2024-03-26 | Forecast | 940 | Preliminary | 800000 | EAC | 700 | n/a | TBD | 940 | 0 | 43936.55 | 43936.55 | Yes | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Huntington Park | 2021-39 | TD1958790/TD1958788 | Santa Ana Street - State Street to California Avenue (Distribution only) | A | Government Agency | Active | Estimating/Design | 2023-01-27 | Forecast | 4350 | Preliminary | 3050000 | EAC | 650 | n/a | TBD | 4350 | 0 | 75149.88 | 75149.88 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Inglewood | n/a | TD1627157/TD1627194 |  | C | Business | Active | Closed | 2021-09-03 | Actual | 795 | Design | 42359.36 | Actual | 53.2822 | n/a | 0 | 795 | 0 | 42359.36 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Irvine | 22-20 | TD2006819/ TD2006798 | Redhill/ McGraw to 650' N/O Alton Parkway | A | Government Agency | Active | Estimating/Design | 2025-03-21 | Forecast | 2023 | Preliminary | 1700000 | EAC | 750 | n/a | TBD | 2023 | 0 | 43038 | 43038 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Irvine | n/a | TD1473163/TD1473185 |  | B | Contractor | Active | Closed | 2023-05-04 | Actual | 1435 | Design | 12316733.13 | Actual | 8583.0893 | n/a | TBD | 1435 | 56 | 12316733.13 | 92625.25 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Orange | Irvine | n/a | TD1629693/TD1629694 |  | B | Contractor | Active | Estimating/Design | 2023-08-18 | Forecast | 3313 | Design | 1156901.93 | EAC | 349.2007 | n/a | TBD | 3313 | 6 | 1982.72 | 0 | Unknown | n/a | No | No | No | Rural | 21 | n/a | n/a
|  | n/a | Orange | Irvine | n/a | TD1629691/TD1629692 |  | B | Contractor | Active | Closed | 2022-03-31 | Actual | 1505 | Design | 352952.24 | Actual | 234.5198 | n/a | 1346 | 1505 | - | 352952.24 | -13306.56 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Orange | Irvine | n/a | TD1411078 |  | C | Contractor | Active | Estimating/Design | 2022-02-09 | Forecast | 304 | Design | 75262.58 | EAC | 247.5743 | n/a | TBD | 304 | 0 | 38367.43 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Irwindale | n/a | TD1691860/TD1691983/TD1812733/TD1812735 |  | B | Contractor | Active | Estimating/Design | 2023-03-22 | Forecast | 2437 | Design | 653239 | EAC | 268.0505 | n/a | TBD | 2437 | 2 | 917.78 | 0 | Unknown | n/a | Yes | No | No | Rural | 8 | n/a | n/a
|  | n/a | Riverside | Jurupa Valley | n/a | TD2087735/ TD2087784 |  | C | Business | Active | Estimating/Design | 2024-01-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Jurupa Vallley | n/a | TD1503726/TD1503736 |  | B | Contractor | Cancelled |  | n/a |  | 2452 | Design | 360821.86 | EAC | 147.1541 | n/a | Unknown | 2452 | Unknown | 199.9 | -143.62 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Jurupa Vallley | n/a | TD1682134/TD1852242/TD1935343 |  | C | Contractor | Active | Estimating/Design | 2023-03-31 | Forecast | 5880 | Design | 1446541.09 | EAC | 246.0104 | n/a | TBD | 5880 | 2 | 8992.98 | 8992.98 | Unknown | n/a | Yes | No | No | Urban Cluster | 31 | n/a | n/a
|  | n/a | Riverside | Jurupa Vallley | n/a | TD1852713/TD1887549 |  | C | Contractor | Active | Closed | 2022-03-14 | Actual | 692 | Design | 435862 | Actual | 629.8584 | n/a | 844 | 692 | 7 | 435862 | 279703 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Jurupa Vallley | n/a | TD1848130/TD1889915/TD1896385 |  | C | Contractor | Active | Estimating/Design | 2023-07-28 | Forecast | 383 | Design | 124874 | EAC | 326.0418 | n/a | TBD | 383 | 0 | 4793.65 | 4793.65 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
| UNKNOWN | n/a | Riverside | Jurupa Vallley | n/a | TD1940561/TD1940565/TD1897068/TD1897069 | Avalon Street JURUPA VALLEY CA 92509 | C |  | Active | Estimating/Design | 2023-07-28 | Forecast | 1482 | Design | 356380 | EAC | 240.4723 | n/a | TBD | 1482 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Jurupa Vallley | n/a | TD1944990/TD1944991 |  | C | Contractor | Active | Estimating/Design | 2023-05-16 | Forecast | 1286 | Design | 228145 | EAC | 177.4067 | n/a | TBD | 1286 | 1 | 1011.51 | 1011.51 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Los Angeles | La Habra | 4358 | n/a | Harbor/ La Habra-Whittier, Ph 2 | A | Government Agency | Hold | Planning | TBD |  | 3870 | Preliminary | 1074500 | EAC | 278 | n/a | TBD | 3870 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | La Habra | 4358 | n/a | Harbor/ Whittier-No. City Limits, Ph 3 | A | Government Agency | Hold | Planning | TBD |  | 3210 | Preliminary | 904500 | EAC | 282 | n/a | TBD | 3210 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD1763064 |  | A | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | La Habra | n/a | TD1763074 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD1326862/TD1326864 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD1905641/TD1905642 |  | C | Contractor | Active | Closed | 2022-06-14 | Actual | 1062 | Design | 268925.72 | Actual | 253.2257 | n/a | 2382 | 1062 | 2 | 268925.72 | 268925.72 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD2021813 |  | C | Business | Active | Estimating/Design | 2023-08-03 | Forecast | 302 | Design | 0 | EAC | TBD | n/a |  | 302 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD2021820 |  | C | Business | Active | Estimating/Design | 2023-08-03 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD2021662 |  | C | Business | Active | Estimating/Design | 2023-08-03 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | La Habra | n/a | TD2021780 |  | C | Business | Active | Estimating/Design | 2023-08-03 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | La Mirada | 22-08 | TD2001823/ TD2001822 | La Mirada Blvd/ Imperial Hwy and Hutchins | A | Government Agency | Active | Estimating/Design | 2025-08-21 | Forecast | 1954 | Design | 1700000 | EAC | 750 | n/a | TBD | 1954 | 28 | 40019.48 | 40019.48 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0
| UNKNOWN | n/a | Orange | La Mirada | n/a | TD2048904/ TD2048998 | 14447 FIRESTONE BLVD LA MIRADA CA 90638 | C |  | Active | Estimating/Design | 2023-11-07 | Forecast | 1101 | Design | 0 | EAC | TBD | n/a |  | Unknown | 18 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Los Angeles | La Puente | 22-5726 | TD2004448/ TD2004466 | AMAR ROAD AND SUNSET AVE LA PUENTE CA 91744 | A | Government Agency | Active | Estimating/Design | 2023-12-29 | Forecast | 1940 | Preliminary | 1350000 | EAC | 650 | n/a | TBD | 1940 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | La Verne | 16-26 | TD1137685/TD1137684 | White Ave/ Town Center Dr to 1st Street | A | Government Agency | Active | Construction | 2023-03-30 | Forecast | 8967 | Design | 3800000 | EAC | 550 | n/a | TBD | 8967 | 150 | 5431910.75 | 4203862.78 | Unknown | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 44 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | La Verne | n/a | TD1997985 | 123456 PATTIGLEN AVE LA VERNE CA 91750 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unkown | n/a |  | - |  | - | - | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | La Verne | n/a | TD1784339 |  | B | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | 19450.06 | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Los Angeles | La Verne | n/a | TD1830323/TD1830344 | 2219 PATTIGLEN AVE LA VERNE CA 91750 | B |  | Cancelled |  | n/a |  | 6548 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Los Angeles | La Verne | n/a | TD1683690/TD1683692 | 2548 Magnolia Ave LA VERNE CA 91750 | B |  | Active | Estimating/Design | 2021-03-19 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | La Verne | n/a | TD1883633/TD1883640 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | La Verne | n/a | TD1768611/TD1784356 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | 20.067 | TD1782378/TD1782375 | Bluebird Canyon Dr/ Cress St to Eastman Way | A | Government Agency | Active | Estimating/Design | 2023-09-04 | Forecast | 4192 | Design | 3200000 | EAC | 725 | n/a | TBD | 4192 | 40 | 110819.52 | 36892.35 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 22 | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | 20.066 | TD1784784/TD1784780/903100184 | Coast Highway | A | Government Agency | Active | Estimating/Design | 2024-10-13 | Forecast | 3968 | Design | 4400000 | EAC | 800 | n/a | TBD | 3968 | 251 | 170416.09 | 6156.3 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 28 | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | 19.023 | TD1536921/TD1536914 | PCH/ Arch St to Agate St | A | Government Agency | Active | Estimating/Design | 2024-11-05 | Forecast | 2894 | Design | 5000000 | EAC | 850 | n/a | TBD | 2894 | 89 | 21201.64 | 7315.6 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 28 | n/a | n/a
| JOE CHIQUETE | n/a | Orange | Laguna Beach | UUAD 2013-4 | TD744396/TD744401 | AGATE ST & GLENNEYRE ST LAGUNA BEACH CA 92651 | B | Government Agency | Cancelled |  | n/a |  | 1965 | Design | 578669.04 | EAC | 294.4881 | n/a | Unknown | 1965 | 4 | -67924.64 | -2165.51 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 10 | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | n/a | TD806287/TD954607 | CRESTVIEW S/O DIAMOND LAGUNA BEACH CA 00000 | B | Government Agency | Active | Closed | 2020-06-12 | Actual | 617 | Design | 80521.75 | Actual | 130.5053 | n/a | Secondary only | 617 | - | 80521.75 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | UUAD 2014-1 | TD781687/TD997323 | DIAMOND ST / CRESTVIEW DR / GAINSBOROUGH LAGUNA BEACH CA 92651 | B | Government Agency | Active | Estimating/Design | 2023-11-01 | Forecast | 1161 | Design | 579559 | EAC | 499.1895 | n/a | TBD | 1161 | 18 | 7315.92 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
| LAGUNA BEACH, CITY OF | n/a | Orange | Laguna Beach | n/a | TD1947851/TD1947855 | FAIRVIEW X LA BREA LAGUNA BEACH CA 92651 | B | Government Agency | Active | Estimating/Design | 2023-12-15 | Forecast | TBD | Preliminary | 80000 | EAC | TBD | n/a | TBD | TBD | - | 130034.25 | 130034.25 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| LAGUNA BEACH, CITY OF | n/a | Orange | Laguna Beach | n/a | TD1852110/TD1852111 | PARK AVE AND SKYLINE LAGUNA BEACH CA 92651 | B | Government Agency | Active | Estimating/Design | 2023-06-30 | Forecast | 1666 | Design | 408013.46 | EAC | 244.906 | n/a | TBD | 1666 | 34 | 1819.12 | 1455.05 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
| CITY OF LAGUNA BEACH | n/a | Orange | Laguna Beach | n/a | TD991860/TD991861 | PCH TO SANTA CRUZ TO ARCHES TO BLUEB LAGUNA BEACH CA 92651 | B | Government Agency | Cancelled |  | n/a |  | 23713 | Design | 7838055.42 | EAC | 330.5383 | n/a | Unknown | 23713 | - | -140636.32 | -139477.06 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 130 | n/a | n/a
| LAGUNA BEACH, CITY OF | n/a | Orange | Laguna Beach | n/a | TD1631311/TD1846105 | PCH TO SANTA CRUZ TO ARCHES TO BLUEB LAGUNA BEACH CA 92651 | B | Government Agency | Active | Estimating/Design | 2024-12-31 | Forecast | 19854 | Design | 6525238.92 | EAC | 328.6612 | n/a | TBD | 19854 | 507 | 730157.41 | 701961.8 | Unknown | n/a | No | No | No | Urban Cluster | 124 | n/a | n/a
| LAGUNA BEACH, CITY OF | n/a | Orange | Laguna Beach | n/a | TD1846974/TD1846975/TD1849779 | PCH RULE 20C PEARL ST TO ARCH ST LAGUNA BEACH CA 92651 | C | Government Agency | Active | Estimating/Design | 2023-07-28 | Forecast | 88 | Design | 57177.98 | EAC | 649.7498 | n/a | TBD | 88 | 60 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1888684 |  | A | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown |  | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| LAKE ELSINORE, CITY OF | n/a | Riverside | Lake Elsinore | n/a | TD2057533/TD2057535 | 130 S MAIN ST LAKE ELSINORE CA 92530 | B | Government Agency | Active | Estimating/Design | 2023-11-30 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 2342.22 | 2342.22 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1724338/TD1724340 |  | B | Business | Cancelled |  | n/a |  | 1575 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | 3 | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1659910/TD1659911 |  | B | Business | Active | Closed | 2021-03-02 | Actual | 1575 | Design | 352568.7 | Actual | 223.8531 | n/a | 1182 | 1575 | - | 352568.7 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1510440/TD1510444 |  | B | Contractor | Active | Closed | 2021-03-12 | Actual | 1759 | Design | 374943.53 | Actual | 213.1572 | n/a | 1140 | 1759 | 4 | 374943.53 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD2046189/TD2046187 |  | B | Business | Active | Estimating/Design | 2023-10-05 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | - | - | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1927028/TD1927029/TD2056372 |  | B | Contractor | Active | Estimating/Design | 2023-08-30 | Forecast | TBD | Preliminary | 10000 | EAC | TBD | n/a | TBD | TBD | - | 496.57 | 496.57 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1877380/TD1877384/TD1908732 |  | B | Contractor | Active | Estimating/Design | 2022-12-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 1159.56 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1877609/TD1877614/TD1903807 |  | B | Contractor | Cancelled |  | n/a |  | 408 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1877526/TD1908742 |  | B | Contractor | Active | Estimating/Design | 2023-05-30 | Forecast | 2022 | Design | 131385.31 | EAC | 64.9779 | n/a | TBD | 2022 | - | 395.09 | 395.09 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1908070/TD1908084 |  | B | Contractor | Active | Estimating/Design | 2023-04-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 22258.55 | 21355.39 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1267772/TD1267779 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | -552.59 | -547.14 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD2023030/ TD1968171 |  | C | Business | Active | Estimating/Design | 2023-06-30 | Forecast | 875 | Design | 127296 | EAC | 145.4811 | n/a |  | 875 | 5 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1928836/TD1928848 |  | C | Contractor | Active | Estimating/Design | 2023-05-30 | Forecast | 1404 | Design | 316652 | EAC | 225.5356 | n/a | TBD | 1404 | 2 | 825.93 | 825.93 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1929625/TD1929639 |  | C | Contractor | Active | Estimating/Design | 2023-04-20 | Forecast | 449 | Design | 294647 | EAC | 656.2294 | n/a | TBD | 449 | 0 | 1037.98 | 1037.98 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1893809/TD1893815 |  | C | Contractor | Active | Estimating/Design | 2022-08-24 | Forecast | 2266 | Design | 0 | EAC | TBD | n/a | TBD | 2266 | 0 | 901.31 | 901.31 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Lake Elsinore | n/a | TD1896472/TD1896480 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Lake Forest | n/a | TD1722130/TD1722132 |  | B | Contractor | Active | Closed | 2021-06-18 | Actual | - | Design | 164699.94 | Actual | Unknown | n/a | 2712 | - | - | 164699.94 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
| Government Agency | n/a | Los Angeles | Lancaster | 13-46 | n/a | Ave I/ 10th St West to 20th St West | A | Government Agency | Hold | Planning | TBD |  | 6500 | Preliminary | 3600000 | EAC | 500 | n/a | TBD | 6500 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Lancaster | n/a | TD1882096/TD1882097 | 3041 W AVENUE K LANCASTER CA 93536 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1849761/TD1849764 |  | B | Business | Active | Estimating/Design | 2022-11-30 | Forecast | 1775 | Design | 469763 | EAC | 264.6552 | n/a | TBD | 1775 | - | 20823.49 | 20823.49 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1882263/TD1884214 |  | B | Business | Active | Construction | 2022-12-30 | Forecast | 1775 | Design | 468276 | EAC | 263.8175 | n/a | TBD | 1775 | - | 520549.42 | 520549.42 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1771226/TD1771230 |  | B | Contractor | Active | Closed | 2022-03-22 | Actual | 857 | Design | 77703.05 | Actual | 90.6687 | n/a | 364 | 857 | - | 77703.05 | 73240.36 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1862467/TD1862475 |  | B | Contractor | Active | Estimating/Design | 2023-07-06 | Forecast | 1834 | Design | 372544.98 | EAC | 203.1325 | n/a | TBD | 1834 | 1 | 10175.76 | 10175.76 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1704901/TD1705580 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1460311/TD1460314 |  | C | Contractor | Active | Closed | 2020-04-16 | Actual | 232 | Design | 31755 | Actual | 136.875 | n/a | 220 | 232 | 0 | 31755 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1877993/TD1877994 |  | C | Contractor | Active | Closed | 2022-08-01 | Actual | 361 | Design | 211177 | Actual | 584.9778 | n/a | 369 | 361 | 1 | 211177 | 209552 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Lancaster | n/a | TD1978089 |  | C | Business | Active | Estimating/Design | 2023-04-07 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Tulare | Lindsay | 11-48 | n/a | Sweet Brier Ave | A | Government Agency | Hold | Planning | TBD |  | 3150 | Preliminary | 3500000 | EAC | 350 | n/a | TBD | 3150 | 0 | 0 | 0 | Yes | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Loma Linda | n/a | TD2015395 | 25915 BARTON RD LOMA LINDA CA 92354 | C |  | Active | Estimating/Design | 2023-03-03 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 0 | 3312.22 | 3312.22 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD1506078/ TD1531443 |  | C | Contractor | Active | Closed | 2020-10-29 | Actual | 647 | Design | 158834.16 | Actual | 245.4933 | n/a | 0 | 647 | 19 | 158834.16 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD1555692/TD1570224 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD1782436 |  | C | Business | Active | Estimating/Design | 2021-12-30 | Forecast | TBD | Preliminary | 13403.77 | EAC | TBD | n/a | TBD | TBD | 14 | 18376.38 | 18376.38 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD1839542/TD1839543 |  | C | Contractor | Active | Estimating/Design | 2023-08-24 | Forecast | 923 | Design | 448566 | EAC | 485.987 | n/a | TBD | 923 | 33 | 3723.56 | 3008.12 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD2059600/TD2068480/TD2059599 |  | C | Business | Active | Estimating/Design | 2023-11-16 | Forecast | 1468 | Preliminary | 412613.97 | EAC | 281.0722 | n/a |  | 1468 | 59 | 211.79 | 211.79 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Long Beach | n/a | TD1992547 | 854 E 7TH ST LONG BEACH CA 90813 | C |  | Active | Estimating/Design | 2024-12-27 | Forecast | 1142 | Preliminary | 251731.12 | EAC | 220.4301 | n/a |  | 1142 | 33 | 404.04 | 404.04 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Long Beach | n/a | TD999563 |  | C | Business | Active | Estimating/Design | 2023-12-15 | Forecast | 0 | Preliminary | 20917.05 | EAC | TBD | n/a |  | 0 | 20 | 869.57 | 869.57 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Orange | Los Alamitos | n/a | TD1355328/TD1367212 |  | C | Contractor | Active | Closed | 2020-12-28 | Actual | 510 | Design | 143482.28 | Actual | 281.3378 | n/a | 535 | 510 | 14 | 143482.28 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1629460/TD1629461 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1565389 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1565400 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1936270 |  | C | Contractor | Active | Closed | 2022-03-31 | Actual | 145 | Design | 18381.95 | Actual | 126.7721 | n/a | 0 | 145 | 6 | 18381.95 | 17727.66 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1966301/ TD1972676 |  | C | Business | Active | Estimating/Design | 2023-12-27 | Forecast | 229 | Design | 71220 | EAC | 311.0044 | n/a | TBD | 229 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1471458/TD1471475 |  | C | Contractor | Active | Closed | 2020-04-10 | Actual | 489 | Design | 189519 | Actual | 0 | n/a | 811 | 489 | 49 | 189519 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Los Angeles | n/a | TD1936266 |  | C | Contractor | Active | Closed | 2022-03-30 | Actual | 0 | Design | 15512.98 | actual | 0 | n/a | 0 | 0 | 0 | 15512.98 | 15512.98 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD2067170/TD2067171 |  | B | Business | Active | Estimating/Design | 2027-07-23 | Forecast | TBD | Preliminary | - | EAC | TBD | N/A |  | TBD | - | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1460367/TD1460368 |  | B | Individual | Cancelled |  | n/a |  | 1304 | Design | 328261 | EAC | 251.7339 | n/a | TBD | 1304 | - | 0.38 | -569.78 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1679433/TD1679435 |  | B | Individual | Active | Estimating/Design | 2025-12-26 | Forecast | 2299 | Design | 487338 | EAC | 211.9783 | n/a | TBD | 2299 | 26 | 2258.54 | 1540.94 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1788161 |  | B | Contractor | Active | Estimating/Design | 2023-07-27 | Forecast | TBD | Preliminary | 10000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1512473/TD1512474 |  | B | Individual | Cancelled |  | n/a |  | 1282 | Design | 218328.13 | EAC | Unknown | n/a | Unknown | Unknown | 18 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1630213/TD1630214 |  | B | Individual | Active | Estimating/Design | 2024-12-20 | Forecast | 583 | Design | 59549 | EAC | 102.1424 | n/a | TBD | 583 | 10 | 2322.2 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1858664/TD1858665 |  | B | Individual | Active | Estimating/Design | 2023-09-08 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | - | 56.89 | 56.89 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1548602/TD1548628 |  | B | Individual | Active | Closed | 2021-02-23 | Actual | 1111 | Design | 161394.97 | Actual | 145.27 | n/a | 1063 | 1111 | 7 | 161394.97 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1888079 |  | B | Individual | Cancelled |  | n/a |  | n/a |  | 3097.48 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1424835/TD1424836 |  | B | Individual | Active | Estimating/Design | 2025-12-26 | Forecast | 1459 | Design | 170692.3 | EAC | 116.9927 | n/a | TBD | 1459 | 5 | 5540.87 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1719078/TD1719080 |  | B | Contractor | Active | Estimating/Design | 2025-12-26 | Forecast | 2095 | Design | 211755 | EAC | 101.0764 | n/a | TBD | 2095 | 4 | 8444.49 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1454428/TD1454547 |  | C | Individual | Active | Estimating/Design | 2024-07-18 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1944805/TD1944806 |  | C | Contractor | Active | Estimating/Design | 2023-01-26 | Forecast | 739 | Design | 154958 | EAC | 209.6861 | n/a | TBD | 739 | 5 | 5310.85 | 5310.85 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1413827 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | no | Unknown | Unknown | Rural | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1575977/TD575978 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | no | Unknown | Unknown | Rural | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD802110/TD862154 |  | C | Contractor | Active | Estimating/Design | 2025-06-10 | Forecast | 1876 | Design | 454713 | EAC | 242.3843 | n/a | TBD | 1876 | 3 | 12052.76 | 3900.03 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1792976 |  | C | Individual | Active | Estimating/Design | 2024-07-17 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD2047489 |  | C | Business | Active | Estimating/Design | 2025-07-18 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1816040/TD1816041 |  | C | Individual | Active | Closed | 2022-04-07 | Actual | 358 | Design | 121870 | actual | 340.419 | n/a | 303 | 358 | 14 | 121870 | 121234 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1788156 |  | C | Contractor | Active | Estimating/Design | 2025-07-24 | Forecast | TBD | Preliminary | 5000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1829121/TD1829122 |  | C | Individual | Active | Closed | 2022-08-10 | Actual | 361 | Design | 53302 | Actual | 147.651 | n/a | 185 | 361 | 1 | 53302 | 50817 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD2080570/ TD2080571 |  | C | Individual | Active | Estimating/Design | 2024-07-31 | Forecast | 653 | Preliminary | 113375 | EAC | 173.6217 | n/a |  | 653 | 4 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1854493/TD1854494 |  | C | Individual | Active | Estimating/Design | 2023-12-29 | Forecast | 254 | Design | 59233 | EAC | 233.2008 | n/a | TBD | 254 | 0 | 5884 | 2435.02 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1564521/TD1564522 |  | C | Individual | Active | Closed | 2020-06-01 | Actual | 411 | Design | 36500.11 | Actual | 88.8081 | n/a | 32 | 411 | 0 | 36500.11 | 0 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1392963/TD1392964 |  | C | Individual | Active | Estimating/Design | 2025-07-15 | Forecast | 194 | Design | 65015 | EAC | 335.1289 | n/a | TBD | 194 | 3 | 3528.23 | 56.37 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1283252/TD1417526 |  | C | Individual | Active | Estimating/Design | 2025-12-26 | Forecast | 307 | Design | 25713 | EAC | 83.7557 | n/a | TBD | 307 | 0 | 3355.94 | 0 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1846785/TD1846786 |  | C | Individual | Active | Estimating/Design | 2023-12-15 | Forecast | 171 | Design | 11954.34 | EAC | 69.9084 | n/a | TBD | 171 | 9 | 4194.73 | 0 | Unknown | n/a | No | No | No | Rural | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1540208/TD1540209 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Rural | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1453027/TD1453028 |  | C | Individual | Active | Closed | 2022-09-07 | Actual | 344 | Design | 85306.51 | Actual | 247.984 | n/a | 306 | 344 | 3 | 85306.51 | 80838 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1784876/TD1784877 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1784815/TD1784818 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1768800/TD1768802 |  | C | Individual | Active | Estimating/Design | 2023-11-24 | Forecast | 197 | Design | 16131 | EAC | 81.8832 | n/a | TBD | 197 | 6 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD2008137 |  | C | Individual | Active | Estimating/Design | 2024-05-16 | Forecast | 0 | Preliminary | 5000 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1758759 |  | C | Individual | Active | Estimating/Design | 2023-01-26 | Forecast | TBD | Preliminary | 1200 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1769303/TD1769304 |  | C | Contractor | Active | Estimating/Design | 2023-11-30 | Forecast | 138 | Design | 31315 | EAC | 226.9203 | n/a | TBD | 138 | 4 | 683.13 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1772453 |  | C | Contractor | Active | Estimating/Design | 2022-05-27 | Forecast | TBD | Preliminary | 2200 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1885170/TD1889479 |  | C | Individual | Active | Closed | 2022-03-17 | Actual | 147 | Design | 17507.28 | Actual | 119.0971 | n/a | Secondary only | 147 | 2 | 17507.28 | 15979.39 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1890694/TD1890695 |  | C | Individual | Active | Closed | 2022-09-14 | Actual | 474 | Design | 33439 | Actual | 70.5464 | n/a | 549 | 474 | 4 | 33439 | 33439 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Malibu | n/a | TD1384442/TD1384445 |  | C | Individual | Active | Estimating/Design | 2025-12-26 | Forecast | 396 | Design | 99173 | EAC | 250.4369 | n/a | TBD | 396 | 5 | 681.93 | 0 | Unknown | n/a | No | No | No | Rural | 2 | n/a | n/a
| Government Agency | n/a | Mono | Mammoth Lakes | 2022-15 | n/a | Laurel Mountain Rd. from Hwy 203 to 300' North of Tavern Rd. | A | Government Agency | Hold | Planning | TBD |  | 750 | Preliminary | 700000 | EAC | 750 | n/a | TBD | 750 | 0 | 0 | 0 |  | Arterial Street or Major Collector | No | No | No | Urban Cluster | 0 | n/a | n
|  | n/a | Mono | Mammoth Lakes | n/a | TD1403374/TD1403375 |  | C | Contractor | Active | Estimating/Design | 2023-04-05 | Forecast | 0 | Preliminary | 19136 | EAC | TBD | n/a | TBD | 0 | 0 | 6373.78 | 0 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
| CITY OF MANHATTAN BEACH | n/a | Los Angeles | Manhattan Beach | n/a | TD666072 | 1ST/DIANTHUS MANHATTAN BEACH CA 90266 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 1106.54 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | -341.69 | -341.7 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| MANHATTAN BEACH, CITY OF | n/a | Los Angeles | MANHATTAN BEACH | n/a | TD2020305/TD2020307 | CREST DR ROSECRANS AVE TO MARINE AVE MANHATTAN BEACH CA 90266 | B | Government Agency | Active | Estimating/Design | 2024-06-28 | Forecast | TBD | Preliminary | 150000 | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| MANHATTAN BEACH, CITY OF | n/a | Los Angeles | MANHATTAN BEACH | n/a | TD2020294/TD2020296 | OCEAN DR 14TH PL TO 8TH ST MANHATTAN BEACH CA 90266 | B | Government Agency | Active | Estimating/Design | 2024-06-28 | Forecast | TBD | Preliminary | 100000 | EAC | TBD | n/a |  | TBD | - | - | - | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Manhattan Beach | UUAD12 | TD1249184/TD237146/TD237163 |  | B | Individual | Active | Construction | 2022-06-30 | Forecast | 283 | Design | 3412299 | EAC | 12057.5936 | n/a | TBD | 283 | 340 | 2742317.21 | 190490.73 | Unknown | n/a | No | No | No | Rural | 46 | n/a | n/a
| CITY OF MANHATTAN BEACH | n/a | Los Angeles | Manhattan Beach | UUAD14 | TD1389048/TD666049 | OCEAN, MOONSTONE TO ROSECRANS MANHATTAN BEACH CA 90266 | B | Government Agency | Active | Construction | 2022-06-30 | Forecast | 199 | Design | 3139197 | EAC | 15774.8593 | n/a | TBD | 199 | 421 | 2454808.42 | 153831.34 | Unknown | n/a | No | No | No | Rural | 41 | n/a | n/a
| CITY OF MANHATTAN BEACH | n/a | Los Angeles | Manhattan Beach | n/a | TD1351127/TD1351129 | UUAD #4 MANHATTAN BEACH CA 90266 | B | Government Agency | Active | Construction | 2022-12-30 | Forecast | 12637 | Design | 3501205 | EAC | 277.0598 | n/a | TBD | 12637 | 178 | 3226877.81 | 1942914.66 | Unknown | n/a | No | No | No | Urban Cluster | 78 | n/a | n/a
|  | n/a | Los Angeles | MANHATTAN BEACH | n/a | TD1975637/TD2011844 |  | C | Business | Active | Estimating/Design | 2023-12-27 | Forecast | 227 | Preliminary | 109763.08 | EAC | 483.5378 | n/a |  | 227 | 15 | 2774.86 | 2774.86 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Manhattan Beach | n/a | TD1639580/TD1639581 |  | C | Individual | Active | Closed | 2022-09-02 | Actual | 396 | Design | 70519.19 | Actual | 178.0788 | n/a | TBD | 396 | 15 | 70519.19 | 66404.92 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Manhattan Beach | n/a | TD1198394/TD1198395 |  | C | Individual | Active | Estimating/Design | 10827/22 | Forecast | 60 | Design | 14756 | EAC | 245.9333 | n/a | TBD | 60 | 1 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Manhattan Beach | n/a | TD1637549/TD1637550 |  | C | Individual | Active | Estimating/Design | 2022-05-20 | Forecast | 121 | Design | 13398.72 | EAC | 110.7332 | n/a | TBD | 121 | 16 | 16037.87 | 4625.06 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Los Angeles | Maywood | 6268 | n/a | Fruitland Avenue /Vista Loma Avenue to East City Limits | A | Government Agency | Active | Planning | TBD |  | 1180 | Preliminary | 1000000 | EAC | 750 | n/a | TBD | 1180 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Maywood | 6268 | TD2053814/TD2053816 | Maywood Ave/Slauson to 58th St. | A | Government Agency | Active | Estimating/Design | 2026-04-24 | Forecast | 1600 | Preliminary | 1300000 | EAC | 750 | n/a | TBD | 1600 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Riverside | Menifee | 2022-36 | n/a | Goetz Road and Vista | A | Government Agency | Hold | Planning | 2025-10-16 | Forecast | 1082 | Preliminary | 700000 | EAC | 600 | n/a | TBD | 1082 | 0 | 0 | 0 |  | Arterial Street or Major Collector | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1732458/TD1732461 |  | B | Individual | Cancelled |  | n/a |  | 673 | Design | 80976.69 | EAC | 120.322 | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1549899/TD1549900 |  | B | Contractor | Active | Closed | 2020-08-17 | Actual | 2396 | Design | 502093.16 | Actual | 209.5547 | n/a | 1779 | 2396 | 0 | 502093.16 | 407.18 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1504005 |  | B | Contractor | Active | Closed | 2020-03-04 | Actual | 1071 | Design | 101333.07 | Actual | TBD | n/a | 0 | 1071 | 1 | 101333.07 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1470064/TD1470066 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 359.44 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1614703/TD1614704 |  | B | Contractor | Active | Estimating/Design | 2022-09-06 | Forecast | 1421 | Design | 157194 | EAC | 110.6221 | n/a | TBD | 1421 | - | 10175.01 | 823.49 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1484223/TD1484224 |  | B | Contractor | Active | Construction | 2022-11-21 | Forecast | 2839 | Design | 716433 | EAC | 252.354 | n/a | TBD | 2839 | - | 1124749.54 | 211353.43 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1885518/TD1885519/TD1903794/TD2054688 |  | B | Contractor | Active | Estimating/Design | 2023-11-29 | Forecast | 5527 | Design | 1360559.27 | EAC | 246.166 | n/a | TBD | 5527 | 2 | 808.38 | 626.27 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1937403/TD1937415 |  | C | Individual | Active | Construction | 2023-01-09 | Forecast | 757 | Design | 125759 | EAC | 166.1281 | n/a | TBD | 757 | 20 | 403053 | 403053 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1358236/TD1358238 |  | C | Contractor | Active | Closing | 2022-07-01 | Actual | 3534 | Design | 651252.51 | Actual | 184.282 | n/a | 2588 | 3534 | 2 | 651252.51 | 643133.97 | Unknown | n/a | No | No | No | Urban Cluster | 15 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1775422/TD1777702/TD1819723 |  | C | Contractor | Active | Closed | 2022-07-29 | Actual | 1406 | Design | 504243.88 | Actual | 358.6372 | n/a | 1584 | 1406 | 1 | 504243.88 | 500124.78 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1995897/ TD1995900 |  | C | Business | Active | Estimating/Design | 2023-10-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 279.46 | 279.46 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1939589/TD1939591 |  | C | Contractor | Active | Estimating/Design | 2023-03-17 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1928943/TD1928949 |  | C | Contractor | Active | Estimating/Design | 2023-04-25 | Forecast | 2151 | Design | 578378.88 | EAC | 268.8884 | n/a | TBD | 2151 | 1 | 2048.61 | 2048.61 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Menifee | n/a | TD1623512/TD1623513 |  | C | Contractor | Active | Closed | 2021-05-19 | Actual | 1254 | Design | 346882 | Actual | 276.6204 | n/a | 1261 | 1254 | 3 | 346882 | 0 | Unknown | n/a | no | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD2043291/TD1983252 |  | B | Business | Active | Estimating/Design | 2023-09-08 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD1643896 |  | B | Contractor | Active | Estimating/Design | 2020-07-10 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD1644788/TD1645695 |  | B | Contractor | Active | Estimating/Design | 2021-07-01 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD2054808/TD2054801 |  | C | Business | Active | Estimating/Design | 2024-01-24 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 12 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD2061821/TD2061825 |  | C | Business | Active | Estimating/Design | 2023-11-16 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD1512056/TD1512059 |  | C | Contractor | Active | Estimating/Design | 2022-02-14 | Forecast | 677 | Design | 323508 | EAC | 477.8552 | n/a | TBD | 677 | 0 | 968.79 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | Monrovia | n/a | TD1807776/ TD1981706 |  | C | Contractor | Active | Estimating/Design | 2023-02-17 | Forecast | 1111 | Preliminary | 305289 | EAC | 274.7876 | n/a | TBD | 1111 | 2 | 5657.09 | 5657.09 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Montclair | n/a | TD1727906/TD1727907 |  | C | Contractor | Active | Closed | 2021-09-02 | Actual | 242 | Design | 14740.82 | Actual | 60.9125 | n/a | 176 | 242 | 2 | 14740.82 | 3459.61 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Los Angeles | Montebello | 02 45 | TD443728/TD443740/TD2074327/TD2074326 | Beverly/ Montebello-E. City Bdry | A | Government Agency | Hold | Estimating/Design | 2025-11-10 | Forecast | 5200 | Preliminary | 3300000 | EAC | 550 | n/a | TBD | 5200 | 0 | 96572 | -190208.17 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Monterey Park | 11257 | TD359678/TD359677 | Newmark/Garfield-New Avenue | A | Government Agency | Cancelled | Estimating/Design | 2022-09-16 | Forecast | 11430 | Preliminary | 5700000 | EAC | 427 | n/a | TBD | 11430 | 0 | 352.98 | -309.05 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Monterey Park | n/a | TD1678292/TD1678278 |  | B | Contractor | Active | Estimating/Design | 2021-11-19 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 43955.13 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| Government Agency | n/a | Los Angeles | Monterey Park | 2022-R71 | TD2041069/ TD2041072 | Monterey Pass Rd/Garvey Ave. to Vagabond Dr. | A | Government Agency | Active | Estimating/Design | 2025-11-02 | Forecast | 8745 | Preliminary | 6800000 | EAC | 700 | n/a | TBD | 8745 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Monterey Park | n/a | TD1590769/TD1590770 | 100 S GARFIELD BLVD MONTEREY PARK CA 91754 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Moorpark | n/a | TD1557408/TD1620530 |  | B | Contractor | Cancelled |  | n/a |  | 1007 | Design | 225535.15 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 5 | n/a | n/a
| CITY OF, MOORPARK | n/a | Ventura | Moorpark | n/a | TD180036/TD1810038/TD1868074 | PRINCETON AVE/EAST OF SPRING RD MOORPARK CA 93021 | B | Government Agency | Active | Estimating/Design | 2024-07-18 | Forecast | 5839 | Design | 1055564.77 | EAC | 180.7783 | n/a | TBD | 5839 | 8 | 1370.93 | 532.76 | Unknown | n/a | No | No | No | Urban Cluster | 15 | n/a | n/a
|  | n/a | Ventura | Moorpark | n/a | TD1773336 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Moorpark | n/a | TD1755284/TD1755285 |  | C | Contractor | Active | Estimating/Design | 2024-07-18 | Forecast | 516 | Design | 226195 | EAC | 438.3624 | n/a | TBD | 516 | 3 | 1648.48 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Ventura | Moorpark | n/a | TD1669533/TD1669535 |  | C | Contractor | Active | Estimating/Design | 2022-12-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | no | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Ventura | Moorpark | n/a | TD1984962 | 220 E HIGH STE MOORPARK CA 93021 | C |  | Active | Estimating/Design | 2024-04-26 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 360.95 | 360.95 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1811062/TD1811063 |  | B | Contractor | Active | Closed | 2022-04-22 | Actual | 927 | Design | 222758.23 | Actual | 240.3001 | n/a | 876 | 927 | - | 222758.23 | 161581.86 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1688723/TD1688724 |  | B | Contractor | Active | Closed | 2021-07-26 | Actual | 812 | Design | 400483.64 | Actual | 493.2065 | n/a | 688 | 812 | - | 400483.64 | -16928.62 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1765791/TD1765792 |  | B | Contractor | Active | Closed | 2022-07-13 | Actual | 603 | Design | 243196.01 | Actual | 403.3101 | n/a | 906 | 603 | - | 243196.01 | 230610.74 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1563254/TD1563255 |  | B | Contractor | Active | Estimating/Design | 2023-02-28 | Forecast | 791 | Design | 353283.78 | EAC | 446.6293 | n/a | TBD | 791 | - | 10499.43 | 2411.09 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1692550/TD1729423 |  | B | Contractor | Cancelled |  | n/a |  | 984 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1686923/TD1686926 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1480670/TD1480671 |  | C | Contractor | Active | Closed | 2020-07-01 | Actual | 412 | Design | 187393 | Actual | 454.8374 | n/a | 445 | 412 | 0 | 187393 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1463686 |  | C | Contractor | Active | Closed | 2020-05-07 | Actual | 2587 | Design | 327996.36 | Actual | 126.7864 | n/a | 4871 | 2587 | 0 | 327996.36 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1635050/TD1635112 |  | C | Contractor | Active | Closed | 2021-10-19 | Actual | 2030 | Design | 767055 | Actual | 377.8596 | n/a | 1344 | 2030 | 16 | 767055 | 4623.34 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1729410/TD1729481 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1718632/TD1718641 |  | C | Contractor | Active | Closed | 2021-04-26 | Actual | 382 | Design | 76176.74 | Actual | 199.4155 | n/a | 285 | 382 | 4 | 76176.74 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD1479873/TD1479877 |  | C | Contractor | Active | Closed | 2020-02-11 | Actual | 834 | Design | 151842 | Actual | 182.0647 | n/a | 508 | 834 | 0 | 151842 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Moreno Valley | n/a | TD2003840/ TD2003842 |  | C | Business | Active | Estimating/Design | 2023-08-21 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 3144.31 | 3144.31 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1927549/TD1927550/TD2003403/TD2003216 |  | B | Contractor | Active | Estimating/Design | 2023-06-15 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 24.26 | 24.26 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1610779/TD1610780 |  | B | Contractor | Cancelled |  | n/a |  | 1180 | Design | 195098.22 | EAC | Unknown | n/a | Unknown | Unknown | 8 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1795581/TD1795586 |  | B | Contractor | Active | Construction | 2022-11-08 | Forecast | TBD | Design | 38360.19 | EAC | #VALUE! | n/a | TBD | TBD | 1 | 56075.1 | 56075.1 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1508411/TD1508419 |  | B | Contractor | Active | Closing | 2021-03-03 | Actual | 965 | Design | 246222.32 | Actual | 255.1527 | n/a | 917 | 965 | - | 246222.32 | 17161.7 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1927595/TD1927644 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1389170 |  | C | Contractor | Active | Closed | 2020-09-28 | Actual | 590 | Design | 181106.51 | Actual | 306.9602 | n/a | 316 | 590 | 0 | 181106.51 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1498733/TD1498735 |  | C | Contractor | Active | Closed | 2020-12-28 | Actual | 770 | Design | 138101 | Actual | 179.3519 | n/a | 714 | 770 | 1 | 138101 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| UNKNOWN | n/a | Riverside | Murrieta | n/a | TD1596759/TD1596760 | 41833 IVY ST MURRIETA CA 92562 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD2031552/ TD2031548 |  | C | Business | Active | Estimating/Design | 2023-08-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1607323/TD1607327 |  | C | Business | Active | Closing | 2022-07-19 | Actual | 1206 | Design | 276842 | Actual | 229.5539 | n/a | 277 | 1206 | 0 | 276842 | 267510 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1870948/TD1870954/TD1915165 |  | C | Contractor | Active | Estimating/Design | 2023-04-20 | Forecast | 809 | Design | 272774 | EAC | 337.1743 | n/a | TBD | 809 | 1 | 2615.7 | 2615.7 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1951533/TD1951538/ TD2003234 |  | C | Contractor | Active | Estimating/Design | 2023-01-27 | Forecast | 222 | Design | 0 | EAC | TBD | n/a | TBD | 222 | 2 | 2170 | 2170 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1871436/TD1871439 |  | C | Contractor | Active | Estimating/Design | 2023-03-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 111.23 | 111.23 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Murrieta | n/a | TD1544768/TD1544769 |  | C | Contractor | Active | Closed | 2020-09-30 | Actual | 660 | Design | 188833 | Actual | 286.1106 | n/a | 250 | 660 | 0 | 188833 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Orange | Newport Beach | 2013-82 | TD1509510/TD1573998/ TD1507697 | Balboa Blvd/28th to 24th - PH 2 | A | Government Agency | Active | Construction | 2023-04-15 | Forecast | 4790 | Design | 2780000 | EAC | 750 | n/a | TBD | 4790 | 276 | 3914657.55 | 912870.61 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 24 | n/a | n/a
| Government Agency | n/a | Orange | Newport Beach | 2013-82 | TD781739/TD781741 | Balboa Blvd/PCH to 28th | A | Government Agency | Active | Closed | 2022-07-26 | Actual | 2745 | Design | 3883579.71 | Actual | 1388 | n/a | 682 | 2745 | 128 | 3883579.71 | 74575.75 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 14 | n/a | n/a
| Government Agency | n/a | Orange | Newport Beach | 2013-82 | TD1574917/TD1574918 | Court St - PH3 | A | Government Agency | Active | Construction | 2023-04-15 | Forecast | 1203 | Preliminary | 970000 | EAC | 750 | n/a | TBD | 1203 | 150 | 1110587.94 | 447966.39 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 12 | n/a | n/a
| NEWPORT BEACH CITY OF | n/a | Orange | Newport Beach | n/a | TD1103838/TD1103841 | BALBOA BLVD. RIVER AVE/ 38TH ST NEWPORT BEACH CA 92663 | B | Government Agency | Active | Closed | 2022-10-28 | Actual | 3221 | Design | 727644.82 | Actual | 225.9065 | n/a | 0 | 3221 | 148 | 727644.82 | 114256.31 | Unknown | n/a | No | No | No | Urban Cluster | 26 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Newport Beach | n/a | TD1878534/TD1878535 | BALBOA ISLAND NEWPORT BEACH CA 92658 | B | Government Agency | Active | Estimating/Design | 2024-12-31 | Forecast | TBD | Preliminary | 270000 | EAC | TBD | n/a | TBD | TBD | 0 | 445262.88 | 191436.37 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| NEWPORT BEACH CITY OF | n/a | Orange | Newport Beach | n/a | TD1103674/TD1103682 | NEWPORT BLVD/23RD ST/OCEAN FRONT W/31ST NEWPORT BEACH CA 92663 | B | Government Agency | Active | Construction | 2022-08-16 | Forecast | 5762 | Design | 2054366 | EAC | 356.537 | n/a | TBD | 5762 | 270 | 1487921.1 | 1195005.2 | Unknown | n/a | No | No | No | Urban Cluster | 43 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Newport Beach | n/a | TD1103828/TD1103830 | RIVER AVE / 47TH ST / BALBOA BLVD 45ST. NEWPORT BEACH CA 92663 | B | Government Agency | Active | Closed | 2022-08-05 | Actual | 1324 | Design | 178321.92 | Actual | 134.6842 | n/a | TBD | 1324 | 104 | 178321.92 | 78724.09 | Unknown | n/a | No | No | No | Urban Cluster | 15 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Newport Beach | n/a | TD1828598/TD1828602 | SANTA ANA AVENUE AND CLIFF DRIVE NEWPORT BEACH CA 92663 | B | Government Agency | Active | Estimating/Design | 2024-12-31 | Forecast | 5656 | Design | 963349.88 | EAC | TBD | n/a | TBD | 5656 | 55 | 64255.19 | 5651.12 | Unknown | n/a | No | No | No | Urban Cluster | 24 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Newport Beach | n/a | TD1821690/TD1521691/TD1539040 | VARIOUS LOCATION NEWPORT BEACH CA 92658 | B | Government Agency | Active | Construction | 2028-12-31 | Forecast | 6768 | Design | 2484209 | EAC | 367.0522 | n/a | TBD | 6768 | 322 | 471436.22 | 188881.45 | Unknown | n/a | No | No | No | Urban Cluster | 42 | n/a | n/a
|  | n/a | Orange | Newport Beach | n/a | TD1717598 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Newport Beach | n/a | TD1668293/TD1668294 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Newport Beach | n/a | TD1609410 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Newport Beach | n/a | TD1617874/TD1619080 | 3955 W BALBOA BLVD NEWPORT BEACH CA 92663 | C | Government Agency | Active | Construction | 2023-03-28 | Forecast | 126 | Design | 23905 | EAC | 189.7222 | n/a | TBD | 126 | 35 | 74572.52 | 840.44 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Norwalk | 04-55 | TD1189453/TD1189454 | Pioneer Blvd/ Alondra Blvd -166th St. | A | Government Agency | Active | Closing | 2022-09-22 | Actual | 7564 | Design | 7098383.03 | Actual | 550 | n/a | TBD | 7564 | 104 | 7098383.03 | 1341026.4 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 34 | n/a | n/a
| Government Agency | n/a | Los Angeles | Norwalk | 04-55 | n/a | Pioneer Blvd/ Rosecrans Ave - Alondra Blvd | A | Government Agency | Hold | Planning | TBD |  | 7564 | Preliminary | 0 |  | Unknown | n/a | TBD | 7564 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD203300/ TD2078311/ TD2033071 |  | C | Business | Active | Estimating/Design | 2023-12-14 | Forecast | 461 | Preliminary | 144131 | EAC | 312.6486 | n/a |  | 461 | 10 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD1743255/TD1768735 |  | C | Individual | Active | Closed | 2021-04-19 | Actual | 96 | Design | 15394 | Actual | 0 | n/a | 86 | 96 | 5 | 15394 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD2025698 |  | C | Individual | Active | Estimating/Design | 2024-02-21 | Forecast | TBD | Preliminary | 900 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD1979854/TD1979855 |  | C | Business | Active | Estimating/Design | Unknown | Forecast | Unknown | Preliminary | Unknown | EAC | Unknown | N/A | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | - | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD1979683/TD1979685 |  | C | Business | Active | Estimating/Design | Unknown | Forecast | Unknown | Preliminary | Unknown | EAC | Unknown | N/A | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | - | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD2028205/TD2028206 |  | C | Individual | Active | Estimating/Design | 2023-10-11 | Forecast | 109 | Preliminary | 22056 | EAC | 202.3486 | n/a |  | 109 | 3 | 1586.43 | 1586.43 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD1743133 |  | C | Individual | Active | Estimating/Design | 2023-05-23 | Forecast | TBD | Preliminary | 25936.86 | EAC | TBD | n/a | TBD | TBD | 1 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Ventura | Ojai | n/a | TD1785014 |  | C | Individual | Active | Estimating/Design | 2023-10-11 | Forecast | 501 | Design | 77716 | EAC | 155.1218 | n/a | TBD | 501 | 0 | 2854.29 | 1597.74 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Ontario | 2005-092 | TD1306458/TD1306462 | Holt/ Mountain | A | Government Agency | Active | Estimating/Design | 2024-06-30 | Forecast | 3310 | Design | 3900000 | EAC | 500 | n/a | TBD | 3310 | 16 | 24066.53 | 7147.56 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 20 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD267050 |  | B | Contractor | Active | Estimating/Design | 2009-06-26 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 1697.07 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1389649/TD1442032/TD1505186 |  | B | Contractor | Active | Estimating/Design | 2021-12-27 | Forecast | 10076 | Design | 1688279.42 | EAC | 167.5545 | n/a | TBD | 10076 | 11 | 426326.84 | -4475.2 | Unknown | n/a | No | No | No | Urban Cluster | 16 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1647480/TD1647483 |  | B | Contractor | Active | Closed | 2020-11-09 | Actual | 1954 | Design | 323622.3 | Actual | 165.6204 | n/a | 2660 | 1954 | - | 323622.3 | -9919.08 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1307319/TD1307322 |  | B | Contractor | Active | Closed | 2020-04-24 | Actual | 1111 | Design | 281029.41 | Actual | 252.9518 | n/a | 1589 | 1111 | 6 | 281029.41 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1788427/TD1788428 |  | B | Contractor | Active | Closing | 2022-10-04 | Actual | 2467 | Design | 567650.37 | Actual | 230.0974 | n/a | 2038 | 2467 | - | 567650.37 | 564335.1 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1889130/TD1889137 |  | B | Contractor | Active | Estimating/Design | 2023-07-20 | Forecast | 2476 | Design | 497210.09 | EAC | 200.8118 | n/a | TBD | 2476 | 1 | 3088.87 | 3088.87 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Ontario | n/a | TD1983652/TD1983653 | CHINO AVE. ONTARIO CA 91710 | B |  | Active | Estimating/Design | 2023-05-26 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| CITY OF FONTANA | n/a | San Bernardino | Ontario | n/a | TD1414987/TD1414988 | ETIWANDA & SLOVER ONTARIO CA 91761 | B | Government Agency | Cancelled |  | 2021-03-01 | Forecast | 1298 | Design | 519849 | EAC | 400.5 | n/a | TBD | 1298 | 54 | 0 | -8727.96 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Ontario | n/a | TD1966659/TD1966660 | ETIWANDA & SLOVER ONTARIO CA 91761 | B |  | Active | Estimating/Design | 2022-10-31 | Forecast | 1232 | Design | 681532 | EAC | 553.1916 | n/a | TBD | 1232 | - | 18835.07 | 18835.07 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1959421/TD1959682 |  | B | Business | Active | Estimating/Design | 2023-02-24 | Forecast | Unknown | Preliminary | - | EAC | TBD | n/a |  | Unknown | - | 287.08 | 287.08 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Ontario | n/a | TD1959789/TD1959787 | HAVEN AVE. ONTARIO CA 91710 | B |  | Active | Estimating/Design | 2023-01-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD2071872/TD2072040 |  | B | Individual | Active | Estimating/Design | 2023-06-07 | Forecast | 1648 | Design | 306324.75 | EAC | TBD | n/a |  | 1648 | 12 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 16 | n/a | n/a
| CITY OF ONTARIO | n/a | San Bernardino | Ontario | n/a | TD1265280/TD1265282 | HOLT & MOUNTAIN ONTARIO CA 91761 | B | Government Agency | Active | Construction | 2023-03-15 | Forecast | 6286 | Design | 1787770.69 | EAC | 284.4051 | n/a | TBD | 6286 | 32 | 359226.92 | 264234.8 | Unknown | n/a | Yes | No | No | Urban Cluster | 38 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD2070716/TD2073458 |  | B | Business | Active | Estimating/Design | 2023-12-04 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1909193/TD1909196 |  | B | Contractor | Active | Estimating/Design | 2023-07-10 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1890259/TD1890267/TD1943936 |  | B | Contractor | Active | Estimating/Design | 2023-07-20 | Forecast | 960 | Design | 219107.04 | EAC | TBD | n/a | TBD | 960 | - | 33237.73 | 33237.73 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Ontario | n/a | TD1983663/TD1983666 | RIVERSIDE DRIVE ONTARIO CA 91710 | B |  | Active | Estimating/Design | 2022-09-30 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD267830 |  | B | Contractor | Active | Estimating/Design | 2009-03-26 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1759143/TD1780794/TD1780796 |  | B | Contractor | Active | Estimating/Design | 2023-01-27 | Forecast | 1429 | Design | 382215.5 | EAC | 267.4706 | n/a | TBD | 1429 | 4 | 10202.35 | 760.13 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1573326/TD1573346 |  | B | Contractor | Active | Estimating/Design | 2020-07-22 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Ontario | n/a | TD2070725/TD2073487 | Transit St &Palm Ave ONTARIO CA 91762 | B |  | Active | Estimating/Design | 2023-12-08 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1639861/TD1639862 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1645772/TD1645773 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1645732/TD1645736 |  | C | Contractor | Active | Closed | 2022-07-25 | Actual | 469 | Design | 213205 | Actual | 454.5949 | n/a | 605 | 469 | 3 | 213205 | 208507.44 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1595792/TD1595801 |  | C | Contractor | Active | Estimating/Design | 2020-09-11 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1952312/TD1952313 |  | C | Business | Active | Estimating/Design | 2023-03-23 | Forecast | 325 | Design | 150062.19 | EAC | 461.7298 | n/a | TBD | 325 | 0 | 40.08 | 40.08 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD2054403/ TD2054406 |  | C | Business | Active | Estimating/Design | 2023-11-01 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1707223/TD1707224 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | San Bernardino | Ontario | n/a | TD1600575/TD1600581 |  | C | Business | Active | Closed | 2022-01-23 | Actual | 242 | Design | 91840.76 | Actual | 379.5073 | n/a | 436 | 242 | 4 | 91840.76 | 42048.72 | Unknown | n/a | no | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | Orange | Orange | n/a | TD2021842 | ORNG HGTS CHAPMAN AVE/SANTIAGO CYN WO1 ORANGE CA 92869 | B |  | Active | Estimating/Design | 2023-05-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 6014.81 | 6014.81 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Orange | Orange | n/a | TD2021843 | ORNG HGTS CHAPMAN AVE/SANTIAGO CYN WO2 ORANGE CA 92869 | B |  | Active | Estimating/Design | 2023-05-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Orange | Orange | n/a | TD2021844 | ORNG HGTS CHAPMAN AVE/SANTIAGO CYN WO3 ORANGE CA 92869 | B |  | Active | Estimating/Design | 2023-05-05 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| CITY OF ORANGE | n/a | Orange | Orange | n/a | TD1161766 | VILAREAL N/ESCHOLWTR ORANGE CA 92867 | C | Government Agency | Active | Closed | 2020-03-13 | Actual | 296 | Design | 51342.93 | Actual | 173.4558 | n/a | 210 | 296 | 1 | 51342.93 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Oxnard | n/a | TD1248419/TD1248423 |  | B | Contractor | Active | Estimating/Design | 2023-06-30 | Forecast | 3377 | Design | 324361 | EAC | 96.05 | n/a | TBD | 3377 | 1 | 25458.2 | 6264.25 | Unknown | n/a | No | No | No | Urban Cluster | 13 | n/a | n/a
| UNKNOWN | n/a | Ventura | Oxnard | n/a | TD1853191/TD1853192/TD1857652 | N ROSE AVE & CAMINO DEL SOL OXNARD CA 93030 | B |  | Active | Estimating/Design | 2023-10-26 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 5 | 12057.56 | 6277.78 | Unknown | n/a | Yes | No | No | Urban Cluster | 19 | n/a | n/a
|  | n/a | Ventura | Oxnard | n/a | TD1450681/TD1450682 |  | C | Contractor | Active | Closed | 2021-04-22 | Actual | 1387 | Design | 203706 | Actual | 146.8681 | n/a | 1172 | 1387 | 10 | 203706 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
| UNKNOWN | n/a | Ventura | Oxnard | n/a | TD2016552/ TD2016549 | 241 W 2ND ST OXNARD CA 93030 | C |  | Active | Estimating/Design | 2023-07-18 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 0 | 2377.1 | 2377.1 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Oxnard | n/a | TD1977988/ TD1977986 |  | C | Business | Active | Estimating/Design | 2023-04-07 | Forecast | 905 | Preliminary | 0 | EAC | 0 | n/a |  | 905 | 13 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Riverside | Palm Desert | 2022-46 | TD2011796/TD2017792 | Chia Drive -- Haystack Road to Loma Vista Lane | A | Government Agency | Hold | Estimating/Design | 2025-12-26 | Forecast | 650 | Preliminary | 500000 | EAC | 700 | n/a | TBD | 650 | 0 | 39633.76 | 39633.76 |  | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Rural | 0 | n/a | n/a
| Government Agency | n/a | Riverside | Palm Desert | n/a | TD1839347 | DESERT LILY DR & BURSERA WAY PALM DESERT CA 92260 | A | Government Agency | Cancelled |  | n/a |  | Unknown |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown |  | n/a | No | Unknown | Unknown | Rural | Unknown | n/a | n/a
| CITY OF PALM DESERT | n/a | Riverside | Palm Desert | n/a | TD1248017 | ALESSANDRO ALLEY E/O MONTEREY TO LAS PAL PALM DESERT CA 92260 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 11400 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | -199.5 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| PALM DESERT, CITY OF | n/a | Riverside | Palm Desert | n/a | TD1844149/TD922685/TD922765 | DESERT LILY DR & BURSERA WAY PALM DESERT CA 92260 | B | Government Agency | Active | Estimating/Design | 2026-06-16 | Forecast | 12677 | Design | 2893762 | EAC | 228.2687 | n/a | TBD | 12677 | 141 | 151633.52 | 15026.46 | Unknown | n/a | No | No | No | Rural | 47 | n/a | n/a
|  | n/a | Riverside | Palm Desert | n/a | TD2015171/ TD2015183 |  | C | Individual | Active | Estimating/Design | 2023-09-19 | Forecast | 69 | Design | 10098.77 | EAC | 146.359 | n/a |  | 69 | 0 | 375.69 | 375.69 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Palm Desert | n/a | TD1551353/TD1551524 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Rural | Unknown | n/a | n/a
| Government Agency | n/a | Riverside | Palm Springs | 21526 | TD282024/TD277131/ TD2075170/ 2075146 | Ramon Rd/ Cerritos Rd/ El Cielo Rd | A | Government Agency | Hold | Estimating/Design | 2025-06-14 | Forecast | 4279 | Preliminary | 2000000 | EAC | 475 | n/a | TBD | 4279 | 10 | 144357.46 | 1136.57 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1761438/TD1761455 |  | B | Contractor | Active | Estimating/Design | 2021-10-07 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1842762/TD1844603 |  | C | Individual | Active | Estimating/Design | 2023-07-13 | Forecast | 1922 | Design | 142952 | EAC | 74.3767 | n/a | TBD | 1922 | 27 | 50357 | 46613.44 | Unknown | n/a | No | No | No | Rural | 5 | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1381544/TD1381549 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1867309/TD1867311 |  | C | Contractor | Active | Closed | 2022-07-25 | Actual | 487 | Design | 259459 | Actual | 532.77 | n/a | 510 | 487 | 0 | 259459 | 258368 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1629316/TD1629322 |  | C | Contractor | Active | Closed | 2022-06-06 | Actual | 954 | Design | 747825.4 | Actual | 783.8841 | n/a | 1586 | 954 | 0 | 747825.4 | 740184 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Palm Springs | n/a | TD1628832/TD1628834/TD1825299 |  | C | Business | Active | Closing | 2022-06-07 | Actual | 714 | Design | 535420 | Actual | 749.888 | n/a | 553 | 714 | 0 | 535420 | 14199.88 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1069474/TD1069475/TD1132060 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Palmdale | n/a | TD1776642/TD1776644 | 6851 E AVENUE T PALMDALE CA 93550 | B |  | Active | Estimating/Design | 2024-12-30 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Palmdale | n/a | TD1550289 | AVENUE N & HWY 14 PALMDALE CA 93550 | B |  | Active | Estimating/Design | 2023-10-24 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 406.23 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1875718/TD1875719/TD1986350/TD2082081 |  | B | Contractor | Active | Estimating/Design | 2024-02-02 | Forecast | 13315 | Design | 0 | EAC | TBD | n/a | TBD | 13315 | 1 | 9216.99 | 7581.52 | Unknown | n/a | No | No | No | Urban Cluster | 118 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1875698/TD1875699 |  | B | Contractor | Active | Estimating/Design | 2022-07-13 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 7607.01 | 4912.23 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1600084 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1893037/TD1893040 |  | C | Contractor | Active | Construction | 2022-11-30 | Forecast | 1091 | Design | 98849 | EAC | 90.604 | n/a | TBD | 1091 | 1 | 116242.41 | 115897.49 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Palmdale | n/a | TD1311009/TD1311013 | 71222; 41155 10TH ST. WEST PALMDALE CA 93551 | C |  | Active | Estimating/Design | 2020-12-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1329999/TD139722 |  | C | Business | Active | Closed | 2021-01-09 | Actual | 683 | Design | 184895.04 | Actual | 270.7102 | n/a | 312 | 683 | 1 | 184895.04 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1728032/TD1728035 |  | C | Contractor | Active | Estimating/Design | 2023-05-15 | Forecast | 2100 | Design | 91614 | EAC | 43.6257 | n/a | TBD | 2100 | 9 | 4086.97 | 1659.16 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Los Angeles | Palmdale | n/a | TD1770907/TD1770909 |  | C | Contractor | Active | Construction | 2022-06-20 | Forecast | 1126 | Design | 214508 | EAC | 190.5044 | n/a | TBD | 1126 | 2 | 153291.35 | 147539.82 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Palos Verdes Estates | n/a | TD1469892/ TD1523388 |  | C | Individual | Active | Estimating/Design | 2023-01-11 | Forecast | 486 | Design | 51662.69 | EAC | 106.3018 | n/a |  | 486 | 8 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| PARAMOUNT, CITY OF | n/a | Los Angeles | Paramont | n/a | TD1117380/TD1123373 | 16400 COLARADO AVE PARAMOUNT CA 90723 | B | Government Agency | Active | Estimating/Design | 2022-12-31 | Forecast | 71 | Design | 0 | EAC | 0 | n/a | TBD | 71 | - | 116099.78 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
| PARAMOUNT, CITY OF | n/a | Los Angeles | Paramont | n/a | TD1123301/TD1242156 | 16400 COLORADO AVE PARAMOUNT CA 90723 | B | Government Agency | Active | Estimating/Design | 2022-12-31 | Forecast | 6042 | Design | 211748 | EAC | 35.046 | n/a | TBD | 6042 | 60 | 83744.08 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 39 | n/a | n/a
| PARAMOUNT, CITY OF | n/a | Los Angeles | Paramont | n/a | TD1241457/TD1241458/TD1242163 | 16400 COLORADO AVE PARAMOUNT CA 90723 | B | Government Agency | Active | Estimating/Design | 2022-12-31 | Forecast | 1 | Design | 111150 | EAC | 111150 | n/a | TBD | 1 | - | 84254.54 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
| PARAMOUNT | n/a | Los Angeles | Paramont | n/a | TD1117434/TD1242158/TD1305239/TD1305251 | 16400 COLORADO AVE PARAMOUNT CA 90723 | B | Government Agency | Active | Estimating/Design | 2022-12-31 | Forecast | 5797 | Design | 1850673 | EAC | 319.2467 | n/a | TBD | 5797 | 60 | 48342.06 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 25 | n/a | n/a
| Government Agency | n/a | Riverside | Perris | 3365 | n/a | Nuevo/Perris Blvd to Redlands Blvd, Ph 2 | A | Government Agency | Hold | Planning | TBD |  | 2700 | Preliminary | 675000 | EAC | 250 | n/a | TBD | 2700 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1958764/TD1958766 |  | B | Individual | Active | Estimating/Design | 2023-06-21 | Forecast | 824 | Design | 365008.56 | EAC | 442.9716 | n/a |  | 824 | 0 | 540.54 | 540.54 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1943704/TD1943705 | 131 W PERRY ST PERRIS CA 92571 | B |  | Active | Closed | 2022-08-30 | Actual | 1429 | Design | 255694.75 | Actual | TBD | n/a | TBD | 1429 | - | 255694.75 | 255694.75 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1935418/TD1935419 | 23111 PERRY ST PERRIS CA 92570 | B |  | Active | Estimating/Design | 2022-12-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 6283.23 | 6283.23 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1810375/TD1810376 |  | B | Contractor | Active | Closed | 2022-12-29 | Actual | 649 | Design | 291710.61 | Actual | 449.4771 | n/a | 676 | 649 | 0 | 291710.61 | 61799.13 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1560626/TD1560629 |  | B | Contractor | Active | Closed | 2020-07-01 | Actual | 1388 | Design | 240382.3 | Actual | 173.1861 | n/a | 1263 | 1388 | - | 240382.3 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1951045/TD1951047 | NANCE ST AND PATTERSON AVE PERRIS CA 92571 | B |  | Active | Estimating/Design | 2023-07-13 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 5003.02 | 5003.02 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1837327/TD1837330 | RIDER ST AND REDLANDS PERRIS CA 92571 | B |  | Active | Closed | 2022-12-01 | Actual | 0 |  | -0.02 | Actual | TBD | n/a | TBD | 0 | - | -0.02 | -12138.79 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1799397/TD1799399 |  | B | Business | Active | Estimating/Design | 2023-02-24 | Forecast | 5430 | Design | 835607 | EAC | 153.8871 | n/a | TBD | 5430 | - | 13159.58 | 3695.67 | Unknown | n/a | Yes | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1334311/TD1334313 |  | B | Business | Active | Closed | 2021-07-19 | Actual | 2065 | Design | 1121063.56 | Actual | 542.8879 | n/a | 1075 | 2065 | 0 | 1121063.56 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1849085/TD1849089 |  | B | Contractor | Active | Estimating/Design | 2022-11-28 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1821559/TD1821561 |  | B | Contractor | Active | Estimating/Design | 2023-03-01 | Forecast | 864 | Design | 245059.84 | EAC | 283.6341 | n/a | TBD | 864 | - | 6084.48 | 846.75 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1957277/TD1957278 |  | B | Contractor | Active | Estimating/Design | 2023-07-19 | Forecast | 1129 | Design | 178394.89 | EAC | TBD | n/a | TBD | 1129 | - | 1329.76 | 1329.76 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1448218/TD1448221 |  | B | Business | Active | Estimating/Design | 2023-11-30 | Forecast | 844 | Design | 361845 | EAC | 428.7263 | n/a | TBD | 844 | 2 | 6994.59 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1467637/TD1467639 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1328814/TD1387282 |  | C | Contractor | Active | Closed | 2021-05-07 | Actual | 1014 | Design | 203043.15 | Actual | 200.2398 | n/a | 707 | 1014 | 1 | 203043.15 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1430594 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1979997/TD1979998 | 69 BUSINESS PARK DR PERRIS CA 92571 | B |  | Active | Estimating/Design | 2022-12-30 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | 0 | 8305.38 | 8305.38 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD2004607/TD2004611 |  | B | Business | Active | Estimating/Design | 2023-12-29 | Forecast | 1003 | Design | 293715.11 | EAC | TBD | n/a |  | 1003 | 1 | 6293.43 | 6293.43 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD2059359/TD2059360/TD2059456 | HWY 74 AND DOCKERY LN PERRIS CA 92570 | B |  | Active | Estimating/Design | 2023-12-28 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | 0 | 180.16 | 180.16 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD2084379/TD2084381 |  | B | Contractor | Active | Estimating/Design | 2024-11-13 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD2078941/TD2078944 | WADE ST AND NANCE ST PERRIS CA 92571 | B |  | Active | Estimating/Design | 2023-12-29 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD2001125/TD201126 |  | B | Business | Active | Estimating/Design | 2023-06-29 | Forecast | 821 | Design | 253142.46 | EAC | TBD | n/a |  | 821 | 0 | 4471.43 | 4471.73 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1810347/TD1810348 | 11111 PLACENTIA AVE PERRIS CA 92570 | C |  | Active | Estimating/Design | 2023-12-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1888539/TD1888545 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1464930/TD146931 |  | C | Contractor | Active | Closed | 2020-07-23 | Actual | 269 | Design | 213582.53 | Actual | 793.9871 | n/a | 0 | 269 | 1 | 213582.53 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD2025592/ TD2025619 |  | C | Individual | Active | Estimating/Design | 2023-12-28 | Forecast | 439 | Design | 117478.62 | EAC | 267.6051 | n/a |  | 439 | 0 | 4181.09 | 4181.09 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1495609/TD1495610 |  | C | Contractor | Active | Closed | 2020-09-08 | Actual | 374 | Design | 578008.52 | Actual | 374 | n/a | 0 | 374 | 0 | 578008.52 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD1979982/ TD1979985 | 69 BUSINESS PARK DR PERRIS CA 92571 | C |  | Active | Estimating/Design | 2022-12-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 8255.64 | 8255.64 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1796361/TD1796362/TD1857131 |  | C | Contractor | Active | Estimating/Design | 2023-03-24 | Forecast | 2293 | Design | 560278.61 | EAC | 244.343 | n/a | TBD | 2293 | 0 | 9652.65 | 5759.85 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1761718/TD1893484 |  | C | Individual | Active | Construction | 2022-04-06 | Forecast | 449 | Design | 74082.5 | EAC | 164.9944 | n/a | TBD | 449 | 4 | 53081.19 | 53081.19 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1446617/TD1446618 |  | C | Contractor | Active | Estimating/Design | 2023-04-28 | Actual | 3914 | Design | 1472562 | EAC | 376.2294 | n/a | TBD | 3914 | 36 | 7672 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
| UNKNOWN | n/a | Riverside | Perris | n/a | TD2013401/ TD2013403 | PATTERSON AVE AND NANCE ST PERRIS CA 92571 | C |  | Active | Estimating/Design | 2023-03-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 5481.94 | 5481.94 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1748903/TD748904 |  | C | Business | Active | Estimating/Design | 2024-12-30 | Forecast | 684 | Design | 282553.54 | EAC | 413.09 | n/a | TBD | 684 | 4 | 3954.13 | 47 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1593947/TD1593948 |  | C | Contractor | Active | Closed | 2021-03-22 | Actual | 811 | Design | 296536 | Actual | 365.6424 | n/a | 801 | 811 | 2 | 296536 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1476076/TD1476077 |  | C | Contractor | Active | Closed | 2020-05-21 | Actual | 935 | Design | 88949.13 | Actual | 95.1328 | n/a | 615 | 935 | 0 | 88949.13 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1857741/TD1857742/TD1981424 |  | C | Contractor | Active | Estimating/Design | 2023-07-24 | Forecast | 4580 | Design | 1027076 | EAC | 224.2524 | n/a | TBD | 4580 | 7 | 6240 | 4828.32 | Unknown | n/a | Yes | No | No | Urban Cluster | 21 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1351746/TD1351750 |  | C | Business | Active | Closed | 2021-06-13 | Actual | 7491 | Design | 1620100 | Actual | 216.2729 | n/a | 5102 | 7491 | 21 | 1620100 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 23 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1972887/ TD1972891 |  | C | Business | Active | Estimating/Design | 2023-06-26 | Forecast | 568 | Design | 186319 | EAC | 328.0264 | n/a |  | 568 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1919420/TD1919421 |  | C | Contractor | Active | Estimating/Design | 2022-12-19 | Forecast | 568 | Design | 0 | EAC | 0 | n/a | TBD | 568 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD1810746/TD1810748 |  | C | Contractor | Active | Estimating/Design | 2023-08-09 | Forecast | 2571 | Design | 665956 | EAC | 259.0261 | n/a | TBD | 2571 | 0 | 12732 | 2230.04 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Perris | n/a | TD2081861/ TD2081862 |  | C | Business | Active | Estimating/Design | 2024-06-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Pico Rivera | n/a | TD1213840/TD1213843 |  | B | Contractor | Active | Construction | 2020-12-30 | Forecast | 2622 | Design | 2216713 | EAC | 845.4283 | n/a | TBD | 2622 | 8 | 3891981.1 | 9493.09 | Unknown | n/a | Yes | No | No | Urban Cluster | 12 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Pico Rivera | n/a | TD1135254 | 4700 DURFEE PICO RIVERA CA 90660 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Placentia | R-2018-04 | TD1361185/TD1361184/801851933 | Crowther 600' East of Melrose St | A | Government Agency | Active | Closed | 2021-01-28 | Actual | 1647 | Design | 1165443.38 | Actual | 627 | n/a | 1192 | 1647 | 9 | 1165443.38 | 2550.02 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 7 | n/a | n/a
| CITY OF PLACENTIA | n/a | Orange | Placentia | n/a | TD1499867/ TD1499868 | 202 W SANTA FE AVE PLACENTIA CA 92870 | C | Government Agency | Cancelled |  | n/a |  | Unknown |  | Unknown |  | Unknown | n/a |  | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Placentia | n/a | TD1993107/TD1993097 |  | C | Business | Active | Estimating/Design | 2023-05-18 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
|  | n/a | Orange | Placentia | n/a | TD2048890/ TD2048833 |  | C | Business | Active | Estimating/Design | 2023-08-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Placentia | n/a | TD1578134/TD1578141 |  | C | Contractor | Active | Construction | 2023-03-31 | Forecast | 1320 | Design | 320008 | EAC | 242.4303 | n/a | TBD | 1320 | 18 | 435543 | 411663 | Unknown | n/a | No | No | No | Rural | 7 | n/a | n/a
|  | n/a | Orange | Placentia | n/a | TD1760962/TD1760966 |  | C | Contractor | Active | Estimating/Design | 2023-04-28 | Forecast | 386 | Design | 125123.24 | EAC | 324.1535 | n/a | TBD | 386 | 2 | 1306.78 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Los Angeles | Pomona | n/a | TD2015964/ TD1977537 |  | C | Business | Active | Estimating/Design | 2024-01-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | Tulare | Porterville | 43-2008 | n/a | Division St/Putnam Ave So.-Olive Ave | A | Government Agency | Hold | Planning | TBD |  | 1500 | Preliminary | 0 |  | Unknown | n/a | TBD | 1500 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Tulare | Porterville | 88-2022 | TD2039445/TD2039444 | Morton Ave, Main St. to Roach | A | Government Agency | Hold | Estimating/Design | 2025-06-06 | Forecast | 1933 | Preliminary | 1600000 | EAC | 750 | n/a | TBD | 1933 | 0 | 36144.45 | 36144.45 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Tulare | Porterville | n/a | TD2028997/TD2028998 |  | B | Business | Active | Estimating/Design | 2023-08-23 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1887672/TD1887674/TD1962116 |  | B | Individual | Active | Estimating/Design | 2022-08-26 | Forecast | 968 | Design | 194408 | EAC | 200.8347 | n/a | TBD | 968 | 6 | 1552.3 | 1552.3 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD794346 |  | B | Contractor | Cancelled |  | n/a |  | 1939 | Design | 91848.16 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | -1322.1 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| CITY OF RANCHO CUCAMONGA | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1084035/TD1084036 | ARROW ROUTE - BEAR GULCH TO ARCHIBALD AV RANCHO CUCAMONGA CA 91730 | B | Government Agency | Active | Closed | 2020-07-30 | Actual | 2237 | Design | 783411.86 | Actual | 350.2065 | n/a | 1559 | 2237 | 3 | 783411.86 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1878812/TD1878974 |  | B | Contractor | Active | Estimating/Design | 2023-12-21 | Forecast | 1625 | Design | 360061.6 | EAC | TBD | n/a | TBD | 1625 | 3 | 17088.29 | 15473.42 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| Government Agency | n/a | San Bernardino | Rancho Cucamonga | 11-170 | TD1053528/TD1053526 | Arrow Route/ Bear Gulch to Archibald | A | Government Agency | Active | Closed | 2020-07-01 | Actual | 3993 | Design | 1940523.8 | Actual | 486 | n/a | 2317 | 3993 | 4 | 1940523.8 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 20 | n/a | n/a
| Government Agency | n/a | San Bernardino | Rancho Cucamonga | 11-158 | TD1056463/TD1056454 | Baseline Road/ Carnelian to Vineyard | A | Government Agency | Active | Closing | 2021-11-16 | Actual | 1263 | Design | 1699693.9 | Actual | 1299 | n/a | 893 | 1263 | 4 | 1699693.9 | 63024 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1524819/TD1524820 |  | C | Contractor | Active | Construction | 2023-03-30 | Forecast | 769 | Design | 274648 | EAC | 357.1495 | n/a | TBD | 769 | 0 | 454383.23 | 335379.31 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1914594/TD1914595 |  | C | Contractor | Active | Closed | 2022-08-08 | Actual | 140 | Design | 95576 | Actual | 682.6857 | n/a | 144 | 140 | 0 | 95576 | 90723.17 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1626677/TD1626692 |  | C | Contractor | Active | Closed | 2021-07-27 | Actual | 0 | Design | 171123.09 | Actual | 0 | n/a | 460 | 0 | 9 | 171123.09 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1924310/TD1924311 |  | C | Business | Active | Closed | 2022-08-29 | Actual | 969 | Design | 163862 | Actual | 169.1042 | n/a | 932 | 969 | 4 | 163862 | 161363 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1450567/TD1450648 |  | C | Contractor | Active | Estimating/Design | TBD | Forecast | n/a |  | 0 |  | TBD | n/a | TBD | n/a | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1561688/TD1561689 |  | C | Contractor | Active | Closed | 2022-03-23 | Actual | 563 | Design | 245999 | Actual | 436.9432 | n/a | 340 | 563 | 0 | 245999 | 43262.54 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1559533/TD1559534 |  | C | Individual | Active | Estimating/Design | 2023-06-01 | Forecast | 802 | Design | 293317 | EAC | 365.7319 | n/a | TBD | 802 | 1 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1953079/TD1953080 |  | C | Business | Active | Estimating/Design | 2023-06-02 | Forecast | 438 | Design | 150443 | Actual | 343.4772 | n/a | TBD | 438 | 4 | 6938.83 | 6938.83 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1532986/TD1596756 |  | C | Contractor | Active | Closed | 2022-07-12 | Actual | 846 | Design | 152613.1 | Actual | 180.3937 | n/a | 700 | 846 | 15 | 152613.1 | 143938 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1726971/TD1726972 |  | C | Contractor | Active | Closed | 2022-02-24 | Actual | 506 | Design | 235961.06 | Actual | 466.3262 | n/a | 516 | 506 | 1 | 235961.06 | 223444 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1462232/TD1462233 |  | C | Business | Active | Closed | 2020-10-26 | Actual | 583 | Design | 44622.84 | Actual | 76.54 | n/a | 314 | 583 | 11 | 44622.84 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1026026 |  | C | Contractor | Active | Closed | 2020-07-02 | Actual | 53 | Design | 108274.69 | Actual | 2042.9187 | n/a | 527 | 53 | 1 | 108274.69 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1620710/TD1620717 |  | C | Contractor | Active | Closed | 2021-03-22 | Actual | 389 | Design | 19586.66 | Actual | 50.3513 | n/a | 337 | 389 | 4 | 19586.66 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Rancho Cucamonga | n/a | TD1848049/ TD1848029 |  | C | Business | Active | Estimating/Design | 2022-11-16 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Rancho Palos Verdes | 2017-05 | TD1297899/TD1297898 | Crenshaw Blvd/ Crest Rd to 3rd Pole s/o Valley View Rd | A | Government Agency | Active | Construction | 2023-02-26 | Forecast | 655 | Design | 550000 | EAC | 550 | n/a | TBD | 655 | 0 | 703870.91 | 620503.24 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 4 | n/a | n/a
| Government Agency | n/a | Los Angeles | Rancho Palos Verdes | 2017-05 | TD1292482/TD1292481 | Palos Verdes Dr. So. - La Rotonda Dr to East City Limits | A | Government Agency | Active | Closed | 2021-09-28 | Actual | 1183 | Design | 527092.98 | Actual | 448 | n/a | 1081 | 1183 | 3 | 527092.98 | -3279.09 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Rancho Palos Verdes | n/a | TD1745715/TD1746741/TD1746810 | 6001 PALOS VERDES DR S S RANCHO PALOS VERDES CA 90275 | C |  | Active | Estimating/Design | 2022-07-14 | Forecast | 1303 | Preliminary | 356999.99 | EAC | 273.9831 | n/a | TBD | 1303 | 3 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 25 | n/a | n/a
| Government Agency | n/a | San Bernardino | Redlands | 6749 | TD1521334/TD1521326 | Cypress Ave/ Lakeside to San Jacinto | A | Government Agency | Active | Estimating/Design | 2024-10-16 | Forecast | 3970 | Preliminary | 3000000 | EAC | 700 | n/a | TBD | 3970 | 4 | 134254.95 | 1105.35 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1755704/TD1755708 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | no | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1846041/TD1846045 |  | B | Contractor | Active | Construction | 2022-12-02 | Forecast | 1158 | Design | 193025 | EAC | 166.6883 | n/a | TBD | 1158 | - | 94149.15 | 93466.77 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1732828/TD1732839 |  | B | Contractor | Active | Construction | 2022-12-15 | Forecast | 3850 | Design | 1363362 | EAC | 354.12 | n/a | TBD | 3850 | 16 | 1583983.46 | 1569484.62 | Unknown | n/a | No | No | No | Urban Cluster | 18 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1334389/TD1334401 |  | B | Contractor | Active | Estimating/Design | 2024-02-15 | Forecast | 1769 | Design | 474196 | EAC | 268.0588 | n/a | TBD | 1769 | 0 | 124.54 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1738814/TD1738817 |  | B | Business | Active | Construction | 2022-06-14 | Forecast | 1307 | Design | 169393.45 | EAC | 129.6048 | n/a | TBD | 1307 | - | 19356.91 | 16104.61 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1839483/TD1850009 |  | C | Individual | Active | Closed | 2022-10-24 | Actual | 1128 | Design | 312358 | Actual | 276.9131 | n/a | 645 | 1128 | 7 | 312358 | 301369.33 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Redlands | n/a | TD1534645 | 10797 NEW JERSEY ST REDLANDS CA 92373 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1832181/TD1832460 |  | C | Contractor | Active | Estimating/Design | 2022-12-20 | Forecast | 1139 | Design | 209726 | EAC | 184.1317 | n/a | TBD | 1139 | 8 | 21087 | 17558.28 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1424487/TD1424496 |  | C | Contractor | Active | Closed | 2020-05-08 | Actual | 0 | Design | 553.41 | Actual | 0 | n/a | 0 | 0 | 0 | 553.41 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1932280/TD1932297 |  | C | Contractor | Active | Construction | 2022-12-16 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a | TBD | 0 | 0 | 1978.91 | 1827.96 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1915579/TD1915580 |  | C | Individual | Active | Estimating/Design | 2023-09-22 | Forecast | 605 | Design | 167059 | EAC | 276.1306 | n/a | TBD | 605 | 3 | 2330.88 | 2330.88 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1603053/TD1603058 |  | C | Contractor | Active | Closing | 2022-10-14 | Actual | 1519 | Design | 907386 | Actual | 597.3575 | n/a |  | 1519 | 10 | 907386 | 711583 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1469672/TD1469682 |  | C | Contractor | Active | Closed | 2020-02-04 | Actual | 1679 | Design | 324217 | Actual | 193.1013 | n/a | 635 | 1679 | 15 | 324217 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1342996 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Redlands | n/a | TD1702802/TD1702806 |  | C | Individual | Active | Construction | 2021-03-05 | Forecast | 1614 | Design | 465052.63 | Actual | 288.1367 | n/a | 1684 | 1614 | 0 | 465052.63 | 1855.59 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
| CITY OF TORRANCE | n/a | Los Angeles | Redondo Beach | n/a | TD1807075/TD1807076 | 449 PASEO DE LA PLAYA REDONDO BEACH CA 90277 | B | Government Agency | Active | Estimating/Design | 2025-01-31 | Forecast | TBD | Preliminary | 91500 | EAC | TBD | n/a | TBD | TBD | 22 | 69310.56 | 69310.56 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| Government Agency | n/a | Los Angeles | Redondo Beach | 7543 | TD856189/TD1241178/TD856188 | PCH/ Prospect East to City Boundary | A | Government Agency | Active | Estimating/Design | 2024-06-30 | Forecast | 1604 | Design | 1100000 | EAC | 600 | n/a | TBD | 1604 | 12 | 1124141.99 | 78665.01 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 12 | n/a | n/a
| Government Agency | n/a | Los Angeles | Redondo Beach | 7543 | TD1447952 | PCH/ Prospect East to City Boundary - Trans | A | Government Agency | Active | Estimating/Design | 2025-06-27 | Forecast | 900 | Preliminary | 2520613.24 | EAC | 2801 | n/a | TBD | 900 | 0 | 829 | 0 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Rialto | 6676 | TD989408/TD989405 | Riverside Ave/Easton Street to Walnut Ave | A | Government Agency | Hold | Estimating/Design | 2026-07-07 | Forecast | 3323 | Preliminary | 1400000 | EAC | 500 | n/a | TBD | 3323 | 44 | 76865.71 | 642.46 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 20 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1511099/TD1511102 |  | B | Contractor | Active | Closed | 2020-10-29 | Actual | 861 | Design | 220278.91 | Actual | 255.8408 | n/a | 707 | 861 | - | 220278.91 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2046312/TD2046313 | 2180 S WILLOW AVE RIALTO CA 92376 | B |  | Active | Estimating/Design | 2023-12-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2087728/TD2087729 | 305 S. CEDAR AVE RIALTO CA 92376 | B |  | Active | Estimating/Design | 2023-08-31 | Forecast | 1009 | Design | 363976.79 | EAC | TBD | n/a |  | TBD | 1 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 3 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2074829/TD2074839 | 436 W RIALTO AVE RIALTO CA 92376 | B |  | Active | Estimating/Design | 2023-12-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2035069/TD2035081 | 520 FOOTHILL BLVD RIALTO CA 92376 | B |  | Active | Estimating/Design | 2023-09-08 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2015704/TD2015701 | W. DURST DR & CEDAR AVE RIALTO CA 92376 | B |  | Active | Estimating/Design | 2024-01-27 | Forecast | 752 | Design | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1670807/TD1670810 |  | C | Contractor | Active | Closed | 2021-12-08 | Actual | 338 | Design | 150499 | Actual | 445.2633 | n/a | 376 | 338 | 1 | 150499 | 2349.22 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1353953/TD1353955 |  | C | Contractor | Active | Closed | 2020-03-30 | Actual | 364 | Design | 42029.62 | Actual | 0 | n/a | 475 | 364 | 0 | 42029.62 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1712104 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1845817 |  | C | Contractor | Active | Estimating/Design | 2022-03-03 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a |  | No | No |  | 0 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1831867/TD1832235 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1626206/TD1626211 |  | C | Contractor | Active | Closed | 2021-06-07 | Actual | 2171 | Design | 355865.72 | Actual | 163.9179 | n/a | 2185 | 2171 | 8 | 355865.72 | -43.28 | Unknown | n/a | No | No | No | Urban Cluster | 12 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1466362 |  | C | Contractor | Active | Closed | 2020-01-15 | Actual | 2687 | Design | 413115.55 | Actual | 153.746 | n/a | 2271 | 2687 | 0 | 413115.55 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1579347/TD1579348 |  | C | Contractor | Active | Closed | 2021-02-24 | Actual | 1384 | Design | 277383 | Actual | 200.4212 | n/a | 873 | 1384 | 17 | 277383 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1606051/TD1607957 |  | C | Contractor | Active | Closed | 2021-03-11 | Actual | 353 | Design | 147410.93 | Actual | 417.5947 | n/a | 0 | 353 | 1 | 147410.93 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1809657/TD1809658 |  | C | Contractor | Active | Construction | 2023-04-07 | Forecast | 1216 | Design | 280750 | EAC | 230.8799 | n/a | TBD | 1216 | 3 | 26799.22 | 20872 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Rialto | n/a | TD2044858 | 350 W VALLEY BLVD RIALTO CA 92376 | C |  | Active | Estimating/Design | 2024-03-14 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Rialto | n/a | TD1854224/TD1857811/TD1876500 |  | C | Contractor | Active | Estimating/Design | 2023-08-31 | Forecast | 300 | Design | 118179 | EAC | 393.93 | n/a | TBD | 300 | 0 | 4744.05 | 3314.95 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Riverside | Riverside | n/a | TD1141765/TD1141768 |  | B | Contractor | Active | Closed | 2020-12-15 | Actual | 1783 | Design | 257061.65 | Actual | 144.1737 | n/a | 2036 | 1783 | - | 257061.65 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Riverside | Riverside | n/a | TD1982327/ TD1982337/ TD2058633 |  | C | Business | Active | Estimating/Design | 2024-01-11 | Forecast | 1990 | Design | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
| Government Agency | n/a | Los Angeles | Rolling Hills | 1276 | TD1869862/TD1869860 | Crest Road - 87 Crest Rd to East City Limits | A | Government Agency | Active | Estimating/Design | 2023-11-24 | Forecast | 2128 | Design | 1000000 | EAC | 700 | n/a | TBD | 2128 | 0 | 104881.47 | 37870.24 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Rural | 7 | n/a | n/a
| Government Agency | n/a | Los Angeles | Rolling Hills | 1316 | TD2084825/TD2084813 | Eastfield Drive - Hackamore Road to Pole 4866725E | A | Government Agency | Active | Estimating/Design | 2025-05-26 | Forecast | 1250 | Preliminary | 1000000 | EAC | 750 | n/a | TBD | 1250 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Rural | 0 | n/a | n/a
| ROLLING HILLS, CITY OF | n/a | Los Angeles | Rolling Hills | n/a | TD2010145/TD2085195/TD2010146 | 45 EASTFIELD DR ROLLING HILLS CA 90274 | B | Government Agency | Active | Estimating/Design | 2024-05-16 | Forecast | TBD | Preliminary | 16800 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Rural | 0 | n/a | n/a
| ROLLING HILLS, CITY OF | n/a | Los Angeles | Rolling Hills | n/a | TD1270924/TD1270926 | EASTFIELD DR AND CHUCKWAGON RD ROLLING HILLS CA 90274 | B | Government Agency | Active | Estimating/Design | 2023-07-20 | Forecast | 3640 | Design | 1607676 | EAC | 441.6692 | n/a | TBD | 3640 | 35 | 48404.36 | 0 | Unknown | n/a | No | No | No | Rural | 16 | n/a | n/a
| ROLLING HILLS, CITY OF | n/a | Los Angeles | Rolling Hills | n/a | TD1500155/TD1500171 | EL CONCHO RD/GEORGEFF RD ROLLING HILLS CA 00000 | B | Government Agency | Active | Estimating/Design | 2023-02-24 | Forecast | TBD | Preliminary | 61000 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Rural | - | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Rolling Hills | n/a | TD1824474 | 32 EASTFIELD DR ROLLING HILLS CA 90274 | C |  | Active | Estimating/Design | 2022-12-22 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
|  | n/a | Los Angeles | Rolling Hills | n/a | TD1127930 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Los Angeles | Rolling Hills | n/a | TD1417611/TD1417612 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Rural | Unknown | n/a | n/a
|  | n/a | Los Angeles | Rolling Hills | n/a | TD2070949/ TD2070950 |  | C | Individual | Active | Estimating/Design | 2023-06-16 | Forecast | 488 | Design | 57539.48 | EAC | 117.9088 | n/a |  | 488 | 8 | 1275.69 | 1275.69 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
| ROLLING HILLS, CITY OF | n/a | Los Angeles | Rolling Hills | n/a | TD2019774/ TD1993916 | 92 CREST RD E ROLLING HILLS CA 90274 | C | Government Agency | Active | Estimating/Design | 2024-01-19 | Forecast | 545 | Design | 237639.59 | EAC | 436.0359 | n/a |  | 545 | 8 | 1059.21 | 1059.21 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
|  | n/a | Los Angeles | Rolling Hills Estates | n/a | TD1886931/ TD2033095 |  | C | Individual | Active | Estimating/Design | 2023-12-13 | Forecast | TBD | Preliminary | 1000 | EAC | TBD | n/a | TBD | TBD | 0 | 237.61 | 237.61 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Rolling Hills Estates | n/a | TD1740313 | 54 SILVER SADDLE LN ROLLING HILLS ESTATES CA 90274 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | Rosemead | 2011-20 | TD1147311/TD1147308 | Walnut Grove Ave/ Marshall Ave to Valley Blvd | A | Government Agency | Active | Closed | 2021-11-30 | Actual | 5333 | Design | 2848291.27 | Actual | 567 | n/a | 1955 | 5333 | 39 | 2848291.27 | -175133.63 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 22 | n/a | n/a
| Government Agency | n/a | San Bernardino | San Bernardino | 2019-61 | TD1595027/TD1567224 | 40th Street/ Electric Ave to Johnson Street | A | Government Agency | Active | Estimating/Design | 2024-11-30 | Forecast | 3839 | Preliminary | 2600000 | EAC | 800 | n/a | TBD | 3839 | 38 | 133156.76 | 15061.96 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 12 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1802020/TD1802036 |  | B | Contractor | Active | Estimating/Design | 2023-08-18 | Forecast | 1338 | Design | 328545.97 | EAC | TBD | n/a | TBD | 1338 | - | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1845965/TD1846015 |  | B | Contractor | Active | Estimating/Design | 2023-05-18 | Forecast | 544 | Design | 405177 | EAC | 744.8107 | n/a | TBD | 544 | - | 412.78 | 412.78 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1721314/TD1721323 |  | B | Contractor | Active | Closing | 2021-09-08 | Actual | 1729 | Design | 605252.54 | Actual | 350.0593 | n/a | 1353 | 1729 | 1 | 605252.54 | 0.02 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1507145/TD1507146 |  | B | Contractor | Active | Closed | 2020-09-08 | Actual | 1936 | Design | 445315.67 | Actual | 230.0184 | n/a | 1614 | 1936 | 1 | 445315.67 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 13 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1856436/TD1856437/TD1887155 |  | C | Contractor | Active | Closed | 2022-05-09 | Actual | 351 | Design | 241465 | Actual | 687.9345 | n/a | 308 | 351 | 0 | 241465 | 237373 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1487548/TD1487549 |  | C | Contractor | Active | Estimating/Design | 2023-09-30 | Forecast | 522 | Design | 92718 | EAC | 177.6207 | n/a | TBD | 522 | 3 | 13.13 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1772370/TD190137 |  | C | Individual | Active | Estimating/Design | 2023-12-07 | Forecast | 971 | Design | 251392 | EAC | 258.9001 | n/a | TBD | 971 | 2 | 193.31 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1326724 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1426082/TD1426086 |  | C | Contractor | Active | Closed | 2020-05-12 | Actual | 322 | Design | 83098.92 | Actual | 258.0712 | n/a | 124 | 322 | 0 | 83098.92 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1854903/TD1854915 |  | C | Contractor | Active | Estimating/Design | 2022-05-25 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 461.15 | 461.15 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1653074/TD1653076 |  | C | Contractor | Active | Closed | 2021-03-11 | Actual | 213 | Design | 102903.93 | Actual | 483.117 | n/a | 331 | 213 | 0 | 102903.93 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1912038/TD1912039 |  | C | Business | Active | Estimating/Design | 2023-04-20 | Forecast | 526 | Design | 166679 | EAC | 316.8802 | n/a | TBD | 526 | 3 | 1627.53 | 1627.53 | Unknown | n/a | No | No | No | Rural | 2 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1956456/TD1956457 |  | C | Business | Active | Estimating/Design | 2023-06-30 | Forecast | 1556 | Design | 584879 | EAC | 375.8862 | n/a | TBD | 1556 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1458025/TD1603727 |  | C | Contractor | Active | Closed | 2021-01-27 | Actual | 2809 | Design | 442441.16 | Actual | 157.5084 | n/a | 3486 | 2809 | 3 | 442441.16 | 0 | Unknown | n/a | No | No | No | Rural | 7 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1656061/TD1656062 |  | C | Business | Active | Closed | 2022-09-01 | Actual | 758 | Design | 168090.66 | Actual | 221.7555 | n/a | 645 | 758 | 0 | 168090.66 | 166610 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1500734/TD1500735 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | San Bernardino | San Bernardino | n/a | TD1488860/TD1488886 | 945 S WATERMAN AVE SAN BERNARDINO CA 92408 | C |  | Active | Estimating/Design | 2023-07-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 5801.9 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD2011170 |  | C | Business | Active | Estimating/Design | 2023-06-12 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD |  | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | San Bernardino | n/a | TD1649157/TD1649175 |  | C | Contractor | Active | Closed | 2021-08-17 | Actual | 2118 | Design | 452450 | Actual | 213.6213 | n/a | 1357 | 2118 | 9 | 452450 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Los Angeles | San Dimas | n/a | TD1641968/TD1642404 |  | B | Business | Cancelled |  | n/a |  | 7086 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | 68 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | San Dimas | n/a | TD1627915 |  | B | Individual | Cancelled |  | n/a |  | 617 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | 11 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | San Dimas | n/a | TD1768615/TD1880342 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | San Dimas | 2018-36 | TD1691085/TD1691084 | So. San Dimas Ave/ E. Commercial to E. Bonita Ave | A | Government Agency | Active | Closed | 2021-10-05 | Actual | 811 | Design | 1077522.73 | Actual | 1527 | n/a | 438 | 811 | 7 | 1077522.73 | -160567.53 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | San Dimas | n/a | TD1880039 |  | B | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | San Dimas | n/a | TD1020665/TD1020666 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| SAN GABRIEL, CITY OF | n/a | Los Angeles | San Gabriel | n/a | TD1392996/TD1932998 | 101 W VALLEY BLVD SAN GABRIEL CA 91776 | B | Government Agency | Active | Closing | 2022-04-20 | Actual | 1099 | Design | 651488.23 | Actual | 592.8009 | n/a | TBD | 1099 | 1 | 651488.23 | 639195.13 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | San Gabriel | n/a | TD1600677/TD1600680 |  | B | Contractor | Active | Estimating/Design | 2022-10-05 | Forecast | 868 | Design | 238817 | EAC | 275.1348 | n/a | TBD | 868 | 37 | 4635.62 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Los Angeles | San Gabriel | n/a | TD1778657/TD1778658 |  | C | Individual | Active | Estimating/Design | 2023-09-22 | Forecast | 250 | Design | 43556 | EAC | 174.224 | n/a | TBD | 250 | 9 | 3517.98 | 2819.3 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1839181/TD1839183 |  | B | Individual | Active | Estimating/Design | 2024-11-20 | Forecast | 1834 | Design | 781446 | EAC | 426.0883 | n/a | TBD | 1834 | 1 | 60.05 | 60.05 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1554470 |  | B | Contractor | Active | Closed | 2020-01-24 | Actual | 506 | Design | 222600.35 | Actual | 439.9216 | n/a | 0 | 506 | 0 | 222600.35 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1677084/TD1677086 |  | C | Business | Active | Estimating/Design | 2022-07-14 | Forecast | 776 | Design | 277713 | EAC | 357.8776 | n/a | TBD | 776 | 0 | 5917.14 | 5000.32 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1694218/TD1694219 |  | C | Business | Active | Estimating/Design | 2023-08-30 | Forecast | 396 | Design | 174236 | EAC | 439.9899 | n/a | TBD | 396 | 2 | 4769.08 | 1057.32 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1433225/TD1508394 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1536742/TD1536747 |  | C | Contractor | Active | Closed | 2020-09-23 | Actual | 339 | Design | 80054.31 | Actual | 236.1484 | n/a | 900 | 339 | 0 | 80054.31 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Riverside | San Jacinto | n/a | TD1876231/TD1876233 |  | C | Contractor | Active | Estimating/Design | 2023-03-16 | Forecast | 2029 | Design | 313561.66 | EAC | 154.54 | n/a | TBD | 2029 | 12 | 355.07 | 355.07 | Unknown | n/a | No | No | No | Urban Cluster | 14 | n/a | n/a
| Government Agency | n/a | Los Angeles | San Marino | R-04-32 | TD1073299/TD1073298 | Del Mar/ Robin to Lorain | A | Government Agency | Active | Construction | 2023-03-20 | Forecast | 918 | Design | 920000 | EAC | 650 | n/a | TBD | 918 | 7 | 1194469.45 | 757641 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 7 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 93-056 | n/a | Bristol/ 3rd St to Civic Center, Ph 2 | A | Government Agency | Hold | Planning | TBD |  | 2500 | Preliminary | 1185000 | EAC | 390 | n/a | TBD | 2500 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 93-056 | n/a | Bristol/ Civic Ctr-Washington, Ph 3 | A | Government Agency | Hold | Planning | TBD |  | 2200 | Preliminary | 1093000 | EAC | 390 | n/a | TBD | 2200 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 93-056 | n/a | Bristol/ St. Andrew to Warner | A | Government Agency | Hold | Planning | TBD |  | 3200 | Preliminary | 1800000 | EAC | 500 | n/a | TBD | 3200 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 93-056 | n/a | Warner to Alton, Ph 4 | A | Government Agency | Hold | Planning | TBD |  | 8050 | Preliminary | 10420000 | EAC | 1294 | n/a | TBD | 8050 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 2018-078 | TD1537026/TD1537019/802214406 | Warner/ Main Street to Standard - Dist | A | Government Agency | Active | Construction | 2023-10-14 | Forecast | 2932 | Preliminary | 2000000 | EAC | 650 | n/a | TBD | 2932 | 16 | 40776.95 | 23879.78 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 22 | n/a | n/a
| Government Agency | n/a | Orange | Santa Ana | 2018-078 | TD1512197 | Warner/ Main Street to Standard - Trans | A | Government Agency | Active | Estimating/Design | 2023-09-29 | Forecast | 2880 | Preliminary | 5100000 | EAC | 650 | n/a | TBD | 2880 | 0 | 1105616.61 | 909403.19 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Orange | Santa Ana | n/a | TD1667010 | 18032: 1008 E. 4TH ST. SANTA ANA CA 92701 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Orange | Santa Ana | n/a | TD1667015 | 18032: 1008 E. 4TH ST. SANTA ANA CA 92701 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Orange | Santa Ana | n/a | TD1632246 | 651 SUNFLOWER SANTA ANA CA 92707 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Orange | Santa Ana | n/a | TD1653161/TD1653162 | APN: 398-236-03; 609 N. SPURGEON ST. SANTA ANA CA 92701 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| SANTA ANA, CITY OF | n/a | Orange | Santa Ana | n/a | TD1066716/TD1169473 | BRISTOL ST FROM 3RD TO CIVIC CENTER DR SANTA ANA CA 92705 | B | Government Agency | Active | Estimating/Design | 2023-12-01 | Forecast | TBD | Preliminary | 13200 | EAC | TBD | n/a | TBD | TBD | 21 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 14 | n/a | n/a
| SANTA ANA, CITY OF | n/a | Orange | Santa Ana | n/a | TD1066711/TD1143243 | BRISTOL ST FROM WARNER TO ST ANDREW SANTA ANA CA 92705 | B | Government Agency | Active | Estimating/Design | 2023-08-19 | Forecast | TBD | Preliminary | 16200 | EAC | TBD | n/a | TBD | TBD | - | 2697.63 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| SANTA ANA, CITY OF | n/a | Orange | Santa Ana | n/a | TD1066719 | BRISTOL ST, CIVIC CENTER TO WASHINGTON SANTA ANA CA 92705 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 7200 | EAC | Unknown | n/a | Unknown | Unknown | 0 | -26630.13 | 0 | Unknown | n/a | Yes | no | No | Urban Cluster | Unknown | n/a | n/a
| CITY OF SANTA ANA | n/a | Orange | Santa Ana | n/a | TD1444304/TD1692606 | BRISTOL ST, CIVIC CENTER TO WASHINGTON SANTA ANA CA 92840 | B | Government Agency | Active | Estimating/Design | 2023-06-16 | Forecast | 2976 | Design | 1080575 | EAC | 363.0964 | n/a | TBD | 2976 | 0 | 214754.53 | 190108.1 | Unknown | n/a | Yes | No | No | Urban Cluster | 21 | n/a | n/a
| SANTA ANA, CITY OF | n/a | Orange | Santa Ana | n/a | TD2019904/TD2019905 | BRISTOL ST, CIVIC CENTER TO WASHINGTON SANTA ANA CA 92703 | B | Government Agency | Active | Estimating/Design | 2023-06-16 | Forecast | 2845 | Design | 1080203.28 | EAC | 379.6848 | n/a |  | 2845 | 15 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 21 | n/a | n/a
|  | n/a | Orange | Santa Ana | n/a | TD1760797/TD1760807 |  | C | Contractor | Cancelled |  | n/a |  | Unknown |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Orange | Santa Ana | n/a | TD1876697/TD1876699 |  | C | Contractor | Active | Estimating/Design | 2023-05-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 1649.18 | 1649.18 | Unknown | n/a |  | No | No |  | 0 | n/a | n/a
| UNKNOWN | n/a | Orange | Santa Ana | n/a | TD1654120/TD1654127 | APN: 398-236-03; 609 N. SPURGEON ST. SANTA ANA CA 92701 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Orange | Santa Ana | n/a | TD1661055/TD1661057 |  | C | Contractor | Active | Estimating/Design | 2023-04-28 | Forecast | 840 | Design | 84707 | EAC | 100.8417 | n/a | TBD | 840 | 2 | 6394 | 576.54 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Santa Ana | n/a | TD1817557/TD1817585 |  | C | Contractor | Active | Estimating/Design | 2023-05-31 | Forecast | 1166 | Design | 471473.09 | EAC | 404.3508 | n/a | TBD | 1166 | 38 | 355.59 | 355.59 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Orange | Santa Ana | n/a | TD2014559/ TD2014558 |  | C | Business | Active | Estimating/Design | 2024-10-25 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Santa Barbara | Santa Barbara | 21-085 | TD1942119/TD1942114 | Cliff Drive - Salida Del Sol to San Rafael Ave | A | Government Agency | Active | Estimating/Design | 2024-05-27 | Forecast | 3250 | Preliminary | 2250000 | EAC | 650 | n/a | TBD | 3250 | 0 | 237345.14 | 77350.06 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1438510/TD1438513 |  | B | Individual | Active | Closed | 2020-07-08 | Actual | 1095 | Design | 285234.16 | Actual | 260.4878 | n/a | 664 | 1095 | 4 | 285234.16 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1957874 |  | B | Individual | Cancelled |  | n/a |  | n/a |  | 2400 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1186519/TD1186520 |  | C | Contractor | Active | Closed | 2021-03-17 | Actual | 715 | Design | 101216.82 | Actual | 141.562 | n/a | 225 | 715 | 3 | 101216.82 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1383570/TD1383577 |  | C | Individual | Active | Estimating/Design | 2023-03-03 | Forecast | 172 | Design | 40117 | EAC | 233.2384 | n/a | TBD | 172 | 0 | 4296.87 | 3597.84 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1756380/TD1756381 |  | C | Individual | Active | Closed | 2021-10-11 | Actual | 575 | Design | 26691.71 | Actual | 46.4204 | n/a | 0 | 575 | 7 | 26691.71 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1750739/TD1750740 |  | C | Contractor | Active | Estimating/Design | 2025-11-24 | Forecast | 302 | Design | 96864 | EAC | 320.7417 | n/a | TBD | 302 | 7 | 842.92 | 842.92 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1892049/TD1892050 |  | C | Individual | Active | Estimating/Design | 2023-05-01 | Forecast | 410 | Design | 123596 | EAC | 301.4537 | n/a | TBD | 410 | 8 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1456653/TD1456654 |  | C | Individual | Active | Closed | 2020-08-18 | Actual | 242 | Design | 138268 | Actual | 571.3554 | n/a | 0 | 242 | 0 | 138268 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1274854 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1453004/TD1453005 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1110169/TD1165777 |  | C | Individual | Active | Closed | 2021-04-14 | Actual | 416 | Design | 41934.37 | Actual | 100.8038 | n/a | 206 | 416 | 3 | 41934.37 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1541794/TD1541795 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1833399/TD1833400 |  | C | Individual | Active | Estimating/Design | 2022-10-28 | Forecast | TBD | Preliminary | 600 | EAC | TBD | n/a | TBD | TBD | 0 | 321.74 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1493818/TD1493819 |  | C | Individual | Active | Closed | 2021-02-18 | Actual | 149 | Design | 12579 | Actual | 84.4228 | n/a | 0 | 149 | 7 | 12579 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1174942/TD1174945 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1938307/TD1938308/TD1941700 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
| SANTA BARBARA, COUNTY OF | n/a | Santa Barbara | Santa Barbara | n/a | TD1648593/TD1648594 | 4400 CATHEDRAL OAKS RD SANTA BARBARA CA 93110 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1912104/TD1912105/TD1918547/TD1918549 |  | C | Individual | Active | Estimating/Design | 2023-11-02 | Forecast | 110 | Design | 7199 | EAC | 65.4455 | n/a | TBD | 110 | 7 | 6767.53 | 6501.09 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1838458/TD1892999/TD1893000/TD1893082/TD1893087 |  | C | Individual | Active | Estimating/Design | 2023-08-23 | Forecast | 187 | Design | 38015.35 | EAC | 203.2906 | n/a | TBD | 187 | 7 | 2201.78 | 2201.78 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1811489 |  | C | Individual | Active | Estimating/Design | 2022-02-02 | Forecast | TBD | Preliminary | 1800 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1490880/TD1490881 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1537566 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1743229/TD1743258 |  | C | Individual | Active | Closed | 2021-07-21 | Actual | 318 | Design | 24888.51 | Actual | 78.2658 | n/a | 0 | 318 | 0 | 24888.51 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1611803/TD1611816 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1958068/ TD1983459 |  | C | Individual | Active | Estimating/Design | 2023-07-26 | Forecast | 721 | Preliminary | 12809 | EAC | 17.7656 | n/a | TBD | 721 | 3 | 480.73 | 480.73 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1408365/TD1408366 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1464659/TD1553081 |  | C | Individual | Active | Estimating/Design | 2024-06-11 | Forecast | 164 | Design | 61913 | EAC | 377.5183 | n/a | TBD | 164 | 0 | 49.75 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1694504/TD1694505 |  | C | Individual | Active | Closed | 2021-03-10 | Actual | 190 | Design | 29021.89 | Actual | 152.7468 | n/a | 35 | 190 | 5 | 29021.89 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1599162 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1598443 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Santa Barbara | n/a | TD1946907/TD1946909 |  | C | Individual | Active | Estimating/Design | 2023-07-12 | Forecast | 461 | Preliminary | 123133.57 | EAC | 267.101 | n/a | TBD | 461 | 3 | 687.95 | 687.95 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| SANTA BARBARA, COUNTY OF | n/a | Santa Barbara | Santa Barbara | n/a | TD1537347/TD1537349 | HWY 101 HOV WIDENING PROJ SUMMERLAND CA 93067 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Ventura | Santa Barbara | n/a | TD1990692/ TD1990664 |  | C | Individual | Active | Estimating/Design | 2024-02-01 | Forecast | 680 | Preliminary | 79456.49 | EAC | 116.8478 | n/a |  | 680 | 5 | 977.83 | 977.83 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Santa Barbara | n/a | TD2015459/ TD2015460 |  | C | Individual | Active | Estimating/Design | 2023-07-12 | Forecast | TBD | Preliminary | 600 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Santa Barbara | n/a | TD1992507/ TD1992550 |  | C | Individual | Active | Estimating/Design | 2023-08-30 | Forecast | TBD | Preliminary | 1800 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Santa Barbara | n/a | TD1984410/ TD1984411 |  | C | Individual | Active | Estimating/Design | 2023-07-28 | Forecast | 6 | Preliminary | 8056.39 | EAC | 1342.7317 | n/a |  | 6 | 5 | 2608.79 | 2608.79 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Santa Fe Springs | n/a | TD984471/ TD1984472 |  | C | Business | Active | Estimating/Design | 2024-01-18 | Forecast | 240 | Design | 38179.36 | EAC | 159.0807 | n/a |  | 240 | 21 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 1 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Santa Fe Springs | n/a | TD2068015/ TD2068014 | 12222 FLORENCE AVE SANTA FE SPRINGS CA 90670 | C |  | Active | Estimating/Design | 2023-12-26 | Forecast | TBD | Preliminary | 1000 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Santa Fe Springs | n/a | TD1752188/TD1752189 | 9883 GREENLEAF SANTA FE SPRINGS CA 90670 | C |  | Active | Estimating/Design | 2021-09-16 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Santa Fe Springs | n/a | TD1752272/TD1752273 |  | C | Business | Active | Estimating/Design | 2023-07-25 | Forecast | 905 | Preliminary | 813346 | EAC | 898.7249 | n/a | TBD | 905 | 23 | 8008.97 | 8008.97 | Unknown | n/a | Yes | No | No | Urban Cluster | 13 | n/a | n/a
|  | n/a | Los Angeles | Santa Monica | n/a | TD2088531/ TD2088530 |  | C | Business | Active | Estimating/Design | 2024-01-31 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Santa Monica | n/a | TD1145230/TD1145232 | 2300 WILSHIRE BLVD SANTA MONICA CA 90403 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Santa Paula | n/a | TD1965700/TD1965701/ TD1983039 |  | C | Individual | Active | Estimating/Design | 2023-06-26 | Forecast | TBD | Preliminary | 22551.89 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
|  | n/a | Ventura | Santa Paula | n/a | TD1913059/TD1952338 |  | C | Business | Active | Estimating/Design | 2023-06-19 | Forecast | 258 | Design | 25373 | EAC | 98.345 | n/a | TBD | 258 | 9 | 71.43 | 71.43 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Orange | Seal Beach | 6418 | n/a | Seal Beach Blvd/ PCH to Electric | A | Government Agency | Hold | Planning | TBD |  | 1960 | Preliminary | 1100000 | EAC | 500 | n/a | TBD | 1960 | 0 | 0 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Signal Hill | n/a | TD1913382/TD1913383 |  | C | Contractor | Active | Estimating/Design | 2022-12-30 | Forecast | 426 | Design | 64752 | EAC | 152 | n/a | TBD | 426 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
| Government Agency | n/a | Ventura | Simi Valley | 2012-46 | TD1941783/TD1941782 | Erringer Road - Alamo Street to 145' S/O CL Cochran Street | A | Government Agency | Active | Estimating/Design | 2025-01-04 | Forecast | 1308 | Preliminary | 1000000 | EAC | 700 | n/a | TBD | 1308 | 0 | 271314.22 | 62011.12 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1835290/TD1835291 |  | B | Individual | Cancelled |  | n/a |  | 757 | Design | Unknown |  | Unknown | n/a | Unknown | Unknown | 3 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Ventura | Simi Valley | n/a | TD1949113/TD1949114 | 300 W LOS ANGELES AVE SIMI VALLEY CA 93065 | B |  | Cancelled |  | 2024-12-27 | Forecast | n/a | Preliminary | 0 | EAC | TBD | n/a | TBD | n/a | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
| UNKNOWN | n/a | Ventura | Simi Valley | n/a | TD1647640/TD1647642 | NEC OF EASY STREET & MADERA ROAD (NORTH) SIMI VALLEY CA 93065 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1333170/TD1333171 |  | C | Contractor | Active | Closed | 2021-01-15 | Actual | 369 | Design | 192887.2 | Actual | 522.7295 | n/a | 1736 | 369 | 1 | 192887.2 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1848162/TD1848163 |  | C | Individual | Active | Estimating/Design | 2025-11-14 | Forecast | 697 | Design | 78962 | EAC | 113.2884 | n/a | TBD | 697 | 3 | 1868.45 | 1868.45 | Unknown | n/a | No | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1654463/TD1654464 |  | C | Contractor | Active | Construction | 2022-05-04 | Actual | 771 | Design | 146829.81 | Actual | 190.4407 | n/a |  | 771 | 1 | 146829.81 | 137584.23 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1400362/TD1400363 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | n/a | Unknown | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Simi Valley | n/a | TD1647762/TD1647763 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | South El Monte | 09 11 | TD1126221/TD1126222 | Santa Anita/ Merced/Fawcett to Tyler | A | Government Agency | Active | Closing | 2022-11-01 | Actual | 6700 | Design | 1828558.07 | Actual | 500 | n/a | TBD | 6700 | 12 | 1828558.07 | 671639.1 | No | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 10 | n/a | n/a
| Government Agency | n/a | Los Angeles | South Gate | 7209 | n/a | Long Beach Blvd/ Independence Ave to Willow Pl | A | Government Agency | Hold | Planning | TBD |  |  | Preliminary | 4900000 | EAC | Unknown | n/a | TBD | 0 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | South Gate | 7210 | n/a | Long Beach Blvd/ Willow Pl to Tweedy Blvd | A | Government Agency | Hold | Planning | TBD |  |  | Preliminary | 0 |  | Unknown | n/a | TBD | 0 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | South Gate | 7351 | n/a | Tweedy Blvd/ Atlantic to 800' e/o Atlantic | A | Government Agency | Hold | Planning | TBD |  |  | Preliminary | 0 |  | Unknown | n/a | TBD | 0 | 0 | 0 | 0 |  | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | South Pasadena | 7290 | TD1114139/TD1114142/TD1110240 | Park Ave/ Mission St. - Grevelia St | A | Government Agency | Active | Estimating/Design | 2024-10-18 | Forecast | 1482 | Design | 3100000 | EAC | 1750 | n/a | TBD | 1482 | 11 | 1168055.71 | 88521.42 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 9 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | South Pasadena | n/a | TD1834086/ TD1834087 | 1325 MONTEREY RD SOUTH PASADENA CA 91030 | C |  | Active | Estimating/Design | 2022-03-31 | Forecast | 223 | Design | 0 | EAC | TBD | n/a |  | 223 | 3 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 3 | n/a | n/a
|  | n/a | Los Angeles | South Pasadena | n/a | TD1725365/TD1725366 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Orange | Stanton | 2015-02 | TD1607244/TD1607260 | Beach Blvd/Garden Grove Blvd-Lampson Ave | A | Government Agency | Active | Estimating/Design | 2025-06-16 | Forecast | 3582 | Design | 2700000 | EAC | 500 | n/a | TBD | 3582 | 8 | 473162.2 | 6466.31 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 19 | n/a | n/a
|  | n/a | Orange | Stanton | n/a | TD1850371/TD1850372/TD1940929 |  | B | Contractor | Active | Estimating/Design | 2023-06-30 | Forecast | 976 | Design | 313354.72 | EAC | 321.0602 | n/a | TBD | 976 | - | 484.51 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Orange | Stanton | n/a | TD1408745/TD1408746/TD1744774 |  | C | Business | Active | Closed | 2021-09-08 | Actual | 575 | Design | 258230.28 | Actual | 449.0961 | n/a | 152 | 575 | 13 | 258230.28 | 24794.08 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Orange | Stanton | n/a | TD1978465/ TD1978458 |  | C | Business | Active | Estimating/Design | 2023-04-11 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Kern | Tehachapi | 08-22 | TD1998312/TD1998304 | Valley Blvd - Beech Street to Curry St- PH1 | A | Government Agency | Hold | Estimating/Design | 2024-12-31 | Forecast | 5128 | Preliminary | 3400000 | EAC | 650 | n/a | TBD | 0 | 55 | 52495.73 | 52495.73 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Kern | Tehachapi | n/a | TD1980510/ TD1980521 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Temecula | n/a | TD1311057/TD1311059 |  | B | Contractor | Active | Closed | 2023-01-12 | Actual | 1582 | Design | 454875.79 | Actual | 287.5321 | n/a | 933 | 1582 | 10 | 454875.79 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Temecula | n/a | TD1405340/TD1405343 |  | B | Contractor | Active | Closed | 2021-02-11 | Actual | - | Design | 177462.15 | Actual | Unknown | n/a | 1037 | - | 2 | 177462.15 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Temecula | n/a | TD2037452/TD2037451 |  | B | Business | Cancelled |  | n/a |  | Unknown |  | Unknown |  | Unknown | n/a |  | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Riverside | Temecula | n/a | TD2030651/TD2030650 | SOLANA WAY/MARGARITA RD TEMECULA CA 92590 | B |  | Active | Estimating/Design | 2023-06-30 | Forecast | 910 | Design | 269781.18 | EAC | 296.4628 | n/a |  | 910 | 4 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 4 | n/a | n/a
| UNKNOWN | n/a | Riverside | Temecula | n/a | TD2016984 | SOLANA WAY/MARGARITA RD TEMECULA CA 92590 | B |  | Cancelled |  | n/a |  | Unknown |  | Unknown |  | Unknown | n/a |  | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Temecula | n/a | TD1390301/TD1390305 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Temecula | n/a | TD2039994/ TD2039993 |  | C | Business | Active | Estimating/Design | 2023-09-23 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Thousand Oaks | n/a | TD2062966/TD2062971 |  | B | Business | Active | Estimating/Design | 2023-12-15 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| CITY OF THOUSAND OAKS | n/a | Ventura | Thousand Oaks | n/a | TD1227077/TD1227078 | 3532 HILLCREST DR THOUSAND OAKS CA 91362 | B | Government Agency | Active | Closed | 2021-07-27 | Actual | 1420 | Design | 248645.15 | Actual | 175.1022 | n/a | 1075 | 1420 | 16 | 248645.15 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Ventura | Thousand Oaks | n/a | TD1223383 |  | B | Business | Active | Closed | 2020-04-10 | Actual | 0 | Design | 7353.02 | Actual | TBD | n/a | 1746 | Unknown | 1 | 7353.02 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 13 | n/a | n/a
| CITY OF THOUSAND OAKS | n/a | Ventura | Thousand Oaks | n/a | TD1230622/TD1230623 | 5907; 1200 NEWBURY RD. THOUSAND OAKS CA 91362 | B | Government Agency | Active | Closed | 2020-01-10 | Actual | 829 | Design | 41522.42 | Actual | 50.0874 | n/a | 653 | 829 | 4 | 41522.42 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| CITY, OF THOUSAND OAKS | n/a | Ventura | Thousand Oaks | n/a | TD1328455/TD1328457 | 77 CONEJO SCHOOL RD THOUSAND OAKS CA 91360 | B | Government Agency | Active | Closed | 2020-04-16 | Actual | 2112 | Design | 259791.15 | Actual | 123.0072 | n/a | 965 | 2112 | 54 | 259791.15 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Ventura | Thousand Oaks | n/a | TD2031711/ TD2031712 |  | C | Business | Active | Estimating/Design | 2023-08-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Ventura | Thousand Oaks | 2021-64 | TD1941569/TD1941563 | E Janss Road - Moorpark Avenue to Windsor Drive | A | Government Agency | Active | Estimating/Design | 2024-05-15 | Forecast | 3683 | Design | 2000000 | EAC | 650 | n/a | TBD | 3683 | 35 | 112500.78 | 112500.78 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 19 | n/a | n/a
|  | n/a | Ventura | Thousand Oaks | n/a | TD1738201/TD1738202 |  | C | Individual | Active | Estimating/Design | 2024-07-18 | Forecast | 260 | Design | 39494 | EAC | 151.9 | n/a | TBD | 260 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Torrance | 2011-23 | TD538643/TD538653 | Hawthorne Blvd/ Del Amo to 186th St | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 138872.87 | -421266.92 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | Unknown | n/a | n/a
| TORRANCE, CITY OF | n/a | Los Angeles | Torrance | n/a | TD955858/TD962525 | 21209 PALOS VERDES BLVD TORRANCE CA 90503 | B | Government Agency | Active | Estimating/Design | 2023-08-24 | Forecast | 1815 | Design | 687474 | EAC | 378.7736 | n/a | TBD | 1815 | - | 9366.36 | 984.06 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
| TORRANCE, CITY OF | n/a | Los Angeles | Torrance | n/a | TD1691960/TD1691961 | 1740 PLAZA DEL AMO TORRANCE CA 90501 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown | Unknown | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Torrance | n/a | TD1617134/TD1617135 |  | C | Business | Active | Construction | 2023-03-24 | Forecast | 1564 | Design | 121160 | EAC | 77.468 | n/a | TBD | 1564 | 63 | 289567 | 251157.8 | Unknown | n/a | No | No | No | Rural | 8 | n/a | n/a
| Government Agency | n/a | Los Angeles | Torrance | 2011-23 | TD540122/TD540185/TD540121 | Crenshaw Blvd/ Carson St to Sepulveda | A | Government Agency | Active | Closed | 2021-07-15 | Actual | 5698 | Design | 2745028.73 | Actual | 481.7554 | n/a | 2568 | 5698 | 20 | 2745028.73 | -13.75 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 24 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Torrance | n/a | TD1621650/TD1621651 | 182ND ST AND CRENSHAW BLVD TORRANCE CA 90503 | C |  | Active | Estimating/Design | 2022-07-29 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
| TORRANCE, CITY OF | n/a | Los Angeles | Torrance | n/a | TD1487366 | 18798 HAWTHORNE BLVD TORRANCE CA 90504 | C | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Los Angeles | Torrance | n/a | TD1778385/TD1778393 |  | C | Business | Active | Closed | 2021-09-19 | Actual | 513 | Design | 64513.71 | Actual | 125.7577 | n/a | 345 | 513 | 3 | 64513.71 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1860922/TD1860924 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1637628/TD1637629 |  | B | Individual | Active | Estimating/Design | 2023-12-22 | Forecast | TBD | Preliminary | 7200 | EAC | TBD | n/a | TBD | TBD | - | 1982.55 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1888085/TD1888087 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Tulare | Tulare | n/a | TD1897581/TD1897585 | KENSINGTON 3; MOONEY & CARTMILL TULARE CA 93274 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1862544/TD1862545 |  | B | Contractor | Active | Estimating/Design | 2023-09-04 | Forecast | 3283 | Preliminary | 604674.54 | EAC | TBD | n/a | TBD | 3283 | 1 | 1740.37 | 1740.37 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1890893/TD1890895 |  | B | Contractor | Active | Estimating/Design | 2023-01-27 | Forecast | 1703 | Preliminary | 328244 | EAC | TBD | n/a | TBD | 1703 | - | 1475.33 | 1475.33 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1794416/TD1794419 |  | B | Contractor | Active | Estimating/Design | 2022-09-23 | Forecast | TBD | Preliminary | 11668 | EAC | TBD | n/a | TBD | TBD | - | 114.75 | 114.75 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD2002861/TD2002862 |  | B | Business | Active | Construction | 2023-02-08 | Forecast | 1703 | Design | 328891.44 | EAC | TBD | n/a |  | TBD | 0 | 450.35 | 450.35 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 4 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD2071379/TD2071386 |  | B | Business | Active | Estimating/Design | 2023-12-12 | Forecast | 0 | Design | 0 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD2051247/TD2051245 |  | B | Business | Active | Estimating/Design | 2023-12-01 | Forecast | 778 | Design | 0 | EAC | TBD | n/a |  | TBD | 17 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
| TULARE, CITY OF | n/a | Tulare | Tulare | n/a | TD1875833/TD1875834 | WEST ST/PLEASANT AVE TULARE CA 93274 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | 390153.5 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | -2.57 | -2.57 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1946470/TD1946474 |  | C | Contractor | Active | Estimating/Design | 2023-03-24 | Forecast | 1502 | Design | 329480.26 | EAC | 219.361 | n/a | TBD | 1502 | 3 | 761.58 | 761.58 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1816310/TD1816311 |  | C | Contractor | Active | Closed | 2022-01-10 | Actual | 1020 | Design | 418167.35 | Actual | 409.968 | n/a | 1056 | 1020 | 1 | 418167.35 | 41422.74 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1639066/TD1639067 |  | C | Contractor | Active | Estimating/Design | 2023-06-29 | Forecast | 2855 | Design | 357589 | EAC | 125.2501 | n/a | TBD | 2855 | 1 | 653.78 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1473082/TD1473083 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1784743/ TD1784745 |  | A | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1901677/ TD1970267/ TD1901679 |  | C | Business | Active | Estimating/Design | 2023-05-26 | Forecast | 2363 | Design | 512983 | EAC | 217.0897 | n/a |  | 2363 | 23 | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 10 | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1911880/ TD196334/ TD1911879 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Tulare | Tulare | n/a | TD1988612/ TD1988613 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | Orange | Tustin | 22-12 | TD1976679/TD1976676 | Redhill/ El Camino Real to 230' N/O San Juan St. | A | Government Agency | Active | Estimating/Design | 2025-07-19 | Forecast | 1425 | Preliminary | 1200000 | EAC | 750 | n/a | 0 | 1425 | 0 | 40832.94 | 40832.94 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Tustin | n/a | TD2016522/ TD2016518 |  | C | Business | Active | Estimating/Design | 2023-07-28 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a |  | TBD | 0 | 415.37 | 415.37 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Orange | Tustin | n/a | TD2031869/ TD2031868 |  | C | Business | Active | Estimating/Design | 2023-09-01 | Forecast | 0 | Preliminary | 0 | EAC | TBD | n/a |  | 0 | 3 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| CITY OF 29 PALMS | n/a | San Bernardino | Twentynine Palms | n/a | TD1512017/TD1512019 | TWENTYNINE PALMS HWY & TAMARISK AVE TWENTYNINE PALMS CA 92277 | B | Government Agency | Active | Closed | 2021-01-13 | Actual | 985 | Design | 387887.18 | Actual | 393.7941 | n/a | 746 | 985 | 13 | 387887.18 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| Government Agency | n/a | San Bernardino | Twentynine Palms | 15-01 | TD982911/TD982909 | HWY 62 - MESQUITE SPRINGS RD TO PINE AVE TWENTY NINE PALMS CA 92277 | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | -7643.74 | -7836.65 | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | San Bernardino | Twentynine Palms | 18 02 | TD1502969/TD1502971 | Project Phoenix - Tamarisk Ave to Cholla Ave | A | Government Agency | Active | Closed | 2021-01-13 | Actual | 2357 | Design | 1436315.92 | Actual | 608.8665 | n/a | 746 | 2357 | 35 | 1436315.92 | 0 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | San Bernardino | Twentynine Palms | n/a | TD2058549/ TD2058550 |  | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | 602 | Design | 91262.81 | EAC | 151.5994 | n/a |  | 602 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 3 | n/a | n/a
|  | n/a | Ventrua | Unincorporated Ventura (Lake Sherwood) | n/a | TD1844427/TD1844428 |  | C | Individual | Active | Estimating/Design | 2022-11-23 | Forecast | TBD | Preliminary | 27049 | EAC | TBD | n/a | TBD | TBD | 3 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Unincorporated Los Angeles | 2-16 | TD1971470/TD1971466/ TD2070648/ TD2070649 | Amar Road - Feather Avenue to Sunset | A | Government Agency | Active | Estimating/Design | 2025-02-11 | Forecast | 13945 | Preliminary | 9800000 | EAC | 650 | n/a | 0 | 13945 | 0 | 123532.23 | 123532.23 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic |  |  |  |  | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | Unincorporated Los Angeles | 15-1125 | TD1190256/TD1190260 | Park to Playa Trail | A | Government Agency | Active | Closed | 2020-01-16 | Actual | 1261 | Design | 1210296.37 | Actual | 1638 | Delays due to Native American Impacts | 1217 | 1261 | 0 | 1210296.37 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 6 | n/a | n/a
| Government Agency | n/a | Los Angeles | Unincorporated Los Angeles | 2012-0003 | TD560748/TD593495/TD648480 | Topanga Canyon Business District | A | Government Agency | Active | Construction | 2023-04-28 | Forecast | 3153 | Design | 3500000 | EAC | 750 | n/a | TBD | 3153 | 32 | 6609559.26 | 962731.13 | Yes | Heavy Concentration of OH Facilities | No | Yes | No | Urban Cluster | 23 | n/a | n/a
| Government Agency | n/a | Los Angeles | Unincorporated Los Angeles | 2- | TD1722150/TD1722142 | Vermont Avenue - 228th Street to Belson Street | A | Government Agency | Active | Construction | 2023-03-01 | Forecast | 2407 | Preliminary | 1100000 | EAC | 630 | n/a | TBD | 2407 | 3 | 1255001.57 | 1041555.97 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 12 | n/a | n/a
| Government Agency | n/a | Los Angeles | Unincorporated Los Angeles | 02 16 | TD1721101/TD1724327 | Whittier Boulevard - Hicks Avenue to Downey Road | A | Government Agency | Active | Construction | 2023-04-28 | Forecast | 6673 | Design | 4600000 | EAC | 675 | n/a | TBD | 6673 | 130 | 1608648.83 | 1454990.33 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 40 | n/a | n/a
|  | n/a | Los Angeles | Unincorporated Los Angeles (Castaic) | n/a | TD1766099/TD1766100 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Unincorporated Los Angeles (Littlerock) | n/a | TD1805641/TD1805643 | 7311 E AVE T LITTLEROCK CA 93543 | B |  | Active | Estimating/Design | 2024-12-30 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 302.25 | 302.25 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Los Angeles | Unincorporated Los Angeles (Marina Del Rey) | n/a | TD1450352/TD1450369 |  | C | Business | Active | Estimating/Design | 2023-04-19 | Forecast | 1077 | Design | 321989 | EAC | 298.9684 | n/a | TBD | 1077 | 0 | 224638.66 | 10000.15 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Ventura | Unincorporated Los Angeles (Topanga) | n/a | TD1446606/ TD1446607 |  | C | Individual | Active | Estimating/Design | 2025-12-15 | Forecast | 256 | Design | 70250.07 | EAC | 274.4143 | N/A |  | 256 | 2 | 186.09 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 1 | n/a | n/a
|  | n/a | Los Angeles | Unincorporated Los Angeles (Topanga) | n/a | TD1507711/TD1507712 |  | C | Individual | Active | Estimating/Design | 2025-07-17 | Forecast | 514 | Design | 67165 | EAC | 130.6712 | n/a | TBD | 514 | 8 | 5404.73 | 2263.04 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| Government Agency | n/a | Orange | Unincorporated Orange | 02-196 | TD408576/TD408577/800055515 | Hwy 133/El Toro-San Joaquin Hills T/C | A | Government Agency | Hold | Estimating/Design | 2024-12-31 | Forecast | 4184 | Design | 3000000 | EAC | 750 | n/a | TBD | 4184 | 3 | 924703.16 | 166253.52 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 19 | n/a | n/a
| Government Agency | n/a | Orange | Unincorporated Orange | 02-196 | TD1364864/903100183 | Hwy 133/El Toro-San Joaquin Hills T/C- Trans | A | Government Agency | Hold | Estimating/Design | 2023-06-29 | Forecast | 2929 | Preliminary | 6700000 | EAC | 780 | n/a | TBD | 2929 | 0 | 1692892.48 | 1465993.47 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Unincorporated Orange (Corona Del Mar) | n/a | TD1653525/TD1653526 | 3000 FIFTH AVE CORONA DEL MAR CA 92625 | B | Government Agency | Cancelled |  | n/a |  | 1494 |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Unincorporated Orange (Corona Del Mar) | n/a | TD1683040/TD1683043 | 3000 FIFTH CORONA DEL MAR CA 92625 | B | Government Agency | Active | Closed | 2021-06-24 | Actual | 1499 | Design | 418228.22 | Actual | 279.0048 | n/a | 947 | 1499 | 20 | 418228.22 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
| NEWPORT BEACH, CITY OF | n/a | Orange | Unincorporated Orange (Corona Del Mar) | n/a | TD1089241/TD1089243 | BAYSIDE DR./AVOCADO AVE/PCH/CARNATION AV CORONA DEL MAR CA 92660 | B | Government Agency | Active | Closed | 2020-07-09 | Actual | 9716 | Design | 2092419.18 | Actual | 215.3581 | n/a | 4783 | 9716 | 422 | 2092419.18 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 57 | n/a | n/a
|  | n/a | Orange | Unincorporated Orange (Silverado) | n/a | TD1320439/TD1520515 |  | B | Contractor | Active | Closed | 2022-07-15 | Actual | 2119 | Design | 554065.43 | Actual | 261.475 | n/a | TBD | 2119 | 1 | 554065.43 | 0 | Unknown | n/a | No | No | Yes | Rural | 12 | n/a | n/a
| Government Agency | n/a | Riverside | Unincorporated Riverside | n/a | n/a | Stetson Ave/Santa Fe St-e/o Dartmouth | A | Government Agency | Hold | Planning | TBD |  | 18300 | Preliminary | 14400000 | EAC | 450 | n/a | TBD | 18300 | 0 | 0 | 0 | Yes | Heavy Concentration of OH Facilities | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (French Valley) | n/a | TD1624067/TD1624068 |  | B | Contractor | Active | Construction | 2022-06-09 | Forecast | 3426 | Design | 596930 | EAC | 174.2353 | n/a | TBD | 3426 | 7 | 506100.44 | -168877.58 | Unknown | n/a | No | No | No | Urban Cluster | 11 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Homeland) | n/a | TD1858948/TD1858952 |  | B | Contractor | Active | Construction | 2023-02-13 | Forecast | 2783 | Design | 498581.74 | EAC | 179.1526 | n/a | TBD | 2783 | 2 | 7029.52 | 7029.52 | Unknown | n/a | No | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Homeland) | n/a | TD1824666/TD1824670 |  | B | Contractor | Active | Construction | 2023-03-23 | Forecast | 3295 | Design | 629440 | EAC | 191.0288 | n/a | TBD | 3295 | 3 | 16029.64 | 10483.04 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Romoland) | n/a | TD1691542/TD1691545 |  | B | Contractor | Active | Estimating/Design | 2023-06-20 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 242.45 | 0 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Romoland) | n/a | TD1829054/TD1829055 |  | B | Contractor | Active | Estimating/Design | 2023-05-12 | Forecast | 1837 | Design | 0 | EAC | 0 | n/a | TBD | 1837 | 2 | 4133.46 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Romoland) | n/a | TD1829132/TD1829134 |  | B | Contractor | Active | Estimating/Design | 6/34/23 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | 2 | 4133.46 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1932328/TD1932329 |  | B | Contractor | Active | Estimating/Design | 2023-03-29 | Forecast | 2873 | Design | 613100.15 | EAC | 213.4007 | n/a | TBD | 2873 | - | 3683.33 | 3683.33 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1463568/TD1463569 |  | B | Contractor | Active | Closed | 2020-09-08 | Actual | 2089 | Design | 493344.03 | Actual | 236.1628 | n/a | 1434 | 2089 | - | 493344.03 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1932092/TD1932093 |  | B | Contractor | Active | Estimating/Design | 2023-02-15 | Forecast | 2795 | Design | 383.87 | EAC | TBD | n/a | TBD | 2795 | - | 383.87 | 383.87 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1609187/TD1609188 |  | B | Contractor | Active | Closed | 2021-04-27 | Actual | 2998 | Design | 1348570.34 | Actual | 449.8233 | n/a | 2836 | 2998 | 6 | 1348570.34 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 14 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1505530/TD1505544 |  | B | Individual | Active | Estimating/Design | 2023-05-19 | Forecast | 3666 | Design | 600396 | EAC | 163.7741 | n/a | TBD | 3666 | - | 3440.98 | 3066.74 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD1932129/TD1932130 |  | C | Contractor | Active | Estimating/Design | 2023-06-16 | Forecast | 3115 | Design | 58828.21 | EAC | 18.8855 | n/a | TBD | 3115 | 11 | 881.77 | 881.77 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| Government Agency | n/a | San Bernardino | Unincorporated San Bernardino | 2005-336 | TD272010/TD272011/ TD1213486/ TD1213502/ TD1213487/ TD1213503 | Hwy 18/ Custer-Ladera, Lucerne Valley | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | San Bernardino | Unincorporated San Bernardino | 2005-336 | TD1213517/TD1213516 | Hwy 18/ Custer-Ladera, Lucerne Valley | A | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 70814.31 | -733417.57 | Yes | n/a | No | No | No | urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Unincorporated San Bernardino (Bloomington) | n/a | TD1960402/TD1960404 | 10746 CEDAR AVE BLOOMINGTON CA 92316 | B |  | Active | Estimating/Design | 2023-07-19 | Forecast | 820 | Design | 307524.4 | EAC | 375.0298 | n/a | TBD | 820 | 4 | 5391.72 | 5391.72 | Unknown | n/a | Yes | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Bloomington) | n/a | TD1498473/TD1498474 |  | C | Contractor | Active | Closed | 2020-03-30 | Actual | 1159 | Design | 251876.01 | Actual | 217.3218 | n/a | 1739 | 1159 | 11 | 251876.01 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Bloomington) | n/a | TD1378856/TD1378857 |  | C | Contractor | Active | Closed | 2020-09-15 | Actual | 675 | Design | 190065.46 | Actual | 281.5785 | n/a | 850 | 675 | - | 190065.46 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Bloomington) | n/a | TD1378871/TD1378872 |  | C | Contractor | Active | Closed | 2020-08-28 | Actual | 1667 | Design | 203480.31 | Actual | 122.0638 | n/a | 443 | 1667 | - | 203480.31 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Bloomington) | n/a | TD1610197/TD1610200 |  | C | Contractor | Active | Closed | 2021-09-07 | Actual | 525 | Design | 482723.32 | Actual | 919.473 | n/a | 326 | 525 | 11 | 482723.32 | 113.71 | Unknown | n/a | Yes | No | No | Urban Cluster | 4 | n/a | n/a
| CITY OF RANCHO CUCAMONGA | n/a | San Bernardino | Unincorporated San Bernardino (Foothill) | n/a | TD1104877 | VARIOUS LOCATIONS FOOTHILL CA 00000 | B | Government Agency | Active | Closed | 2020-08-10 | Actual | 0 | Design | -283.26 | Actual | #DIV/0! | n/a | TBD | 0 | 0 | -283.26 | 0 | Unknown | n/a |  |  |  |  | - | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Havasu Lake) | n/a | TD1107253 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unkown | n/a | Unknown | n/a | Unknown | 0 | 0 | Unknown | n/a | No | No | No | Rural | Unknown | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Lytle Creek) | n/a | TD1840689/TD1840690 |  | C | Contractor | Active | Closed | 2021-11-15 | Actual | 851 | Design | 8227 | Actual | 9.6675 | n/a | 126 | 851 | 2 | 8227 | 0.01 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Mentone) | n/a | TD1472450/TD1472452 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0.05 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Mentone) | n/a | TD1449753/TD1449766 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | 198342.94 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 1016.56 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | san Bernardino | Unincorporated San Bernardino (Mentone) | n/a | TD1577310/TD1577311 |  | C | Contractor | Active | Closed | 2021-04-14 | Actual | 1427 | Design | 272485 | Actual | 190.9495 | n/a | 672 | 1427 | 10 | 272485 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Mentone) | n/a | TD1537130/TD1537166 |  | C | Contractor | Active | Closed | 2020-03-18 | Actual | 1526 | Design | 266587.91 | Actual | 174.6972 | n/a | 599 | 1526 | 5 | 266587.91 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Unincorporated San Bernardino (Phelan) | n/a | TD1667022/TD1667023 | 8374 BUTTEMERE PHELAN CA 92371 | B |  | Cancelled |  | n/a |  | 849 | Design | 254942.68 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Phelan) | n/a | TD1820051/TD1820052/TD1820694/TD1820695 |  | B | Individual | Cancelled |  | n/a |  | 200 | Design | 101396.23 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Phelan) | n/a | TD1818429/TD1818434 |  | B | Individual | Cancelled |  | n/a |  | 199 | Design | 1320602.53 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Phelan) | n/a | TD1815745/TD1815746 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | San Bernardino | Unincorporated San Bernardino (Phelan) | n/a | TD1748496 |  |  | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown |  |  | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| Government Agency | n/a | Santa Barbara | Unincorporated Santa Barbara | 04-352 | TD1208798/TD1208793/TD207607/TD207605 | E. Valley Rd/Hot Spgs Rd - Cota Ln | A | Government Agency | Active | Estimating/Design | 2024-05-27 | Forecast | 1217 | Preliminary | 1700000 | EAC | 900 | n/a | TBD | 1217 | 11 | 508131.76 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Santa Barbara | Unincorporated Santa Barbara (Montecito) | n/a | TD1424394 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
| UNKNOWN | n/a | Santa Barbara | Unincorporated Santa Barbara (Montecito) | n/a | TD1734329/TD1734387 | 537 PERIWINKLE MONTECITO CA 93108 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Unincorporated Santa Barbara (Montecito) | n/a | TD2055710/ TD2055711 |  | C | Individual | Active | Estimating/Design | 2023-10-11 | Forecast | TBD | Preliminary | 1200 | EAC | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Santa Barbara | Unincorporated Santa Barbara (Montecito) | n/a | TD1568757 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Santa Barbara | Unincorporated Santa Barbara (Montecito) | n/a | TD1757654/TD1757655 |  | C | Individual | Active | Estimating/Design | 2023-07-17 | Forecast | 575 | Design | 155623 | EAC | 270.6487 | n/a | TBD | 575 | 18 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Santa Barbara | Unincorporated Santa Barbara (Summerland) | n/a | TD1782477/TD1782478 |  | C | Individual | Active | Estimating/Design | 2023-01-04 | Forecast | TBD | Preliminary | 3000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Tulare | Unincorporated Tulare (Terra Bella) | n/a | TD1508504/TD1540026 |  | C | Contractor | Active | Closed | 2020-04-10 | Actual | 304 | Design | 177266.43 | Actual | 583.1133 | n/a | 357 | 304 | 4 | 177266.43 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Unincorporated Ventura (Lake Sherwood) | n/a | TD1983344 |  | B | Individual | Active | Estimating/Design | 2023-12-15 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | No | No | No | Rural | 0 | n/a | n/a
|  | n/a | Ventura | Unincorporated Ventura (Lake Sherwood) | n/a | TD1695479/TD1728782/TD1728783 |  | B | Contractor | Active | Estimating/Design | 2023-12-29 | Forecast | 563 | Design | 95879 | EAC | 170.3002 | n/a | TBD | 563 | 0 | 918 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Unincorporated Ventura (Lake Sherwood) | n/a | TD1983345/TD1989575 |  | C | Individual | Active | Estimating/Design | 2023-12-15 | Forecast | 114 | Design | 46441.81 | EAC | 407.3843 | n/a |  | 114 | 11 | 0 | 0 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
|  | n/a | Ventura | Unincorporated Ventura (Somis) | n/a | TD2034449/ TD2034450 |  | C | Individual | Active | Estimating/Design | 2023-06-09 | Forecast | TBD | Preliminary | 41814.54 | EAC | TBD | n/a |  | TBD | 1 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Unincorporated Ventura (Somis) | n/a | TD2043023 |  | C | Individual | Active | Estimating/Design | 2023-06-09 | Forecast | 403 | Design | 65103.54 | EAC | 161.5472 | n/a |  | 403 | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | San Bernardino | Upland | n/a | TD1570683/TD1570696 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Upland | n/a | TD1658670/TD1658671 |  | B | Business | Active | Estimating/Design | 2023-04-03 | Forecast | 1495 | Design | 332866 | EAC | 222.6528 | n/a | TBD | 1495 | 5 | 12741.57 | 2683.65 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Upland | n/a | TD1588488/TD1588492 |  | C | Contractor | Active | Construction | 2020-07-06 | Actual | 234 | Design | 91755 | EAC | 392.1154 | n/a | 262 | 234 | 13 | 109957 | 3428.8 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | San Bernardino | Upland | n/a | TD1630149/TD1630150 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluser | Unknown | n/a | n/a
|  | n/a | San Bernardino | Upland | n/a | TD1825753/TD1828760 |  | C | Contractor | Active | Closed | 2022-05-25 | Actual | 540 | Design | 271637.21 | Actual | 503.0319 | n/a | TBD | 540 | 7 | 271637.21 | 269368.91 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Upland | 6625 | TD1941265/TD1941259 | Foothill Boulevard - N Central Avenue to 390' W/O C/L of Benson Avenue | A | Government Agency | Active | Estimating/Design | 2025-01-11 | Forecast | 4760 | Preliminary | 3200000 | EAC | 650 | n/a | TBD | 4760 | 0 | 130085.03 | 130085.03 | Yes | Heavy Concentration of OH Facilities | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1750434/TD1750438 |  | B | Contractor | Active | Estimating/Design | 2023-04-07 | Forecast | 1300 | Design | 392377.24 | EAC | 301.8286 | n/a | TBD | 1300 | 9 | 3556.5 | 2955.65 | Unknown | n/a | Yes | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1606771/TD1606773 |  | C | Individual | Active | Closed | 2021-05-10 | Actual | 85 | Design | 16521.25 | Actual | 194.3676 | n/a | 38 | 85 | 5 | 16521.25 | 0 | Unknown | n/a | No | No | No | Rural | 1 | n/a | n/a
| UNKNOWN | n/a | Ventura | Ventura | n/a | TD1448444/TD1448450 | 1290 E THOMPSON BLVD VENTURA CA 93001 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1509101/TD1558113 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1638546/TD1638548 |  | C | Individual | Active | Closed | 2021-11-23 | Actual | 1274 | Design | 85610 | Actual | 67.1978 | n/a | 106 | 1274 | 23 | 85610 | 3241.57 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1481870/TD1481873 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | No | No | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1735971/TD1739531 |  | C | Contractor | Active | Closed | 2021-10-19 | Actual | 306 | Design | 44580.53 | Actual | 145.688 | n/a | 432 | 306 | 0 | 44580.53 | 869.12 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1430056/TD1430061 |  | C | Individual | Active | Construction | 2023-03-23 | Forecast | 1108 | Design | 481607 | EAC | 434.6634 | n/a | TBD | 1108 | 15 | 588821 | 321148 | Unknown | n/a | No | No | No | Urban Cluster | 12 | n/a | n/a
| UNKNOWN | n/a | Ventura | Ventura | n/a | TD1729672/TD1729673/TD1730197 | 2222 HILLCREST DR VENTURA CA 93001 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1445155/TD1445162 |  | C | Individual | Active | Closed | 2020-09-15 | Actual | 450 | Design | 21691.11 | Actual | 48.2025 | n/a | 487 | 450 | 6 | 21691.11 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1899133/TD1899136 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Ventura | Ventura | n/a | TD1971584/ TD1971585 |  | C | Individual | Active | Closed | 2022-11-15 | Actual | 67 | Design | 46848.11 | Actual | 699.2255 | n/a |  | 67 | 1 | 46848.11 | 46848.11 | Unknown | n/a | No | No | No | Urban Cluser | 1 | n/a | n/a
| UNKNOWN | n/a | Ventura | Ventura | n/a | TD2041251 | 7583 LEMUR ST VENTURA CA 93003 | C |  | Active | Estimating/Design | 2023-06-07 | Forecast | 0 | Preliminary | 2752.42 | EAC | 0 | n/a |  | 0 | 4 | 38986 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | San Bernardino | Victorville | 19-076 | TD1650335/TD1649221/TD1669394 | Nisqualli/ Arrowhead to 7th | A | Government Agency | Active | Closing | 2022-05-16 | Actual | 1112 | Design | 764013.66 | Actual | 950 | n/a | TBD | 1112 | 7 | 764013.66 | 680639.19 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 5 | n/a | n/a
|  | n/a | San Bernardino | Victorville | n/a | TD1833919/TD1833920 |  | B | Contractor | Active | Construction | 2022-03-30 | Forecast | 3558 | Design | 404643 | EAC | 113.7277 | n/a | TBD | 3558 | 3 | 550567.88 | 542950.27 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Victorville | n/a | TD1930672/TD1930674 | BEAR VALLEY RD AND AMETHYST RD VICTORVILLE CA 92392 | B |  | Active | Estimating/Design | 2023-02-28 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 40770.31 | 40770.31 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | San Bernardino | Victorville | n/a | TD1340722/TD1440627 |  | B | Contractor | Active | Closed | 2021-08-18 | Actual | 850 | Design | 412627.35 | Actual | 485.4439 | n/a | 879 | 850 | - | 412627.35 | 1055.76 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
| VICTORVILLE, CITY OF | n/a | San Bernardino | Victorville | n/a | TD1298950/TD1298951 | 11734 AMETHYST RD VICTORVILLE CA 92392 | C | Government Agency | Active | Closed | 2020-11-12 | Actual | 189 | Design | 38986.07 | Actual | 206.2755 | n/a | 1066 | 189 | 4 | 38986.07 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
|  | n/a | San Bernardino | Victorville | n/a | TD1641574/TD1641575 |  | C | Contractor | Active | Closed | 2021-05-25 | Actual | 2131 | Design | 776894 | Actual | 364.5678 | n/a | 1050 | 2131 | 16 | 776894 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Victorville | n/a | TD1878015/TD1878016 | 17876 BEAR VALLEY RD VICTORVILLE CA 92395 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Victorville | n/a | TD1765585 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| Government Agency | n/a | Tulare | Visalia | 2007-83 | n/a | Dinuba Blvd/ ShJulioon Pkwy to Riverway Dr, Ph. 2 | A | Government Agency | Hold | Planning | TBD |  | 2055 | Preliminary | 750000 | EAC | 350 | n/a | TBD | 2055 | 0 | 0 | 0 |  | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD1685078/TD1685079 |  | B | Contractor | Active | Estimating/Design | 2021-04-23 | Forecast | TBD | Preliminary | 0 | EAC | TBD | n/a | TBD | TBD | - | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD2084030 |  | B | Contractor | Active | Estimating/Design | 2024-04-26 | Forecast | TBD | Preliminary | - | EAC | TBD | n/a |  | TBD | - | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Urban Cluster | 2 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD1786350/TD1786351 |  | C | Contractor | Active | Closed | 2021-08-23 | Actual | 1456 | Design | 439165.51 | Actual | 301.6247 | n/a | Secondary only | 1456 | 2 | 439165.51 | -363.27 | Unknown | n/a | No | No | No | Urban Cluster | 17 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD1503530/TD1503531 |  | C | Contractor | Active | Closed | 2022-03-15 | Actual | 774 | Design | 165937.65 | Actual | 214.3897 | n/a | 691 | 774 | 2 | 165937.65 | 105511.18 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD1890747/TD1890748 |  | C | Business | Active | Closing | 2022-12-20 | Actual | 1342 | Design | 526688.62 | Actual | 392.4654 | n/a | TBD | 1342 | 4 | 526688.62 | 526688.62 | Unknown | n/a | No | No | No | Urban Cluster | 10 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD2004412/ TD2004413 |  | C | Business | Active | Estimating/Design | 2023-03-24 | Forecast | 1708 | Preliminary | 253356.05 | EAC | 148.3349 | n/a |  | 1708 | 2 | 2324.97 | 2324.97 | Unknown | n/a | Yes | No | No | Urban Cluster | 6 | n/a | n/a
|  | n/a | Tulare | Visalia | n/a | TD2051267/ TD2051268 |  | C | Business | Active | Estimating/Design | 2023-10-18 | Forecast | 0 | Preliminary | 0 | EAC | 0 | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | Walnut | n/a | TD1909876/TD1909877 |  | C | Contractor | Active | Closed | 2022-06-20 | Actual | 676 | Design | 141451.51 | Actual | 209.2478 | n/a |  | 676 | 7 | 141451.51 | 141451.51 | Unknown | n/a | No | No | No | Urban Cluster | 7 | n/a | n/a
| Government Agency | n/a | Los Angeles | West Covina | 2022-45 | TD1996662/TD1996657 | W Merced Ave - 230' E/O C/L S Orange Ave to 140' W/O C/L S Trojan Way | A | Government Agency | Active | Estimating/Design | 2024-12-31 | Forecast | 1935 | Preliminary | 1400000 | EAC | 650 | n/a | TBD | 1935 | 0 | 28376.23 | 28376.23 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | West Covina | n/a | TD174829/TD1806343 |  | C | Contractor | Active | Construction | 2022-08-19 | Forecast | 1072 | Design | 323029 | EAC | 301.333 | n/a | TBD | 1072 | 43 | 175346.44 | 175200.02 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| Government Agency | n/a | Los Angeles | West Hollywood | 19-5215 | TD1638827/TD1638825 | Beverly Blvd/ Doheny Dr to Robertson Blvd | A | Government Agency | Active | Estimating/Design | 2024-06-28 | Forecast | 2510 | Preliminary | 2200000 | EAC | 800 | n/a | TBD | 2510 | 235 | 177007 | 46904.87 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Los Angeles | West Hollywood | 11 4238 | TD1315390/TD1315389 | Melrose Ave/ San Vicente Blvd to Doheny Dr, Ph.2 | A | Government Agency | Active | Construction | 2023-03-31 | Forecast | 2863 | Design | 1600000 | EAC | 600 | n/a | TBD | 2863 | 27 | 4263648.05 | 3976741.31 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 25 | n/a | n/a
| WEST HOLLYWOOD, CITY OF | n/a | Los Angeles | West Hollywood | n/a | TD1758906/TD1758915 | ALMONT DR - MELROSE AVE TO SM BLVD WEST HOLLYWOOD CA 90069 | B | Government Agency | Active | Estimating/Design | 2023-10-18 | Forecast | 355 | Design | 149638 | EAC | 421.5155 | n/a | TBD | 355 | 14 | 551.41 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| WEST HOLLYWOOD, CITY OF | n/a | Los Angeles | West Hollywood | n/a | TD1686467/TD1686616 | LA PEER DR - MELROSE AVE TO SM BLVD WEST HOLLYWOOD CA 90069 | B | Government Agency | Active | Estimating/Design | 2023-10-18 | Forecast | 1051 | Design | 400197 | EAC | 380.7774 | n/a | TBD | 1051 | 56 | 2838.12 | 141.64 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
| WEST HOLLYWOOD, CITY OF | n/a | Los Angeles | West Hollywood | n/a | TD1630272 | LA PEER/ALMONT DR-MELROSE AVE TO SM BLVD WEST HOLLYWOOD CA 90069 | B | Government Agency | Active | Estimating/Design | 2021-12-20 | Forecast | TBD | Preliminary | 20000 | EAC | TBD | n/a | TBD | TBD | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| WEST HOLLYWOOD, CITY OF | n/a | Los Angeles | West Hollywood | n/a | TD1678658 | MELROSE AVE AND ALMONT DR WEST HOLLYWOOD CA 90069 | B | Government Agency | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| WEST HOLLYWOOD, CITY OF | n/a | Los Angeles | West Hollywood | n/a | TD1688460/TD1714192 | MELROSE AVE AND ALMONT DR WEST HOLLYWOOD CA 90069 | B | Government Agency | Cancelled |  | n/a |  | 338 |  | 116462.95 | EAC | 344.5649 | n/a | Unknown | 338 | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 6 | n/a | n/a
|  | n/a | Los Angeles | West Hollywood | n/a | TD1741303 |  | C | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Los Angeles | West Hollywood | n/a | TD1059862 |  | C | Contractor | Active | Closed | 2022-07-10 | Actual | 1029 | Design | 292832.21 | Actual | 284.5794 | n/a | 241 | 1029 | 0 | 292832.21 | 733.73 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Los Angeles | West Hollywood | n/a | TD1211199/TD1211200/TD1919958/TD1919959 |  | C | Contractor | Active | Estimating/Design | 2022-10-24 | Forecast | 926 | Design | 284371.62 | EAC | 307.0968 | n/a | TBD | 926 | 48 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
| CITY OF WEST HOLLYWOOD | n/a | Los Angeles | West Hollywood | n/a | TD1577807 | 8750 EL TOVAR PL WEST HOLLYWOOD CA 90069 | C | Government Agency | Active | Closed | 2022-03-21 | Actual | 0 | Design | 39909.93 | Actual | 0 | n/a | 175 | 0 | 0 | 39909.93 | 39909.93 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| Government Agency | n/a | Orange | Westminster | 4933 | TD1513437 | Bolsa Ave/ Brookhurst | A | Government Agency | Active | Estimating/Design | 2024-03-18 | Forecast | 3430 | Design | 3400000 | EAC | 991.2536 | n/a | TBD | 3430 | 0 | 537758.18 | 104005.05 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 0 | n/a | n/a
| WESTMINSTER, CITY OF | n/a | Orange | Westminster | n/a | TD1659238/TD1659239 | R20B/BOLSA BLVD & BROOKHURST ST. WESTMINSTER CA 92683 | B | Government Agency | Active | Construction | 2022-12-05 | Forecast | 3489 | Design | 950336.67 | EAC | 272.3808 | n/a | TBD | 3489 | 16 | 384525.67 | 347711.16 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Los Angeles | Whittier | n/a | TD553308/ TD553304 |  | A | Individual | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | Yes | Unknown | Unknown | Rural | Unknown | n/a | n/a
| Government Agency | n/a | Los Angeles | Whittier | 7433 | TD1139966/TD1139965/TD1978008/TD1978001 | Broadway/Whittier Blvd to Acacia Ave | A | Government Agency | Active | Estimating/Design | 2024-11-15 | Forecast | 9128 | Design | 3200000 | EAC | 350.5697 | n/a | TBD | 9128 | 288 | 330443.27 | 226919.98 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 28 | n/a | n/a
| Government Agency | n/a | Los Angeles | Whittier | 7781 | TD1141994/TD1141999 | Colima Rd/ Whittier Blvd to Lambert Rd | A | Government Agency | Active | Closed | 2020-09-01 | Actual | 5174 | Design | 3313888.26 | Actual | 641.2848 | n/a | 3365 | 5174 | 46 | 3313888.26 | 0 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 29 | n/a | n/a
| Government Agency | n/a | Los Angeles | Whittier | 8722 | TD1138116/TD1138118/802000577 | Greenway Trail - 5 Points | A | Government Agency | Active | Estimating/Design | 2023-12-29 | Forecast | 3072 | Design | 1200000 | EAC | 550 | n/a | TBD | 3072 | 107 | 135781.87 | 45256.26 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | No | No | Urban Cluster | 21 | n/a | n/a
| UNKNOWN | n/a | Los Angeles | Whittier | n/a | TD2017628 | FIRESTONE WHITTIER CA 90638 | C |  | Active | Estimating/Design | 2023-11-15 | Forecast | 0 | Preliminary | 12362.87 | EAC | 0 | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | Yes | No | No | Urban Cluster | 9 | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1636831 |  | B | Business | Cancelled |  | n/a |  | n/a |  | 67 | EAC | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1751560 |  | B | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Riverside | Wildomar | n/a | TD1830920/TD1830921 | 36485 INLAND VALLEY DR WILDOMAR CA 92595 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | 0 | -6412.85 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
| UNKNOWN | n/a | Riverside | Wildomar | n/a | TD1912031 | 7845 CLINTON KEITH RD WILDOMAR CA 92595 | B |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1852199/TD1852202 |  | B | Contractor | Active | Construction | 2023-02-14 | Forecast | 2057 | Design | 491005 | EAC | 238.6996 | n/a | TBD | 2057 | 7 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 8 | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1215603/TD1215604 |  | B | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | unknown | -366.16 | -366.16 | Unknown | n/a | No | No | No | Urban Cluster | - | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1636839 |  | C | Business | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1500196/TD1500197 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1375160/TD1476402 |  | C | Contractor | Active | Closed | 2020-12-11 | Actual | 490 | Design | 99002.31 | Actual | 202.0455 | n/a | 552 | 490 | 2 | 99002.31 | 757.76 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
| UNKNOWN | n/a | Riverside | Wildomar | n/a | TD1784359 | 5412 CLINTION KEITH WILDOMAR CA 92595 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1782322/TD1782326 |  | C | Contractor | Active | Estimating/Design | 2023-04-20 | Forecast | 0 | Preliminary | 0 | EAC | 0 | n/a | TBD | 0 | 6 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 4 | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1705833/TD1884390 |  | C | Contractor | Active | Estimating/Design | 2023-12-15 | Forecast | 620 | Design | 187109 | EAC | 301.7887 | n/a | TBD | 620 | 0 | 9392.25 | 1435.24 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD1961423/TD1961426 |  | C | Contractor | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a |  | Unknown | Unknown |  | Unknown | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD2067978/ TD2067977 |  | C | Business | Active | Estimating/Design | 2023-12-04 | Forecast | 0 | Preliminary | 0 | EAC | 0 | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Riverside | Wildomar | n/a | TD2085823/ TD2085820 | CLINTON KEITH RD / WILDOMAR TRAIL (R20C) WILDOMAR CA 92595 | C |  | Active | Estimating/Design | 2023-01-24 | Forecast | TBD | Preliminary | 0 | EAC | 0 | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Wildomar | n/a | TD2008060/ TD2008054 |  | C | Business | Active | Estimating/Design | 2023-06-27 | Forecast | 0 | Preliminary | 0 | EAC | 0 | n/a |  | 0 | 0 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 0 | n/a | n/a
| UNKNOWN | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD2054694/TD2054692 | KELLER RD (R20B) WINCHESTER CA 92596 | B |  | Active | Estimating/Design | 2023-10-27 | Forecast | TBD | Preliminary | Unknown |  | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 0 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside (Winchester) | n/a | TD2091981/TD2091983 |  | B | Contractor | Active | Estimating/Design | 2023-03-29 | Forecast | 2873 | Design | Unknown |  | TBD | n/a |  | TBD | 0 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 10 | n/a | n/a
|  | n/a | Riverside | Unincorporated Riverside(Woodcrest) | n/a | TD2003195/TD2003196 |  | B | Business | Active | Closed | 2021-11-09 | Actual | 1290 | Design | 0 | Actual | Unknown | n/a |  | 1290 | 7 | 0 | 0 | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | 6 | n/a | n/a
|  | n/a | Orange | Yorba Linda | n/a | TD1632159/TD1632191 |  | B | Contractor | Active | Closed | 2021-11-09 | Actual | 978 | Design | 349075.59 | Actual | 356.928 | n/a | 794 | 978 | 3 | 349075.59 | 1168.79 | Unknown | n/a | No | No | No | Urban Cluster | 6 | n/a | n/a
| Government Agency | n/a | Orange | Yorba Linda | 2017-5498 | TD1308007/TD1307991 | Lakeview/ Yorba Linda to Lemon Drive | A | Government Agency | Active | Closed | 2020-01-30 | Actual | 1696 | Design | 1104270 | Actual | 651.1026 | n/a | 878 | 1696 | 12 | 1104270 | 0 | Yes | Arterial Street or Major Collector | No | No | No | urban Cluster | 6 | n/a | n/a
|  | n/a | Orange | Yorba Linda | n/a | TD1583748/TD1583749 |  | C | Contractor | Active | Closed | 2022-09-06 | Actual | 153 | Design | 98125.007 | Actual | 641.3399 | n/a | TBD | 153 | 0 | 98125.007 | 88108.1 | Unknown | n/a | No | No | No | Urban Cluster | 2 | n/a | n/a
|  | n/a | Orange | Yorba Linda | n/a | TD1596484/TD1596490 |  | C | Contractor | Active | Closed | 2020-11-13 | Actual | 176 | Design | 97427.17 | Actual | 553.5635 | n/a | 110 | 176 | 0 | 97427.17 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 1 | n/a | n/a
| UNKNOWN | n/a | San Bernardino | Yucaipa | n/a | TD1120576/TD1120577 | C/O YUCAIPA BLVD AND CALIFORNIA YUCAIPA CA 92399 | C |  | Cancelled |  | n/a |  | n/a |  | Unknown |  | Unknown | n/a | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | n/a | No | Unknown | Unknown | Urban Cluster | Unknown | n/a | n/a
|  | n/a | San Bernardino | Yucaipa | n/a | TD1603422/TD1630685 |  | C | Individual | Active | Estimating/Design | 2021-01-04 | Forecast | 606 | Design | 51346 | EAC | 84.7294 | n/a | TBD | 606 | 4 | 0 | 0 | Unknown | n/a | No | No | No | Urban Cluster | 3 | n/a | n/a
| Government Agency | n/a | San Bernardino | Yucca Valley | 21 30 | TD1954008/TD1954013 | Palm Ave & Little League Dr. | A | Government Agency | Active | Estimating/Design | 2026-12-31 | Forecast | 1850 | Preliminary | 1800000 | EAC | 900 | n/a | TBD | 1850 | 8 | 52624.11 | 52624.11 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 12 | n/a | n/a
Note on X4: Talisa Lee: Only SCE Expenditures. Customer Cost not Captured
Note on S802: Jeff Corthell: Need final design trench footage

## Community - By Tranche
Rule 20 Community Data
| Tranche 1 (High Priority) | [28 empty] | Tranche 3 (Low Priority)
| Project Sponsor | Work Credits Redeemed for Rule 20A Projects, Reporting Period | Number of Customers | Outstanding Work Credit Debt | Years of Work Credit Debt (Active Work Credit Debt / Next Year Allocation) | Miles of Primary Overhead Converted Under Rule 20A, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20B, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20C, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20D, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles Trenched Under Rule 20A, Reporting Period | Miles Trenched Under Rule 20D, Reporting Period (SDG&E Only) | Total Cost of Projects Completed Under Rule 20A, Reporting Period | Total Cost of Projects Completed Under Rule 20B, Reporting Period (IOU Work Only) | Total Cost of Projects Completed Under Rule 20C, Reporting Period (IOU Work Only) | Total Cost of Projects Completed Under Rule 20D, Reporting Period (IOU Work Only, SDG&E Only) | Work Credit Ledger Balance, End of Reporting Period (Balance from Prior Year - Work Credit Deductions) | Work Credit Allocation, Next Year (2023) | Work Credit Balance, (Column Q + Column R) | Number of Projects in Planning Phase, Reporting Period | Number of Projects in Estimating/Design Phase, Reporting Period | Number of Projects in Construction Phase, Reporting Period | Number of Projects in Closing Phase, Reporting Period | Number of Projects in Closed Phase, Reporting Period | Work Credits Redeemed for Rule 20A Projects Divided by Number of Customers | Work Credits Used in 2022 | Projects in Top 25% DAC as Defined by CalEnviroScreen? | Total Trenched Miles, Last Year of Reporting Period (Projects Reported in Closing/Closed Phase Only) | Work Credits Added Through Transfer from Other Community, Reporting Period (Any Allowable Method of Transfer) | In Shape File? | Urban/Urban Cluster/Rural Community as Defined in the American Community Survey | Number of Rule 20A Projects Completed to Date | Number of Rule 20B Projects Completed to Date | Number of Rule 20C Projects Completed to Date | Number of Rule 20D Projects Completed to Date (SDG&E Only) | Project Sponsor Active/Inactive?
| Adelanto | 0 | 10579 | -27012.5684 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -27012.5684 | 0 | -27012.5684 | 0 | 1 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Agoura Hills | 55752.24 | 9342 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 22540.4524 | 0 | 22540.4524 | 0 | 2 | 0 | 0 | 0 | 5.9679 | 55752.24 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Alhambra | 433609.16 | 36284 | 0 | * | 0 | 0.18485 | 0 | n/a | 0 | n/a | 0 | 325999 | 0 | n/a | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 11.9504 | 224509.06 | Yes | 0 | 1149883.3996 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Active
| Aliso Viejo | 0 | 20104 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 50771.1154 | 0 | 50771.1154 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Anaheim | 0 | 208 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 2404.0776 | 0 | 2404.0776 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Apple Valley | 0 | 29653 | 0 | * | 0 | 0 | 0.19034 | n/a | 0 | n/a | 0 | 0 | 254481.07 | n/a | 820235.9555 | 0 | 820235.9555 | 0 | 1 | 0 | 1 | 0 | 0 |  | No | 0.12348 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Arcadia | 0 | 24026 | 0 | * | 0 | 0 | 0.080303 | n/a | 0 | n/a | 0 | 0 | 416983.3 | n/a | 11815.9327 | 0 | 11815.9327 | 0 | 2 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Artesia | 257322.57 | 5683 | -3456277.5287 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 58626.3213 | 0 | 58626.3213 | 0 | 1 | 0 | 0 | 0 | 45.2794 | 124300.15 | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Avalon | 0 | 2413 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 233417.7224 | 0 | 233417.7224 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Azusa | 0 | 400 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 96287.0931 | 0 | 96287.0931 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Baldwin Park | 2068809.19 | 20409 | 0 | * | 0.80114 | 0 | 0 | n/a | 0.6233 | n/a | 2132591.54 | 0 | 0 | n/a | 1191830.3566 | 0 | 1191830.3566 | 0 | 0 | 0 | 1 | 0 | 101.3675 | 1528.17 | Yes | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Banning | 0 | 63 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 4982.0944 | 0 | 4982.0944 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Barstow | -152773.58 | 10517 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | -14.5263 | -170092.97 | Yes | 0 | 120708.8622 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Beaumont | 0 | 19066 | 0 | * | 0 | 0 | 0.034848 | n/a | 0 | n/a | 0 | 0 | 82852.48 | n/a | 81404.9783 | 0 | 81404.9783 | 0 | 2 | 0 | 1 | 0 | 0 |  | No | 0.035038 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Bell | 0 | 9845 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 172144.0085 | 0 | 172144.0085 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Bell Gardens | 10185.08 | 11090 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1389080.3628 | 0 | 1389080.3628 | 0 | 1 | 0 | 0 | 0 | 0.9184 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Bellflower | 0 | 27141 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1723698.3432 | 0 | 1723698.3432 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Beverly Hills | 0 | 19997 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 464756.9922 | 0 | 464756.9922 | 0 | 2 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Bishop | 0 | 546 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 101591.8807 | 0 | 101591.8807 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Blythe | 0 | 6446 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 586194.9102 | 0 | 586194.9102 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Bradbury | 0 | 407 | 0 | * | 0 | 0 | 0.044508 | n/a | 0 | n/a | 0 | 0 | 44035.58 | n/a | 124200.9169 | 0 | 124200.9169 | 0 | 0 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Rural | 0 | 0 | 1 | n/a | Inactive
| Brea | 0 | 19874 | -182334.1645 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -182334.1645 | 0 | -182334.1645 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Buena Park | 0 | 29152 | 0 | * | 0 | 0 | 0.071023 | n/a | 0 | n/a | 0 | 0 | 124472.56 | n/a | 95884.954 | 0 | 95884.954 | 0 | 2 | 0 | 0 | 1 | 0 | 154415.7 | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Calabasas | 0 | 10545 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 979982.2501 | 0 | 979982.2501 | 0 | 2 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| California City | 0 | 5649 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 625949.6563 | 0 | 625949.6563 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Calimesa | 0 | 4512 | 0 | * | 0 | 0.13939 | 0.26231 | n/a | 0 | n/a | 0 | 281509.28 | 140044.37 | n/a | 211184.8301 | 0 | 211184.8301 | 0 | 0 | 1 | 0 | 2 | 0 |  | No | 0.13636 | 0 | Yes | Urban Cluster | 0 | 1 | 1 | n/a | Inactive
| Camarillo | 5118.43 | 31763 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 237426.7465 | 0 | 237426.7465 | 0 | 5 | 0 | 0 | 0 | 0.16114 | 9256.89 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Canyon Lake | 0 | 4854 | -21408.0618 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -21408.0618 | 0 | -21408.0618 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Carpinteria | 0 | 6015 | 0 | * | 0 | 0.12973 | 0.50473 | n/a | 0 | n/a | 0 | 830951.14 | 5793664 | n/a | 181368.9256 | 0 | 181368.9256 | 0 | 2 | 0 | 0 | 6 | 0 |  | No | 0.043939 | 0 | Yes | Urban Cluster | 0 | 1 | 5 | n/a | Inactive
| Carson | 0 | 31298 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 903969.8563 | 0 | 903969.8563 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Cathedral City | 0 | 25062 | 0 | * | 0 | 0 | 0.70682 | n/a | 0 | n/a | 0 | 0 | 1536272 | n/a | 81124.5204 | 0 | 81124.5204 | 0 | 2 | 1 | 0 | 2 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 2 | n/a | Active
| Cerritos | 104122.57 | 18718 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 4.6566e-10 | 0 | 4.6566e-10 | 0 | 0 | 1 | 0 | 0 | 5.5627 | 54291.63 | No | 0 | 915227.4615 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Chino | 116408.6 | 32797 | -45283.0973 | * | 0 | 1.0941 | 0.25057 | n/a | 0 | n/a | 0 | 1373973 | 403295 | n/a | -45283.0973 | 0 | -45283.0973 | 0 | 4 | 1 | 1 | 4 | 3.5494 | 104456.69 | No | 0.51061 | 0 | Yes | Urban Cluster | 0 | 1 | 2 | n/a | Active
| Chino Hills | 0 | 28010 | -893908.6849 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -893908.6849 | 0 | -893908.6849 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Claremont | 0 | 13943 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 845784.902 | 0 | 845784.902 | 0 | 2 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Colton | 0 | 362 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 18135.4224 | 0 | 18135.4224 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Commerce | 52103.97 | 6375 | -106112.6975 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -106112.6975 | 0 | -106112.6975 | 0 | 2 | 0 | 0 | 0 | 8.1732 | 52103.97 | Yes | 0 | 0 | Yes | urban cluster | 0 | 0 | 0 | n/a | Active
| Compton | 0 | 27749 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 5668364.6343 | 0 | 5668364.6343 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Corona | 787170.18 | 55579 | -214414.4076 | * | 0.12936 | 0 | 0.36591 | n/a | 0.18371 | n/a | 768427.99 | 0 | 357543 | n/a | -214414.4076 | 0 | -214414.4076 | 0 | 2 | 1 | 0 | 3 | 14.1631 | 0 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 2 | n/a | Active
| Costa Mesa | 67487.28 | 50530 | -1038135.7381 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -1038135.7381 | 0 | -1038135.7381 | 0 | 3 | 0 | 0 | 0 | 1.3356 | 67487.28 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Covina | 0 | 20103 | 0 | * | 0 | 0 | 0.12652 | n/a | 0 | n/a | 0 | 0 | 355332.21 | n/a | 487718.6587 | 0 | 487718.6587 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Cudahy | -97441.97 | 6114 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1805057.2835 | 0 | 1805057.2835 | 0 | 1 | 0 | 0 | 0 | -15.9375 | -110665.01 | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Culver City | 1989423.09 | 20726 | -524307.6406 | * | 0.18087 | 0 | 0.31951 | n/a | 0.33674 | n/a | 2104185.19 | 0 | 5923 | n/a | -524307.6406 | 0 | -524307.6406 | 0 | 1 | 2 | 1 | 5 | 95.9868 | 1341388.81 | No | 0.57273 | 0 | Yes | Urban Cluster | 1 | 0 | 2 | n/a | Active
| Cypress | 0 | 18597 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1701621.1588 | 0 | 1701621.1588 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Delano | 0 | 12737 | -41593.8446 | * | 0 | 0.19432 | 0.76117 | n/a | 0 | n/a | 0 | 232923 | 315225 | n/a | -41593.8446 | 0 | -41593.8446 | 0 | 3 | 1 | 2 | 3 | 0 |  | Yes | 0.78845 | 0 | Yes | Urban Cluster | 0 | 2 | 3 | n/a | Active
| Desert Hot Springs | 0 | 12172 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 193456.2 | 0 | n/a | 969978.4385 | 0 | 969978.4385 | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Diamond Bar | 85358.52 | 21342 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 27860.6436 | 0 | 27860.6436 | 0 | 1 | 0 | 0 | 0 | 3.9996 | 83532.22 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Downey | 0 | 39262 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 2958005.1563 | 0 | 2958005.1563 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Duarte | 0 | 7857 | 0 | * | 0 | 0 | 0.0625 | n/a | 0 | n/a | 0 | 0 | 141108 | n/a | 66994.3585 | 0 | 66994.3585 | 0 | 1 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Eastvale | 188039.27 | 18753 | -55802.5057 | * | 0 | 0.16837 | 0 | n/a | 0 | n/a | 0 | 218317 | 0 | n/a | -55802.5057 | 0 | -55802.5057 | 0 | 1 | 0 | 0 | 1 | 10.0272 | 188039.27 | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Active
| El Monte | 0 | 33003 | 0 | * | 0 | 0 | 1.7019 | n/a | 0 | n/a | 0 | 0 | 741423 | n/a | 425171.5182 | 0 | 425171.5182 | 0 | 2 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| El Segundo | 0 | 9543 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1119329.7002 | 0 | 1119329.7002 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Elsinore, Lake | 0 | 23675 | -78872.7256 | * | 0 | 0.43977 | 0 | n/a | 0 | n/a | 0 | 727512 | 0 | n/a | -78872.7256 | 0 | -78872.7256 | 0 | 10 | 0 | 0 | 2 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 2 | 0 | n/a | Active
| Exeter | 0 | 4061 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 107085.1672 | 0 | 107085.1672 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Farmersville | 0 | 2840 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 653800.0012 | 0 | 653800.0012 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Fillmore | 35933.47 | 5118 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 152909.037 | 0 | 152909.037 | 0 | 1 | 0 | 0 | 0 | 7.021 | 35933.47 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Fontana | 88030.71 | 61973 | 0 | * | 0 | 1.5519 | 2.5839 | n/a | 0 | n/a | 0 | 1123036 | 4342228 | n/a | 0 | 0 | 0 | 4 | 17 | 4 | 0 | 18 | 1.4205 | 88030.71 | Yes | 1.6441 | 208603.7576 | Yes | Urban Cluster | 0 | 2 | 16 | n/a | Active
| Fountain Valley | 0 | 22003 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 972790.9627 | 0 | 972790.9627 | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Fullerton | 0 | 54993 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 819966.4137 | 0 | 819966.4137 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Garden Grove | 101972.64 | 54817 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 2.794e-09 | 0 | 2.794e-09 | 0 | 1 | 0 | 0 | 0 | 1.8602 | 29586.61 | No | 0 | 771588.1436 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Gardena | 0 | 25683 | -923421.8197 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -923421.8197 | 0 | -923421.8197 | 0 | 1 | 1 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Glendale | 0 | 491 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 85275.5383 | 0 | 85275.5383 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Glendora | 355888.57 | 20714 | -44017.5674 | * | 0.30398 | 0 | 0 | n/a | 0.54602 | n/a | 1522295.55 | 0 | 0 | n/a | -44017.5674 | 0 | -44017.5674 | 0 | 0 | 0 | 0 | 1 | 17.1811 | 0 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Goleta | 0 | 14138 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1236870.0758 | 0 | 1236870.0758 | 0 | 4 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Grand Terrace | 0 | 5071 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 815616.7836 | 0 | 815616.7836 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Hanford | 0 | 22716 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1328916.9076 | 0 | 1328916.9076 | 0 | 3 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Hawaiian Gardens | 173258.27 | 3908 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 44.3343 | 3105.26 | Yes | 0 | 81665.7674 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Hawthorne | 0 | 30035 | 0 | * | 0 | 0 | 0.18902 | n/a | 0 | n/a | 0 | 0 | 934250 | n/a | 1421505.311 | 0 | 1421505.311 | 0 | 0 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Hemet | 0 | 34787 | 0 | * | 0 | 0.14432 | 0.041667 | n/a | 0 | n/a | 0 | 319254.03 | 263872 | n/a | 715692.5321 | 0 | 715692.5321 | 0 | 1 | 0 | 1 | 2 | 0 |  | No | 0.055114 | 0 | Yes | urban cluster | 0 | 1 | 2 | n/a | Inactive
| Hermosa Beach | 0 | 11053 | 0 | * | 0 | 0 | 0.083333 | n/a | 0 | n/a | 0 | 0 | 286663 | n/a | 615360.6778 | 0 | 615360.6778 | 0 | 2 | 0 | 0 | 2 | 0 |  | No | 0 | 0 | Yes | urban cluster | 0 | 0 | 2 | n/a | Inactive
| Hesperia | 8851.95 | 34126 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1003514.875 | 0 | 1003514.875 | 0 | 3 | 1 | 0 | 0 | 0.25939 | 8490.92 | No | 0 | 0 | Yes | urban cluster | 0 | 0 | 0 | n/a | Active
| Hidden Hills | 0 | 712 | 0 | * | 0 | 0.2483 | 0.088826 | n/a | 0 | n/a | 0 | 826752.87 | 85953 | n/a | 25893.6239 | 0 | 25893.6239 | 0 | 4 | 0 | 0 | 3 | 0 |  | No | 0.045076 | 0 | Yes | urban cluster | 0 | 1 | 2 | n/a | Inactive
| Highland | 0 | 17964 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 224609.79 | n/a | 23235.4084 | 0 | 23235.4084 | 0 | 1 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Huntington Beach | 0 | 89596 | -1320815.829 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -1320815.829 | 0 | -1320815.829 | 0 | 3 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Huntington Park | 119086.43 | 17602 | -687542.4418 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -687542.4418 | 0 | -687542.4418 | 0 | 2 | 0 | 0 | 0 | 6.7655 | 119086.43 | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Indian Wells | 0 | 5500 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 27099.7195 | 0 | 27099.7195 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Industry | 0 | 3337 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 409048.6866 | 0 | 409048.6866 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Inglewood | 0 | 44106 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 42359.36 | n/a | 2444805.9536 | 0 | 2444805.9536 | 0 | 0 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Irvine | 43038 | 136711 | 0 | * | 0 | 0.25492 | 0 | n/a | 0 | n/a | 0 | 12669685 | 0 | n/a | 196703.6132 | 0 | 196703.6132 | 0 | 3 | 0 | 0 | 2 | 0.31481 | 43038 | No | 0.28504 | 0 | Yes | urban cluster | 0 | 2 | 0 | n/a | Active
| Irwindale | 0 | 1843 | -87327.4963 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -87327.4963 | 0 | -87327.4963 | 0 | 1 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | rural | 0 | 0 | 0 | n/a | Inactive
| Jurupa Valley | 0 | 30338 | 0 | * | 0 | 0 | 0.15985 | n/a | 0 | n/a | 0 | 0 | 435862 | n/a | 117126.0682 | 0 | 117126.0682 | 0 | 5 | 0 | 0 | 1 | 0 |  | Yes | 0.13106 | 0 | Yes | urban cluster | 0 | 0 | 1 | n/a | Inactive
| La Canada-Flintridge | 0 | 7938 | -3329335.0876 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -3329335.0876 | 0 | -3329335.0876 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| La Habra | 0 | 23740 | 0 | * | 0 | 0 | 0.45114 | n/a | 0 | n/a | 0 | 0 | 268925.72 | n/a | 971062.3222 | 0 | 971062.3222 | 2 | 4 | 0 | 0 | 1 | 0 | 0 | Yes | 0.20114 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| La Habra Heights | 0 | 1998 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 207589.6076 | 0 | 207589.6076 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| La Mirada | 40019.48 | 16460 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 174141.3344 | 0 | 174141.3344 | 0 | 2 | 0 | 0 | 0 | 2.4313 | 40019.48 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| La Palma | 0 | 5634 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 129580.4611 | 0 | 129580.4611 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| La Puente | 30598.65 | 11196 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1432355.2237 | 0 | 1432355.2237 | 0 | 1 | 0 | 0 | 0 | 2.733 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| La Verne | 5221181.32 | 12563 | -1323597.9581 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -1323597.9581 | 0 | -1323597.9581 | 0 | 1 | 1 | 0 | 0 | 415.5999 | 4203862.78 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Laguna Beach | 493250.25 | 12526 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 80521.75 | 0 | n/a | 1471685.4627 | 0 | 1471685.4627 | 0 | 8 | 0 | 0 | 1 | 39.3781 | 50364.25 | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Active
| Laguna Hills | 0 | 6078 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 107720.8143 | 0 | 107720.8143 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Laguna Niguel | 0 | 4932 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 74124.3763 | 0 | 74124.3763 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Laguna Woods | 0 | 13691 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1020.7675 | 0 | 1020.7675 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Lake Forest | 0 | 34318 | -1300357.5814 | * | 0 | 0.51364 | 0 | n/a | 0 | n/a | 0 | 164699.94 | 0 | n/a | -1300357.5814 | 0 | -1300357.5814 | 0 | 0 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Inactive
| Lakewood | 0 | 29827 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 5074017.1749 | 0 | 5074017.1749 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Lancaster | 0 | 58122 | 0 | * | 0 | 0.068939 | 0.11155 | n/a | 0 | n/a | 0 | 77703.05 | 242932 | n/a | 3841008.99 | 0 | 3841008.99 | 1 | 3 | 1 | 0 | 3 | 0 |  | No | 0.23068 | 0 | Yes | Urban Cluster | 0 | 1 | 2 | n/a | Active
| Lawndale | 0 | 10860 | -323813.8753 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -323813.8753 | 0 | -323813.8753 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Lindsay | 0 | 4353 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 483086.9737 | 0 | 483086.9737 | 1 | 0 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Loma Linda | 0 | 10924 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 282271.7109 | 0 | 282271.7109 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Lomita | 0 | 9358 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 191298.3024 | 0 | 191298.3024 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Long Beach | -28995.27 | 193431 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 158834.16 | n/a | 21254489.358 | 0 | 21254489.358 | 0 | 5 | 0 | 0 | 1 | -0.1499 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Los Alamitos | 0 | 6237 | 0 | * | 0 | 0 | 0.10133 | n/a | 0 | n/a | 0 | 0 | 143482.28 | n/a | 195689.8684 | 0 | 195689.8684 | 0 | 0 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Los Angeles, City of | 0 | 1461 | 0 | * | 0 | 0 | 0.1536 | n/a | 0 | n/a | 0 | 0 | 223414 | n/a | 74031.2 | 0 | 74031.2 | 0 | 1 | 0 | 0 | 3 | 0 |  | No | 0.027462 | 0 | Yes | Urban Cluster | 0 | 0 | 3 | n/a | Inactive
| Lynwood | 0 | 17195 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 417422.7651 | 0 | 417422.7651 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Malibu | 0 | 7637 | -323563.7756 | * | 0 | 0.20133 | 0.26042 | n/a | 0 | n/a | 0 | 161394.97 | 347925 | n/a | -323563.7756 | 0 | -323563.7756 | 0 | 24 | 0 | 0 | 7 | 0 |  | No | 0.31894 | 0 | Yes | Urban Cluster | 0 | 1 | 6 | n/a | Inactive
| Mammoth Lakes | 0 | 11072 | -25206.0407 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -25206.0407 | 0 | -25206.0407 | 1 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Manhattan Beach | 0 | 16473 | -3712236.2566 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 70519.19 | n/a | -3712236.2566 | 0 | -3712236.2566 | 0 | 5 | 3 | 0 | 1 | 0 |  | No | 0.075 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Maywood | 0 | 7143 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1340385.2348 | 0 | 1340385.2348 | 1 | 1 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| McFarland | 0 | 978 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 133308.7771 | 0 | 133308.7771 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Menifee | 0 | 39459 | -6794.3351 | * | 0 | 0.33693 | 1.029 | n/a | 0 | n/a | 0 | 603426 | 1502378 | n/a | -6794.3351 | 0 | -6794.3351 | 1 | 5 | 2 | 1 | 4 | 0 |  | No | 0.93561 | 0 | Yes | Urban Cluster | 0 | 2 | 3 | n/a | Active
| Mission Viejo | 0 | 27116 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 42906.5817 | 0 | 42906.5817 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Monrovia | 0 | 17446 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 137784.1235 | 0 | 137784.1235 | 0 | 7 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Montclair | 31853.54 | 13096 | 0 | * | 0 | 0 | 0.033333 | n/a | 0 | n/a | 0 | 0 | 14740.82 | n/a | 56801.9468 | 0 | 56801.9468 | 0 | 0 | 0 | 0 | 1 | 2.4323 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Montebello | -185396.34 | 23529 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -7.8795 | -190208.17 | Yes | 0 | 133244.2959 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Monterey Park | -71195.41 | 24196 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 943304.8459 | 0 | 943304.8459 | 0 | 3 | 0 | 0 | 0 | -2.9424 | -309.05 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Moorpark | 0 | 13490 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 535145.8533 | 0 | 535145.8533 | 0 | 4 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Moreno Valley | 0 | 54746 | 0 | * | 0 | 0.4678 | 1.4116 | n/a | 0 | n/a | 0 | 866438 | 1510463 | n/a | 1375120.9727 | 0 | 1375120.9727 | 0 | 2 | 0 | 0 | 8 | 0 |  | Yes | 0.28977 | 0 | Yes | Urban Cluster | 0 | 3 | 5 | n/a | Active
| Murrieta | 0 | 40948 | 0 | * | 0 | 0.17367 | 0.29489 | n/a | 0 | n/a | 0 | 246222.32 | 784883 | n/a | 67511.8806 | 0 | 67511.8806 | 0 | 5 | 1 | 2 | 3 | 0 |  | No | 0.22841 | 0 | Yes | Urban Cluster | 0 | 1 | 4 | n/a | Active
| Newport Beach | 7304136.43 | 48952 | -848081.51 | * | 0.12917 | 0 | 0 | n/a | 0.51989 | n/a | 3883579.71 | 905967 | 0 | n/a | -848081.51 | 0 | -848081.51 | 0 | 2 | 5 | 0 | 3 | 149.2102 | 1435412.75 | No | 1.3807 | 301462.3042 | Yes | Urban Cluster | 1 | 2 | 0 | n/a | Active
| Norco | 0 | 8584 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 991243.4974 | 0 | 991243.4974 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Norwalk | 3838127.12 | 29758 | 0 | * | 0 | 0 | 0 | n/a | 0.51989 | n/a | 7098383.03 | 0 | 0 | n/a | 1958552.7072 | 0 | 1958552.7072 | 1 | 0 | 0 | 1 | 0 | 128.978 | 1341026.4 | Yes | 1.4326 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Ojai | 0 | 3988 | -120657.3168 | * | 0 | 0 | 0.016288 | n/a | 0 | n/a | 0 | 0 | 15394 | n/a | -120657.3168 | 0 | -120657.3168 | 0 | 7 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Ontario | 11457.63 | 65047 | 0 | * | 0 | 1.1907 | 0.19716 | n/a | 0 | n/a | 0 | 1172302 | 305046 | n/a | 2926.18 | 0 | 2926.18 | 0 | 20 | 1 | 1 | 4 | 0.17614 | 7147.56 | No | 0.60189 | 1635249.2465 | Yes | Urban Cluster | 0 | 3 | 1 | n/a | Active
| Orange | 0 | 55712 | 0 | * | 0 | 0 | 0.039773 | n/a | 0 | n/a | 0 | 0 | 51342.93 | n/a | 658541.6916 | 0 | 658541.6916 | 0 | 3 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Oxnard | 0 | 60322 | 0 | * | 0 | 0 | 0.039773 | n/a | 0 | n/a | 0 | 0 | 203706 | n/a | 138998.7842 | 0 | 138998.7842 | 0 | 4 | 0 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Palm Desert | 39633.76 | 42787 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 290971.5942 | 0 | 290971.5942 | 0 | 3 | 0 | 0 | 0 | 0.9263 | 39633.76 | No | 0 | 0 | Yes | Rural | 0 | 0 | 0 | n/a | Active
| Palm Springs | 3308.65 | 39336 | 0 | * | 0 | 0 | 0.5017 | n/a | 0 | n/a | 0 | 0 | 1542704 | n/a | 4.6566e-10 | 0 | 4.6566e-10 | 0 | 3 | 0 | 1 | 2 | 0.084113 | 1136.57 | No | 0.40814 | 645181.2663 | Yes | Urban Cluster | 0 | 0 | 3 | n/a | Active
| Palmdale | 0 | 52450 | 0 | * | 0 | 0 | 0.059091 | n/a | 0 | n/a | 0 | 0 | 184895.04 | n/a | 1603507.6619 | 0 | 1603507.6619 | 0 | 6 | 2 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Palos Verdes Estates | 0 | 5758 | -162644.8205 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -162644.8205 | 0 | -162644.8205 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Paramount | 0 | 16551 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1291366.7174 | 0 | 1291366.7174 | 0 | 4 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Pasadena | 0 | 139 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 9555.9092 | 0 | 9555.9092 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Perris | 0 | 21236 | -11727.6227 | * | 0 | 0.57083 | 1.3684 | n/a | 0 | n/a | 0 | 1908851 | 3000219 | n/a | -11727.6227 | 0 | -11727.6227 | 1 | 26 | 1 | 0 | 11 | 0 |  | No | 0.39356 | 0 | Yes | Urban Cluster | 0 | 5 | 6 | n/a | Inactive
| Pico Rivera | 0 | 18364 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 973231.8664 | 0 | 973231.8664 | 0 | 0 | 1 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Placentia | 1101447.58 | 19481 | -305175.0796 | * | 0.22576 | 0 | 0 | n/a | 0.31193 | n/a | 1165443.38 | 0 | 0 | n/a | -305175.0796 | 0 | -305175.0796 | 0 | 3 | 1 | 0 | 1 | 56.5396 | 2550.02 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Pomona | 0 | 47431 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 7410421.6267 | 0 | 7410421.6267 | 0 | 1 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Port Hueneme | 0 | 8730 | -81343.0703 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -81343.0703 | 0 | -81343.0703 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Porterville | 36144.45 | 20592 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 156530.6022 | 0 | 156530.6022 | 1 | 2 | 0 | 0 | 0 | 1.7553 | 36144.45 | Yes | 0 | 750000 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Rancho Cucamonga | 1620082.6 | 66655 | 0 | * | 0.60795 | 0.29527 | 0.80871 | n/a | 0.99545 | n/a | 3640217.7 | 783411.86 | 1237618 | n/a | 408616.8061 | 0 | 408616.8061 | 0 | 6 | 1 | 1 | 11 | 24.3055 | 63024 | No | 0.57273 | 0 | Yes | Urban Cluster | 2 | 1 | 9 | n/a | Active
| Rancho Mirage | 0 | 15883 | -85801.2058 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -85801.2058 | 0 | -85801.2058 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Rancho Palos Verdes | 1150193.8 | 17328 | 0 | * | 0.20473 | 0 | 0 | n/a | 0.22405 | n/a | 527092.98 | 0 | 0 | n/a | 547763.4584 | 0 | 547763.4584 | 0 | 1 | 1 | 0 | 1 | 66.3778 | 617224.15 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Rancho Santa Margarita | 0 | 18947 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 65883.771 | 0 | 65883.771 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Redlands | 67509.16 | 30954 | 0 | * | 0 | 0 | 0.24242 | n/a | 0 | n/a | 0 | 0 | 1544514 | n/a | 4.6566e-10 | 0 | 4.6566e-10 | 0 | 4 | 5 | 1 | 3 | 2.181 | 1105.35 | No | 0.50133 | 497482.1396 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Redondo Beach | 800710.2 | 35301 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 292437.3819 | 0 | 292437.3819 | 0 | 3 | 0 | 0 | 0 | 22.6824 | 78665.01 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 4 | n/a | Active
| Rialto | 1870.25 | 30824 | 0 | * | 0 | 0 | 1.1705 | n/a | 0 | n/a | 0 | 220278.91 | 1386304 | n/a | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 7 | 0.060675 | 642.46 | Yes | 0 | 282155.2184 | Yes | Urban Cluster | 0 | 1 | 6 | n/a | Active
| Ridgecrest | 0 | 13657 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 3005755.9462 | 0 | 3005755.9462 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Riverside, City of | 0 | 961 | 0 | * | 0 | 0.1339 | 0 | n/a | 0 | n/a | 0 | 257061.65 | 0 | n/a | 5439.1604 | 0 | 5439.1604 | 0 | 1 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Inactive
| Rolling Hills | 104881.47 | 905 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 208982.9886 | 0 | 208982.9886 | 0 | 8 | 0 | 0 | 0 | 115.8911 | 37870.24 | No | 0 | 1000000 | Yes | Rural | 0 | 0 | 0 | n/a | Active
| Rolling Hills Estates | 0 | 3802 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 18970.4133 | 0 | 18970.4133 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Rosemead | 1790741.5 | 16655 | 0 | * | 0.37027 | 0 | 0 | n/a | 1.01 | n/a | 2848291.27 | 0 | 0 | n/a | 405413.9999 | 0 | 405413.9999 | 0 | 0 | 0 | 0 | 1 | 107.5198 | -175133.63 | Yes | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| San Bernardino | 63023.88 | 75328 | 0 | * | 0 | 0.56193 | 1.1839 | n/a | 0 | n/a | 0 | 1050568 | 1490450 | n/a | 956269.0279 | 0 | 956269.0279 | 0 | 10 | 0 | 1 | 7 | 0.83666 | 15061.96 | Yes | 0.21004 | 0 | Yes | Urban Cluster | 0 | 2 | 6 | n/a | Active
| San Dimas | 1077522.73 | 13871 | 0 | * | 0.082955 | 0 | 0 | n/a | 0.1536 | n/a | 1077522.73 | 0 | 0 | n/a | 230167.6628 | 0 | 230167.6628 | 0 | 0 | 0 | 0 | 1 | 77.6817 | -160567.53 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| San Fernando | 0 | 7856 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 431166.0083 | 0 | 431166.0083 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| San Gabriel | 0 | 16030 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 651488.23 | 0 | n/a | 12181.0284 | 0 | 12181.0284 | 0 | 2 | 0 | 1 | 0 | 0 |  | No | 0.20814 | 0 | Yes | Urban Cluster | 0 | 1 | 0 | n/a | Active
| San Jacinto | 0 | 16331 | 0 | * | 0 | 0 | 0.17045 | n/a | 0 | n/a | 0 | 222600.35 | 80054.31 | n/a | 190959.2977 | 0 | 190959.2977 | 0 | 4 | 0 | 0 | 2 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 1 | n/a | Inactive
| San Marino | 769946.2 | 5083 | -255351.8694 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -255351.8694 | 0 | -255351.8694 | 0 | 0 | 1 | 0 | 0 | 151.4748 | 757641 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Santa Ana | 1101998.62 | 91226 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 5.5879e-09 | 0 | 5.5879e-09 | 4 | 0 | 1 | 0 | 9 | 12.0799 | 933282.97 | Yes | 0 | 3547355.0971 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Santa Barbara | 71191.61 | 42645 | 0 | * | 0 | 0.12576 | 0.081629 | n/a | 0 | n/a | 0 | 285234.16 | 374600 | n/a | 308321.8631 | 0 | 308321.8631 | 0 | 15 | 0 | 0 | 8 | 1.6694 | 77350.06 | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 7 | n/a | Active
| Santa Clarita | 0 | 88986 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 194448.9672 | 0 | 194448.9672 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Santa Fe Springs | 0 | 10765 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1204981.0558 | 0 | 1204981.0558 | 0 | 4 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| Santa Monica | 0 | 59496 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 650347.4226 | 0 | 650347.4226 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | urban Cluster | 0 | 0 | 0 | n/a | Active
| Santa Paula | 0 | 10293 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1109595.8386 | 0 | 1109595.8386 | 0 | 2 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Seal Beach | 0 | 15401 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 140238.2679 | 0 | 140238.2679 | 1 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Sierra Madre | 0 | 5441 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 173403.9121 | 0 | 173403.9121 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Signal Hill | 0 | 6637 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 717935.444 | 0 | 717935.444 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Rural | 0 | 0 | 0 | n/a | Inactive
| Simi Valley | 62011.12 | 49038 | 0 | * | 0 | 0 | 0.32879 | n/a | 0 | n/a | 0 | 0 | 192887.2 | n/a | 114447.9079 | 0 | 114447.9079 | 0 | 2 | 1 | 0 | 1 | 1.2646 | 62011.12 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| South El Monte | 1734073.89 | 8169 | 0 | * | 0 | 0 | 0 | n/a | 1.2689 | n/a | 1828558.07 | 0 | 0 | n/a | 194321.7743 | 0 | 194321.7743 | 0 | 0 | 0 | 1 | 0 | 212.2749 | 671639.1 | Yes | 1.2689 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| South Gate | 0 | 27596 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 4504054.5981 | 0 | 4504054.5981 | 3 | 0 | 0 | 0 | 0 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Inactive
| South Pasadena | 219122.71 | 12413 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 17.6527 | 88521.42 | No | 0 | 266287.1796 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Stanton | 64244.05 | 12267 | 0 | * | 0 | 0 | 0.028788 | n/a | 0 | n/a | 0 | 0 | 258230.28 | n/a | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 5.2371 | 6466.31 | No | 0 | 123391.8901 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Tehachapi | 52495.73 | 4596 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1903958.7198 | 0 | 1903958.7198 | 0 | 1 | 0 | 0 | 0 | 11.422 | 52495.73 | No | 0 | 4455000 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Temecula | 0 | 44315 | 0 | * | 0 | 0.37311 | 0 | n/a | 0 | n/a | 0 | 632338 | 0 | n/a | 328528.8691 | 0 | 328528.8691 | 0 | 2 | 0 | 0 | 2 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 2 | 0 | n/a | Inactive
| Temple City | 0 | 13341 | -264530.6354 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -264530.6354 | 0 | -264530.6354 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Thousand Oaks | 112500.78 | 53901 | 0 | * | 0 | 0.71705 | 0 | n/a | 0 | n/a | 0 | 557312 | 0 | n/a | 56781.0968 | 0 | 56781.0968 | 0 | 4 | 0 | 0 | 4 | 2.0872 | 112500.78 | No | 0 | 0 | Yes | Urban Cluster | 0 | 4 | 0 | n/a | Active
| Torrance | 255168.05 | 64918 | 0 | * | 0.48636 | 0 | 0.065341 | n/a | 1.0792 | n/a | 2745028.73 | 0 | 64513.71 | n/a | 3893306 | 0 | 3893306 | 0 | 2 | 1 | 0 | 2 | 3.9306 | -421280.67 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 1 | n/a | Active
| Tulare | 0 | 24495 | 0 | * | 0 | 0 | 0.2 | n/a | 0 | n/a | 0 | 0 | 418167.35 | n/a | 484563.3738 | 0 | 484563.3738 | 0 | 9 | 1 | 0 | 2 | 0 |  | Yes | 0.19318 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Tustin | 40832.94 | 31946 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 279835.6147 | 0 | 279835.6147 | 0 | 3 | 0 | 0 | 0 | 1.2782 | 40832.94 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Twentynine Palms | 1422596.82 | 8186 | 0 | * | 0.14129 | 0.14129 | 0 | n/a | 0.4464 | n/a | 1436315.92 | 387887.18 | 0 | n/a | 27538.6933 | 0 | 27538.6933 | 0 | 1 | 0 | 0 | 2 | 173.7841 | -7836.65 | No | 0 | 0 | Yes | Urban Cluster | 1 | 1 | 0 | n/a | Active
| Unincorporated Fresno | 0 | 2971 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 709884.0155 | 0 | 709884.0155 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Imperial | 0 | 430 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 165673.8046 | 0 | 165673.8046 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Inyo | 0 | 5453 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 613382.7795 | 0 | 613382.7795 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Kern | 0 | 47939 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 2068422.7744 | 0 | 2068422.7744 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Active
| Unincorporated Kings | 0 | 5719 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 627821.1177 | 0 | 627821.1177 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Los Angeles | 5571392.58 | 320096 | 0 | * | 0.23049 | 0 | 0 | n/a | 0.23883 | n/a | 1210296.37 | 0 | 0 | n/a | 22147444.6627 | 0 | 22147444.6627 | 0 | 5 | 3 | 0 | 1 | 17.4054 | 3582809.66 | No | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Unincorporated Madera | 0 | 15 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 6283.3418 | 0 | 6283.3418 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Mono | 0 | 3805 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 11638.7418 | 0 | 11638.7418 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Orange | 1952334.08 | 31046 | 0 | * | 0 | 1.0852 | 0 | n/a | 0 | n/a | 0 | 3064713 | 0 | n/a | 2.794e-09 | 0 | 2.794e-09 | 0 | 2 | 0 | 0 | 3 | 62.8852 | 1632246.99 | No | 0.40133 | 1440485.2452 | Yes | Urban Cluster | 0 | 3 | 0 | n/a | Active
| Unincorporated Riverside | 0 | 117771 | 0 | * | 0 | 0.80871 | 0 | n/a | 0 | n/a | 0 | 1841914 | 0 | n/a | 11806325.6499 | 0 | 11806325.6499 | 1 | 9 | 3 | 0 | 3 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 3 | 0 | n/a | Active
| Unincorporated San Bernardino | -705640.71 | 122632 | 0 | * | 0 | 0 | 0.90057 | n/a | 0 | n/a | 0 | -283.26 | 1675445 | n/a | 11974902.8577 | 0 | 11974902.8577 | 0 | 1 | 0 | 0 | 8 | -5.7541 | -733417.57 | No | 0 | 0 | Yes | Urban Cluster | 0 | 1 | 7 | n/a | Active
| Unincorporated San Diego | 0 | 17 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1518.6048 | 0 | 1518.6048 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Santa Barbara | 6 | 25908 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 64215.5898 | 0 | 64215.5898 | 0 | 4 | 0 | 0 | 0 | 0.00023159 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Unincorporated Tulare | 0 | 58452 | 0 | * | 0 | 0 | 0.067614 | n/a | 0 | n/a | 0 | 0 | 177266.43 | n/a | 12427149.7956 | 0 | 12427149.7956 | 0 | 0 | 0 | 0 | 1 | 0 |  | Yes | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Unincorporated Tuolumne | 0 | 31 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 1375.6072 | 0 | 1375.6072 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Unincorporated Ventura | 0 | 39265 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 3285734.568 | 0 | 3285734.568 | 0 | 6 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Upland | 130085.03 | 34179 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 271637.21 | n/a | 62826.4169 | 0 | 62826.4169 | 0 | 2 | 1 | 0 | 1 | 3.806 | 130085.03 | No | 0.10227 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Active
| Ventura | 0 | 49988 | 0 | * | 0 | 0 | 0.20133 | n/a | 0 | n/a | 0 | 0 | 215251 | n/a | 1007041.8797 | 0 | 1007041.8797 | 0 | 2 | 1 | 0 | 5 | 0 | 680639.19 | No | 0.012689 | 0 | Yes | Urban Cluster | 0 | 0 | 5 | n/a | Inactive
| Victorville | 763239.59 | 44056 | -1.1642e-10 | * | 0 | 0.16648 | 0.40076 | n/a | 0.21061 | n/a | 764013.66 | 412627.35 | 815880 | n/a | -1.1642e-10 | 0 | -1.1642e-10 | 0 | 1 | 1 | 1 | 3 | 17.3243 |  | No | 0.21061 | 382403.335 | Yes | Urban Cluster | 1 | 1 | 2 | n/a | Active
| Villa Park | 0 | 2160 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 8070.5379 | 0 | 8070.5379 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Visalia | 0 | 56855 | 0 | * | 0 | 0 | 0.13087 | n/a | 0 | n/a | 0 | 0 | 1131792 | n/a | 265096.9004 | 0 | 265096.9004 | 1 | 4 | 0 | 1 | 2 | 0 |  | Yes | 0.40076 | 0 | Yes | Urban Cluster | 0 | 0 | 3 | n/a | Active
| Walnut | 0 | 10459 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 141451.51 | n/a | 742916.6481 | 0 | 742916.6481 | 0 | 0 | 0 | 0 | 1 | 0 |  | No | 0.12803 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| West Covina | 28376.23 | 36652 | -19752.7682 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -19752.7682 | 0 | -19752.7682 | 0 | 1 | 1 | 0 | 0 | 0.77421 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| West Hollywood | 4504492 | 28180 | -2647042.9039 | * | 0 | 0 | 0.078788 | n/a | 0 | n/a | 0 | 0 | 332742 | n/a | -2647190 | 0 | -2647190 | 0 | 5 | 1 | 0 | 2 | 159.8471 | 4023646.18 | No | 0.19489 | 0 | Yes | Urban Cluster | 0 | 0 | 2 | n/a | Active
| Westlake Village | 0 | 4341 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 188506.921 | 0 | 188506.921 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Westminster | 449324.51 | 29908 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 4.6566e-10 | 0 | 4.6566e-10 | 0 | 1 | 1 | 0 | 0 | 15.0236 | 104005.05 | No | 0 | 502856.7244 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
| Whittier | 1645856.91 | 33335 | 0 | * | 0.63731 | 0 | 0 | n/a | 0.97992 | n/a | 3313888.26 | 0 | 0 | n/a | 928285.9527 | 0 | 928285.9527 | 0 | 3 | 0 | 0 | 1 | 49.3732 | 272176.24 | Yes | 0 | 0 | Yes | Urban Cluster | 1 | 0 | 0 | n/a | Active
| Wildomar | 0 | 12425 | 0 | * | 0 | 0 | 0.10455 | n/a | 0 | n/a | 0 | 0 | 99002.31 | n/a | 299595.6648 | 0 | 299595.6648 | 0 | 5 | 1 | 0 | 1 | 0 |  | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 1 | n/a | Inactive
| Woodlake | 0 | 2622 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 138787.6198 | 0 | 138787.6198 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No |  | 0 | 0 | 0 | n/a | Inactive
| Yorba Linda | 229641.4 | 26361 | 0 | * | 0.16629 | 0.15038 | 0.020833 | n/a | 0.32121 | n/a | 1104270 | 349075.59 | 195552 | n/a | 78912.1505 | 0 | 78912.1505 | 0 | 0 | 0 | 0 | 4 | 8.7114 |  | No | 0.028977 | 0 | Yes | Urban Cluster | 1 | 1 | 2 | n/a | Active
| Yucaipa | 0 | 19522 | -58643.8796 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | -58643.8796 | 0 | -58643.8796 | 0 | 1 | 0 | 0 | 0 | 0 |  | No | 0 | 0 | Yes | Urban Cluster |  | 0 | 0 | n/a | Inactive
| Yucca Valley | 52624.11 | 11021 | 0 | * | 0 | 0 | 0 | n/a | 0 | n/a | 0 | 0 | 0 | n/a | 72407.0615 | 0 | 72407.0615 | 0 | 0 | 0 | 0 | 0 | 4.7749 | 52624.11 | No | 0 | 0 | Yes | Urban Cluster | 0 | 0 | 0 | n/a | Active
* Cities/ counties received zero annual allocations for 2023, as determined by Phase 1 of OIR Decison R.17-05-010.
Note on C5: Talisa Lee: Work Credits Redeemed in 2020- 2022
Note on K5: Talisa Lee: Miles Trenched (already completed) = Closed and Closing
Note on Q5: Talisa Lee: Year End 2022 Balance
Note on Y5: Talisa Lee: Work Credits based on reporting period 2020- 2022 (column B divided by colum C)
Note on Z5: Talisa Lee: Data provided equates to amount spent in year 2022 only. *SCE deducts entire estimated amount of project at the initiation of the project
Note on AB5: Talisa Lee: Last Year of report is 2022
Note on AC5: Talisa Lee: Approved by CPUC 03-2023 to report transfers for the last year of the reporting period (2022
Note on AF5: Talisa Lee: Closed and Closing Phase