| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,170,729 | $333,677 | 3% | $1,081,997 | 11% |  |  | $1,081,997 | 11% | $9,088,732 |
| Admin | $284,832 | $260 | 0% | $1,188 | 0% |  |  | $1,188 | 0% | $283,644 |
| Marketing | $255,000 |  |  | $1,714 | 1% |  |  | $1,714 | 1% | $253,286 |
| DI | $9,423,988 | $333,417 | 4% | $1,079,094 | 11% |  |  | $1,079,094 | 11% | $8,344,894 |
| EM&V | $206,909 |  |  |  |  |  |  |  |  | $206,909 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,253 | 246 | 3% | 982 | 12% |  |  | 982 | 12% | 7,271 |
| Annual kWh | 48,295,687 | 1,434,916 | 3% | 5,721,281 | 12% |  |  | 5,721,281 | 12% | 42,574,406 |
| Lifecyc kWh | 289,774,120 | 8,609,495 | 3% | 34,327,684 | 12% |  |  | 34,327,684 | 12% | 255,446,436 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- Prepared a petition to modify the Decision 03-12-060 related to the age restrictions on refrigerators and freezers.  The petition was filed at the end of May 2004 in anticipation of the July 1, 2004 deadline imposed by the CPUC’s ED staff to implement this new program requirement.

- manager ated in e-alongs with rr (ARCA) to evaluation gathered during the ride along included customees with theeduls and logicalsse pickup (csProgram manager

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization -

| Types of Measures Recommended | Numbers of Measures Installed |
| --- | --- |
| Refrigerators | 1,834 |
| Freezers | 207 |

      - Calculated and Actual Payment Reconciliation -

The calculate rebate amount shown in the program’s corresponding workbook does not reflect the cost to pick-up and recycle the refrigerator/freezer.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which will require refrigerators and freezers be manufactured prior to 1990.

- Coordination Activities

- Discussions were initiated with outside contractors used by the LIEE group to conduct RARP HTR outreach efforts to moderate income households.

- Discussions were initiated with Flex Your Power (FYP) to incorporate RARP in their advertising campaigns.

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey report to the RARP program information/sign up web site page.

- Coordinated efforts with the South Bay Partnership Program to promote RARP by distributing brochures through various events held within the cities of the South Bay.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None