| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Single Family Energy Efficiency Rebates Program - Procurement |
| Program Number: | 1160-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $24,390,501 | $839,885 | 3% | $14,478,356 | 59% | $2,984,340 | 12% | $17,462,696 | 72% | $9,912,145 |
| Admin | $850,600 | $9,197 | 1% | $129,045 | 15% |  |  | $129,045 | 15% | $721,555 |
| Marketing | $652,800 | $4,969 | 1% | $175,163 | 27% |  |  | $175,163 | 27% | $477,637 |
| DI | $22,379,722 | $825,719 | 4% | $14,174,149 | 63% | $2,984,340 | 13% | $17,158,488 | 77% | $8,205,573 |
| EM&V | $507,379 |  |  |  |  |  |  |  |  | $507,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 76,630 | 2,590 | 3% | 47,341 | 62% | 12,404 | 16% | 59,745 | 78% | 29,289 |
| Annual kWh | 438,945,086 | 8,938,480 | 2% | 231,983,438 | 53% | 87,988,893 | 20% | 319,972,332 | 73% | 206,961,647 |
| Lifecyc kWh | 4,473,372,488 | 101,580,296 | 2% | 2,336,466,459 | 52% | 944,292,538 | 21% | 3,280,758,997 | 73% | 2,136,906,029 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Conducted additional estimates-to-complete and confirmed that shutting down additional measures will not be necessary.

- Additional Fund shifts for lighting measures were allocated to November and December.   Discussions are underway suggesting that any unspent administrative lighting funds as of December would be earmarked for enhanced promotional involvement in 2005.

    - Marketing -

- None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in November |
| --- | --- |
| Pool Pump & Motors | 361 |
| Room AC | 61 |
| Windows | 4,622 |
| ENERGY STAR® qualified Refrigerators | 1,757 |
| Programmable Thermostats | 4,885 |
| Attic Insulation | 0 |
| Whole House Fans | 125 |
| Desert Area Air Conditioning | 76 |
| HVAC | 741 |
| Evaporative Coolers | 34 |
| Lighting | 113,258 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

The EM&V activity is being done as a supplement to the 2004-05 EM&V study of statewide Single Family Energy Efficiency Rebate program that is being managed by PG&E.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The procument-funded Single Family EE Rebates program underwent a series of fundshifts in August and September. The first in August transferred $2.8M into the Direct Implementation Incentives budget from the procurement-funded Appliance Recycling program ($273,733 from Administrative and $2,526,267 from Direct Implementation Incentives.)  The second in September transferred $500k into the Direct Implementation Incentives budget from the Direct Implementation Incentives budget of the procurement-funded Savings By Design program.  The third in September transferred $500k into the Direct Implementation Incentives budget from the Direct Implementation Incentives budget of the procurement-funded Upstream HVAC & Motors Rebate program.