| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Single Family Energy Efficiency Rebates Program - Procurement |
| Program Number: | 1160-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $24,488,599 | $615,808 | 3% | $1,427,582 | 6% | $7,638,717 | 31% | $9,066,298 | 37% | $23,061,017 |
| Admin | $850,600 | $680 | 0% | $1,037 | 0% |  |  | $1,037 | 0% | $849,563 |
| Marketing | $652,800 | -$100 | 0% | $112,238 | 17% |  |  | $112,238 | 17% | $540,562 |
| DI | $22,477,820 | $615,228 | 3% | $1,314,307 | 6% | $7,638,717 | 34% | $8,953,023 | 40% | $21,163,513 |
| EM&V | $507,379 |  |  |  |  |  |  |  |  | $507,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 76,612 | 967 | 1% | 1,906 | 2% | 34,110 | 45% | 36,015 | 47% | 74,706 |
| Annual kWh | 437,623,136 | 807,889 | 0% | 1,781,009 | 0% | 231,574,507 | 53% | 233,355,516 | 53% | 435,842,127 |
| Lifecyc kWh | 4,449,309,674 | 14,375,764 | 0% | 31,222,802 | 1% | 2,292,826,656 | 52% | 2,324,049,458 | 52% | 4,418,086,872 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Continued discussions with Home Depot regarding the expansion of point-of-sale rebates to include Room Air Conditioners.

- Continued discussions with Lowe’s to include Room Air Conditioners and Electric Water Heaters in the point-of-sale method of rebate payments.

- Lighting measure allocations for April through October are set to achieve targets.

    - Marketing -

See Attachment A for list of marketing materials.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Rebated | Numbers of Measures Installed |
| --- | --- |
| Windows | 180,595 |
| ENERGY STAR® qualified Refrigerators | 2,543 |
| HVAC | 844 |
| Lighting | 0 |

      - Calculated and Actual Payment Reconciliation -

There was an incorrect charge that resulted in a discrepancy between the financial incentives paid in Tab 1A - Expenditures Worksheet and the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.  The discrepancy is being corrected and will be accurately reflected in next month’s report.

    - EM&V

The EM&V activity is being done as a supplement to the 2004-05 EM&V study of statewide Single Family Energy Efficiency Rebate program that is being managed by PG&E.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None