| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Single Family Energy Efficiency Rebates Program - Procurement |
| Program Number: | 1160-04 |
| Month: | January 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program will offer the measures from the traditional part of the program as well as the measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program will allow synergies and efficiencies in the areas of administration, materials preparation, and communications to various market actors.  Included in the procurement-funded SFEER program are refrigerator rebates.

Activities/Accomplishments

- Launched the program in total on January 2, 2004.

- Completed an agreement with Howard's Appliances to provide instant rebates on up to 24,000 EnergyStar Refrigerators.

- Completed agreements with Lowe's and Costco to continue providing instant rebates on programmable thermostats.  An agreement with Home Depot is near completion.  Detailed discussions on expanding instant rebates to water heaters, whole house fans, and room air conditioners are continuing.

- The upstream lighting strategy was successfully rolled out in two components, the manufacturer (wholesale buy-down) component, and the retailer (retail mark-down) component.

- Lighting promotions were announced to lighting manufacturers and big-box statewide retailers, with sign-ups in late January.

- The manufacturer component of the upstream lighting strategy was designed to achieve the program’s hard-to-reach targets, rural ZIP codes, groceries, and drug stores early on.   Implementation for this component will occur during February through May 2004.

- As part of the upstream lighting strategy, the big-box retailers were offered the option to choose the mark-down or the manufacturer buy-down for a particular product.  Implementation for this component will occur during February through October.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

SCE filed updated Program Implementation Plans (PIP) for this program on February 2, 2004.

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Training

There were no activities beyond what may be described in the monthly reporting tables.

- Rebate and Direct Install Expenditure Adjustments

Due to actual incentives paid to customers are capped at maximum program rebate level or measures that are qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may be differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Marketing

There were no activities beyond what may be described in the monthly reporting tables.

- Additional Items

None