| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide CA Energy Star New Homes – Single Family, Multifamily Program - Procurement |
| Program Number: | 1169-04 |
| Month: | August 2005 |

- Program Status

Program Description

The California Energy Star® New Homes Program influences the design and construction of single family and multifamily residential new construction. Working together with single and multifamily builders, architects, energy analysts, and other building industry professionals, this program increases long term annual energy savings and coincident peak demand reduction that is achieved through a combination of education, design assistance and financial incentives. Single family and low-rise multifamily builder projects meeting the program requirements also meet the requirements of the U. S. Environmental Protection Agency (EPA) Energy Star Homes Program. (The EPA does not currently recognize high rise construction with the Energy Star label.)  SCE will again offer the high efficiency HVAC distributor buy-down program (“Buy-Down Program) in the 2004-05 program years.  SCE piloted this innovative program in the summer of 2001 and met with success.  This program will complement the CESNHP as well as capture energy savings and demand from those homes that have progressed in the construction process beyond the timely “point of entry” into CESNHP, and would otherwise become a lost opportunity for increased energy efficiency.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $6,139,345 | $64,411 | 1% | $548,385 | 9% | $3,490,880 | 57% | $4,039,265 | 66% | $5,590,960 |
| Admin | $371,800 | $1,426 | 0% | $63,868 | 17% |  |  | $63,868 | 17% | $307,932 |
| Marketing | $207,400 |  |  | $2,035 | 1% |  |  | $2,035 | 1% | $205,365 |
| DI | $5,420,800 | $62,139 | 1% | $475,504 | 9% | $3,490,880 | 64% | $3,966,384 | 73% | $4,945,296 |
| EM&V | $139,345 | $846 | 1% | $6,977 | 5% |  |  | $6,977 | 5% | $132,368 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Aug-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,235 | 119 | 1% | 523 | 6% | 6,666 | 72% | 7,189 | 78% | 8,713 |
| Annual kWh | 8,332,320 | 110,298 | 1% | 483,660 | 6% | 6,150,485 | 74% | 6,634,145 | 80% | 7,848,660 |
| Lifecyc kWh | 149,981,760 | 1,985,357 | 1% | 8,705,880 | 6% | 110,708,726 | 74% | 119,414,606 | 80% | 141,275,880 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- 2005 CESHNP Applications printed and in use:

  - 2005 Single Family Application

  - 2005 Multi-Family Low-Rise Application

  - 2005 Multi-Family High Rise Application

  - 2005 Multifamily Energy Consultant Application

  - 2005 HVAC Buy-Down Program Application

  - 2005 HVAC Buy-Down Program Fact Sheet

- In discussions with XXXXX, RNC’s third party HVAC Buy-Down program vendor, regarding potential problems with program participation, an important issue was addressed.  The current $200 incentive for a 13 SEER HVAC unit is considered a low motivator for distributor participation and does not necessarily offset the cost of the appliance and installation.  A $300 incentive is considered more favorable as it reasonably offsets appliance and installation costs.

- To promote and generate program success, SCE submitted to the CPUC a request for approval of changes to the incentives for the HVAC Buy-Down Program from $200 per unit to $300 per unit.   Effective July 27th, the CPUC approved the incentive increase to the end of 2005.

- To date, applications for over 400 units have been received

    - Marketing -

The 2005 HVAC Buy-Down Program Fact Sheet and the CESNHP brochure are now being utilized at builder tradeshows, meetings, and conferences.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measures | Installed in August 2005 | Paid & Committed |
| --- | --- | --- |
| SF Home 15% Inland | 82 | 2,230 |
| SF Home 20% Inland | 29 | 3,045 |
| MF Home 15% | 0 | 812 |
| SF Tier I | 0 | 425 |
| SF Tier II | 0 | 12 |
| MF Tier I | 0 | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

California’s Title 24 changes effective in October 2005.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The procurement-funded CA New Homes program underwent a fund shift in the month of December that transferred $600k from DI Incentives into the DI Incentives budget of the procurement-funded Single Family EE Rebates program.