| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Multifamily Energy Efficiency Rebate Program - Procurement |
| Program Number: | 1176-04 |
| Month: | June 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,191,126 | $496,890 | 6% | $967,754 | 12% | $490,112 | 6% | $1,457,866 | 18% | $7,223,372 |
| Admin | $166,400 | $21,775 | 13% | $21,775 | 13% |  |  | $21,775 | 13% | $144,625 |
| Marketing | $230,000 |  |  |  |  |  |  |  |  | $230,000 |
| DI | $7,603,600 | $475,116 | 6% | $945,980 | 12% | $490,112 | 6% | $1,436,091 | 19% | $6,657,620 |
| EM&V | $191,126 |  |  |  |  |  |  |  |  | $191,126 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 3,530 | 240 | 7% | 572 | 16% | 392 | 11% | 964 | 27% | 2,957 |
| Annual kWh | 29,513,699 | 1,863,273 | 6% | 4,059,263 | 14% | 2,905,642 | 10% | 6,964,905 | 24% | 25,454,437 |
| Lifecyc kWh | 302,665,579 | 23,130,196 | 8% | 46,315,594 | 15% | 27,991,524 | 9% | 74,307,118 | 25% | 256,349,985 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

- Finalized service forms and service policy for Duct Test & Seal services program component to be implemented in July 2004.

- Initiated purchase orders for the procurement and distribution of the fluorescent torchiere exchange program component to be implemented in August.

    - Marketing -

- MFEER program monthly advertisements implemented in three apartment association trade journals.

- The statewide MFEER program was represented at the Multifamily Trends conference in San Francisco, June 15, 2004.  Additionally, a statewide advertisement was placed in the conference’s magazine.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in June | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 10,868 | 64,278 |
| Fluorescent Fixtures | 8,284 | 19,503 |
| T8/T5 Fluorescent Lamps | 1,192 | 4,026 |
| Low E Windows | 0 | 2,644 |
| Prog. Thermostats | 306 | 1,369 |
| Heating/Cooling Sys. | 0 | 13 |
| Sensors | 4 | 7 |
| Package Terminal HP | 0 | 10 |
| Pool Pumps | 1 | 1 |
| LED Exit Signs | 90 | 90 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Negotiating with existing LIEE subcontractors to utilize extensive multifamily network for the delivery of fluorescent torchieres to apartment residents.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None