| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency Program - Procurement |
| Program Number: | 1178-04 |
| Month: | September 2004 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficiency. One of the program’s goals is to focus on providing small and medium-sized customers access to energy efficient technologies that had previously been adopted by larger customers. To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program.  Furthermore, the SCE will pursue opportunities to coordinate promotional activities with those of other, community based organizations.  Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,635,562 | $16,644 | 0% | $99,051 | 3% | $1,592,896 | 44% | $1,691,947 | 47% | $3,536,511 |
| Admin | $336,572 | $9,981 | 3% | $74,605 | 22% |  |  | $74,605 | 22% | $261,967 |
| Marketing | $272,500 | $4,684 | 2% | $22,468 | 8% |  |  | $22,468 | 8% | $250,032 |
| DI | $2,930,928 | $1,978 | 0% | $1,978 | 0% | $1,592,896 | 54% | $1,594,875 | 54% | $2,928,950 |
| EM&V | $95,562 |  |  |  |  |  |  |  |  | $95,562 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 10,000 | 423 | 4% | 423 | 4% | 6,116 | 61% | 6,538 | 65% | 9,577 |
| Annual kWh | 56,337,803 | 1,904,911 | 3% | 1,904,911 | 3% | 30,763,110 | 55% | 32,668,021 | 58% | 54,432,892 |
| Lifecyc kWh | 493,989,141 | 29,951,752 | 6% | 29,951,752 | 6% | 420,284,776 | 85% | 450,236,528 | 91% | 464,037,389 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Held bi-weekly telephone conferences with statewide team to discuss program implementation status, strategy, and issues.

- The statewide team is working on 2005 applications, and the team will advise the Energy Division of proposed measure changes.

- SCE completed processing and payment of outstanding 2003 applications as approved by the Energy Division.

- SCE suspended accepting new reservations and applications without existing reservations on September 17 due to the full commitment of incentive funds.  Additional funding has been identified and the program is expected to resume accepting new reservations by mid-October.

    - Marketing –

- Publishing of promotional flyers for CFL’s, T-8 florescent lamps, exit signs, occupancy sensors, refrigeration, and general energy efficiency tips for commercial customers has resumed.  Printing is expected to be completed in late September 2004.

- Reprinted 15,000 2004 SESM Rebate Flyers- Rebates Make It Easier.

- Energy auditors from SCE are now able to provide savings estimates for the installation of strip curtains and replacement of gaskets on walk in coolers and freezers using a PDA audit tool.  Customers receive a detailed printed report that estimates energy and cost savings and calculates available Express rebates.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in August) | Average Cost Per Site |
| --- | --- |
| 600 | $558 |

| Types of Measures Recommended | Measures Installed in September |
| --- | --- |
| Lighting | 19,703 |
| HVAC* | 207,233 |
| Refrigeration** | 321 |
| Food Service | 0 |
| Agricultural | 0 |

* Includes cool roofs and window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation –

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

There are labor charges that were made in error and will be reversed and charged to the PGC Express Efficiency program.