| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency Program - Procurement |
| Program Number: | 1178-04 |
| Month: | January 2005 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficiency. One of the program’s goals is to focus on providing small and medium-sized customers access to energy efficient technologies that had previously been adopted by larger customers. To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program.  Furthermore, the SCE will pursue opportunities to coordinate promotional activities with those of other, community based organizations.  Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,635,562 | $898,517 | 25% | $2,224,550 | 61% | $685,815 | 19% | $2,910,365 | 80% | $1,411,012 |
| Admin | $336,572 | $9,866 | 3% | $120,279 | 36% |  |  | $120,279 | 36% | $216,293 |
| Marketing | $272,500 | $4,817 | 2% | $28,971 | 11% |  |  | $28,971 | 11% | $243,529 |
| DI | $2,930,928 | $883,834 | 30% | $2,075,300 | 71% | $685,815 | 23% | $2,761,115 | 94% | $855,628 |
| EM&V | $95,562 |  |  |  |  |  |  |  |  | $95,562 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 10,000 | 3,565 | 36% | 7,877 | 79% | 3,407 | 34% | 11,284 | 113% | 2,123 |
| Annual kWh | 56,337,803 | 15,944,181 | 28% | 36,252,582 | 64% | 16,911,063 | 30% | 53,163,645 | 94% | 20,085,221 |
| Lifecyc kWh | 493,989,141 | 195,571,620 | 40% | 474,074,409 | 96% | 192,868,243 | 39% | 666,942,652 | 135% | 19,914,732 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Held bi-weekly telephone conferences with the statewide team to discuss program implementation status, performance, delivery strategy, and issues.

- The 2005 Express Efficiency program opened on January 2 with online applications available on SCE.com.  Printed applications were produced in January.

    - Marketing –

- No significant marketing efforts were initiated in the month of January.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in October) | Average Cost Per Site |
| --- | --- |
| 234 | $2,616 |

| Types of Measures Recommended | Measures Installed in January |
| --- | --- |
| Lighting | 101,929 |
| HVAC* | 20,317 |
| Refrigeration** | 175 |
| Food Service | 72 |
| Agricultural | 1,826 |

* Includes window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation –

Underpayments:

1.	(12) “LED Exit Signs”, less $5.40 per unit to account for the rebate amount in the program year 2003 being less than the rebate amount in the 2004/2005 program year.

Overpayments:

1.	(324) “Screw-in Compact Fluorescent Lamp, 14-26 watt” units installed, payment increased by $2.10 per unit to account for the rebate amount in the program year 2003 being more than the rebate amount in the 2004/2005 program year.

2.	(27) “Screw-in Compact Fluorescent Lamp, >=27 watt” units installed, payment was increased by $2.55 per unit to account for the rebate amount in the program year 2003 being more than the rebate amount in the 2004/2005 program year.

3.    (1220) “T-8 or T-5 Lamp and Electronic Ballast, 4 foot installed”, payment was increased by $2.55 per unit to account for the rebate amount in the program year 2003 being more than the rebate amount in the 2004/2005 program year.

Adjustments:

1.	Cost transfer for $295.45 for two payments mistakenly charged to incentive budget in January.

2.	Credit transfer for $200.00 for one payment mistakenly credited to incentive budget in January.

3.	Five customer payments were returned to SCE (Reference numbers 400095, 395721, 399949 and 400696) and cancelled/voided for a total of $13,409.70.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None