| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Upstream HVAC and Motors Rebates Program - Procurement |
| Program Number: | 1179-04 |
| Month: | May 2005 |

- Program Status

Program Description

The Upstream Motors and Air Conditioning program is a prescriptive rebate program that provides upstream financial incentives to distributors to stock and sell qualifying high efficiency products.  All incentives will be paid upstream.  No rebates will be offered to end users.  SCE’s commercial, industrial and agricultural customers are eligible to participate.  Program marketing will be targeted toward transmission-constrained and geographically hard to reach markets in order to maximize program benefits.  Both nonresidential retrofit and new construction applications qualify for the program, as this is an upstream program focused on changing distributors’ stocking practices to favor qualifying energy-efficient equipment. SCE’s customers from the smallest to the largest are eligible to receive the advantage of the upstream incentives.  Packaged air conditioning is used by small commercial customers; motors are used by all customer classes. Incentives are offered for high efficiency packaged and split system air conditioners, heat pumps, integral HVAC smart controls, package chillers, and motors. Depending on market response, additional measures may be added in the second year of the program (i.e., 2005).  The program is offered to customers within Southern California Edison’s (SCE) service territory and is part of both the Commercial and Industrial Hardware Incentive Programs described in SCE’s Long-Term Resource Plan Testimony.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $5,579,453 | $385,718 | 7% | $2,980,914 | 53% | $874,598 | 16% | $3,855,512 | 69% | $2,598,539 |
| Admin | $303,354 | $20,696 | 7% | $232,848 | 77% |  |  | $232,848 | 77% | $70,506 |
| Marketing | $661,500 | $99,282 | 15% | $241,973 | 37% |  |  | $241,973 | 37% | $419,527 |
| DI | $4,495,146 | $265,739 | 6% | $2,506,093 | 56% | $874,598 | 19% | $3,380,691 | 75% | $1,989,053 |
| EM&V | $119,453 |  |  |  |  |  |  |  |  | $119,453 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,655 | 523 | 6% | 5,297 | 61% | 2,361 | 27% | 7,657 | 88% | 3,358 |
| Annual kWh | 23,760,007 | 1,351,415 | 6% | 14,227,543 | 60% | 6,163,388 | 26% | 20,390,931 | 86% | 9,532,463 |
| Lifecyc kWh | 360,406,168 | 20,381,935 | 6% | 215,334,848 | 60% | 93,040,169 | 26% | 308,375,016 | 86% | 145,071,321 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- Significant strides have been made in processing checks to participating Distributors.

- The draft Program Policies and Procedures Manual is under review.

- The V2 (Phase II) on-line application system upgrades will help improve the existing processing and workflow. To be discussed at the statewide meeting on 6/23/05.

- Efforts have focused on finalizing the format for return data on rejected applications. Current Reject Reports are facilitating the communication process with distributors while reducing the reject levels.

    - Marketing –

- Continuing efforts to enroll major HVAC and motor distributors in SCE territory:

32 HVAC Distributors enrolled

85 Motors Distributors enrolled

- The “Top-10” distributor contact program, whereby the top 10 HVAC and motor distributors are contacted every two weeks (in person, e-mail or phone) has continued to be effective through the month of May. We will continue this level of contact into the future.

- Distributor contacts focus on ensuring that the existing up-selling tools are being distributed to sales staff and are helping to increase sales and determining how sales are shaping up for 2005 summer season.

- Results of the 2005 ACWA (Association of California Water Agencies) spring meeting on May 4 & 5 included the exposure to staff and managers of southern California water districts, engineers and designers of water systems as well as to contractors and equipment suppliers. Tangible results included the sale of three 200hp motors to water districts and an invitation to present the Upstream Program at a General Pump conference on June 16, 2005.

- Distributors continue to report that they are utilizing Upstream Program rebates to reduce the sales price of high-efficiency equipment, and are also using pricing to influence designer/contractor equipment selections.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

- Members of the Upstream Team met with the Kaman Regional VP and obtained a commitment to push premium motors in 2005.  The Kaman branches are able to use the rebate to lower the prices for key customers. A 5-step plan has been implemented to work with the Kaman branch offices and track the Kaman results. We have identified significant motor backlog from November 2004 to present.

- Members of the Upstream Team are working with the distributors to make sure that they have and are using the Motor Upselling Tools (XXXXX, XXXXX, XXXXX).

- Intervention Strategies have been developed to address motor market barriers like convincing customers to buy premium motors by tailoring motor manufacturer up-selling tools to the CA market, establishing goals and monitoring distributor performance for 2005, encouraging motor manufacturer involvement, and maximizing branch participation by encouraging distributors to establish an incentive program to motivate sales staff.

| Measures | Measures Installed in May | Committed |
| --- | --- | --- |
| HVAC | 3,645 | 10,999 |
| Motors | 75 | 299 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

There were 32 HVAC inspections completed during May, totaling 109 HVAC units. An additional full-time inspector was added, bringing the total inspectors to 2.  There do not appear to be any significant barriers with completing inspections.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The procurement-funded Upstream HVAC & Motors Rebates program underwent a fundshift in the month of September that transferred $500k from Direct Implementation Incentives into the Incentives budget of the procurement-funded Single Family EE Rebates program.