| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Upstream HVAC and Motors Rebates Program - Procurement |
| Program Number: | 1179-04 |
| Month: | November 2005 |

- Program Status

Program Description

The Upstream Motors and Air Conditioning program is a prescriptive rebate program that provides upstream financial incentives to distributors to stock and sell qualifying high efficiency products.  All incentives will be paid upstream.  No rebates will be offered to end users.  SCE’s commercial, industrial and agricultural customers are eligible to participate.  Program marketing will be targeted toward transmission-constrained and geographically hard to reach markets in order to maximize program benefits.  Both nonresidential retrofit and new construction applications qualify for the program, as this is an upstream program focused on changing distributors’ stocking practices to favor qualifying energy-efficient equipment. SCE’s customers from the smallest to the largest are eligible to receive the advantage of the upstream incentives.  Packaged air conditioning is used by small commercial customers; motors are used by all customer classes. Incentives are offered for high efficiency packaged and split system air conditioners, heat pumps, integral HVAC smart controls, package chillers, and motors. Depending on market response, additional measures may be added in the second year of the program (i.e., 2005).  The program is offered to customers within Southern California Edison’s (SCE) service territory and is part of both the Commercial and Industrial Hardware Incentive Programs described in SCE’s Long-Term Resource Plan Testimony.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $5,579,453 | $431,488 | 8% | $5,050,597 | 91% | $1,347,290 | 24% | $6,397,887 | 115% | $528,856 |
| Admin | $303,354 | $28,876 | 10% | $372,409 | 123% |  |  | $372,409 | 123% | -$69,055 |
| Marketing | $661,500 | $27,097 | 4% | $413,463 | 63% |  |  | $413,463 | 63% | $248,037 |
| DI | $4,495,146 | $375,515 | 8% | $4,264,725 | 95% | $1,347,290 | 30% | $5,612,015 | 125% | $230,421 |
| EM&V | $119,453 |  |  |  |  |  |  |  |  | $119,453 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,655 | 516 | 6% | 8,468 | 98% | 3,236 | 37% | 11,704 | 135% | 187 |
| Annual kWh | 23,760,007 | 1,428,043 | 6% | 22,958,804 | 97% | 8,229,432 | 35% | 31,188,236 | 131% | 801,203 |
| Lifecyc kWh | 360,406,168 | 21,720,366 | 6% | 347,755,925 | 96% | 123,916,854 | 34% | 471,672,778 | 131% | 12,650,244 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- Significant strides have been made in processing checks to participating Distributors.

- The V2 (Phase II) on-line application system upgrades will help improve the existing processing and workflow.  Technical specifications are being addressed.

- Current Reject Reports are facilitating the communication process with distributors while reducing the reject levels.

    - Marketing –

- Continuing efforts to enroll major HVAC and motor distributors in SCE territory:

35 HVAC Distributors enrolled

86 Motors Distributors enrolled

- The “Top-10” distributor contact program, whereby the top 10 HVAC and motor distributors are contacted every two weeks (in person, e-mail or phone) has continued to be effective through the month of September. We will continue this level of contact into the future.

- Distributors continue to report that they are utilizing Upstream Program rebates to reduce the sales price of high-efficiency equipment, and are also using pricing to influence designer/contractor equipment selections.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

- Members of the Upstream Team are working with the distributors to make sure that they have and are using the Motor Upselling Tools (XXXXX, XXXXX, XXXXX).

- Intervention Strategies have been developed to address motor market barriers like convincing customers to buy premium motors by tailoring motor manufacturer up-selling tools to the CA market, establishing goals and monitoring distributor performance for 2005, encouraging motor manufacturer involvement, and maximizing branch participation by encouraging distributors to establish an incentive program to motivate sales staff.

| Measures | Measures Installed in October | Total Measures Committed |
| --- | --- | --- |
| HVAC | 2,287 | 16,478 |
| Motors | 73 | 337 |

      - Calculated and Actual Payment Reconciliation -

In the month of November 2005, financial incentives in the amount of $274,180 (Tab 1A), Direct Implementation Section) were paid to customers.  “Tab 2A – RecordedEEActivities” calculates that $200,895 in financial incentives should have been paid to customers.  The difference was the result of the delay in status changing committed projects to paid projects. The update will appear in December’s report.

    - EM&V

There were 79 HVAC inspections completed during November-. There are two full-time inspectors.  There do not appear to be any significant barriers with completing inspections.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The procurement-funded Upstream HVAC & Motors Rebates program underwent a fundshift in the month of September that transferred $500k from Direct Implementation Incentives into the Incentives budget of the procurement-funded Single Family EE Rebates program.