| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Innovative Designs for Energy Efficiency Activities - Procurement |
| Program Number: | 1185-04 |
| Month: | October 2004 |

- Program Status

Program Description

SCE’s Innovative Designs for Energy Efficiency Activities (IDEEA) program is a competitive bidding solicitation of innovative and cost-effective energy efficiency program proposals across all market and customer segments, funded by energy procurement funds.   The focus will be on different marketing or delivery methods, different market segments, and/or different technologies than those offered in the SCE portfolio.  Winning proposals will fill possible gaps in the overall portfolio of programs offered in SCE’s service territory or offer best practices not incorporated in similar programs in the portfolio.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,528,690 | $12,698 | 0% | $101,797 | 1% |  |  | $101,797 | 1% | $12,426,893 |
| Admin | $490,600 | $12,698 | 3% | $101,797 | 21% |  |  | $101,797 | 21% | $388,803 |
| Marketing | $5,000 |  |  |  |  |  |  |  |  | $5,000 |
| DI | $11,104,400 |  |  |  |  |  |  |  |  | $11,104,400 |
| EM&V | $928,690 |  |  |  |  |  |  |  |  | $928,690 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

Energy savings from this program will depend on the programs offered and selected. The component program request for proposals is scheduled for release August 16, 2004.

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goal | Cumulative | % of Goal | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Telephone calls and e-mails to appropriate contact people at potential bidder entities. | 80 | 0 | 0% | 513 | 641% | 0 | 0% | 513 | 641% | 0 |

  - Activities/Accomplishments

    - Administrative -

- Program RFP Round I Stage 2 proposals were received, reviewed, evaluated and scored.

- Nine Round I Stage 2 proposals were selected to move forward to the Bid Clarification Stage.

    - Marketing –

The IDEEA Program Web page on the http://www.sce.com Web site (http://www.sce.com/sc3/005_regul_info/005d_eff_filings/IDEEA-RFP.htm) was updated.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

A Request for Proposals has been written.  In its June 30, 2004 filing on selected EM&V contractors, SCE requested permission from the Energy Division to defer release of this RFP and selection of an EM&V contractor until the IDEEA programs have been selected.  This will allow EM&V contractors to assemble a team most suitable to evaluate the IDEEA programs that are chosen and to write a specific rather than very vague EM&V plan for Energy Division review.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

No changes from plan.

- Additional Items

XXXXX and XXXXX worked on the RFP process and charged labor dollars to the IDEEA program.  However, Tab 8 of the workbook continues to reflect the positions that SCE will hire to work on the program on a permanent basis.