| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Residential Appliance Recycling Program - PGC |
| Program Number: | 1232-04 |
| Month: | September 2004 |

- Program Status

Program Description

The Statewide Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.  The program is offered to customers within the investor-owned utilities’ (IOUs) service territories of Pacific Gas and Electric (PG&E), Southern California Edison (SCE), and San Diego Gas & Electric (SDG&E).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,322,000 | $1,077,527 | 9% | $2,887,801 | 23% | $1,685,720 | 14% | $4,573,521 | 37% | $9,434,199 |
| Admin | $912,728 | $35,914 | 4% | $324,905 | 36% |  |  | $324,905 | 36% | $587,824 |
| Marketing | $220,000 |  |  | $77,629 | 35% |  |  | $77,629 | 35% | $142,371 |
| DI | $10,867,272 | $1,041,613 | 10% | $2,485,267 | 23% | $1,685,720 | 16% | $4,170,987 | 38% | $8,382,005 |
| EM&V | $322,000 |  |  |  |  |  |  |  |  | $322,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,514 | 948 | 10% | 2,237 | 24% | 1,518 | 16% | 3,756 | 39% | 7,276 |
| Annual kWh | 55,670,889 | 5,506,353 | 10% | 13,019,662 | 23% | 8,840,444 | 16% | 21,860,107 | 39% | 42,651,227 |
| Lifecyc kWh | 334,025,336 | 33,038,120 | 10% | 78,117,975 | 23% | 53,042,664 | 16% | 131,160,639 | 39% | 255,907,361 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Encourage program participation from the "hard-to-reach" (HTR) customer segment as defined by the CPUC in the Energyb Policy Manual | 57% of all customer participation | 0% | n/a | 52% | n/a | 0% | n/a | 52% | n/a |  |

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process will be performed monthly and the results of each inspection will be tabulated and kept on file.

- SCE Project Manager conducted 2 ride alongs (September 23 & 30) with the recycling contractor appliance pick up drivers to gain a better understanding of customer issues and program challenges.

- The SCE Project Manager held a meeting with appliance recycling contractor personnel to emphasize the importance in adhering to the program restrictions (appliance size and age).  Significant progress has been made by both SCE and the contractor to augment operational procedures to ensure program compliance.

- SCE continues to await a final resolution to their Petition to Modify Decision 03-12-060 filed in May 2004 regarding the new age restriction on refrigerators and freezers.

    - Marketing -

- Radio spots on LA-based radio stations and local Spanish speaking radio stations continued into September.

- Completed an “e-mail blast” to approximately 96K SCE customers (both HTR and non HTR).

- Placed Free Standing Inserts (FSIs) in major newspapers distributed throughout the SCE service territory with a total circulation in excess of 4.6 million.

- Completed the installation of advertising panels on all appliance recycling contractor trucks to serve as promotional mobile billboards.

- Continued to promote RARP through POP materials strategically positioned in the appliance retail stores located in the SCE service territory.

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

- Exploring new opportunities to promote RARP through the use of short video ads (15 sec. spots) placed on theater screens prior to the showing of movies.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in September |
| --- | --- |
| Refrigerators | 6,863 |
| Freezers | 927 |

      - Calculated and Actual Payment Reconciliation -

The calculated rebate amount shown in the program’s corresponding workbook does not reflect the cost to pick-up and recycle the refrigerator/freezer.

    - EM&V

None

- Program Challenges

- Since July 1, the contractor has handled many customer calls that have resulted in denials for pick up appointments due to the new age restriction on refrigerators and freezers.  As of September 30, over 2,500 customers have been rejected over the phone due to the new age restriction. These rejections do not take into consideration those customers who knew their unit did not qualify and, therefore, did not call at all.

- Some customers have been denied participation at the time of pick up due to the new age restriction.  In these cases, the driver verified age by finding the manufacturers label which the customer could not find when scheduling the appointment. This has resulted in an increase in customer complaints.

- Due to a lack of industry standard on identifying the age of manufacture on refrigerators and freezers, it is very difficult and, in some instances, impossible to verify the specific age of manufacture on all units turned in through the program.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which requires that all refrigerators and freezers be manufactured prior to 1990.

- Coordination Activities

- Established a link for Spanish speaking customers to schedule pick up appointments online through the SCE.com web site.

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Radio spots continued on LA-based stations and the local Spanish speaking stations  into September 2004.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None