| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Residential Appliance Recycling Program - PGC |
| Program Number: | 1232-04 |
| Month: | January 2005 |

- Program Status

Program Description

The Statewide Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.  The program is offered to customers within the investor-owned utilities’ (IOUs) service territories of Pacific Gas and Electric (PG&E), Southern California Edison (SCE), and San Diego Gas & Electric (SDG&E).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,322,000 | $38,688 | 0% | $5,574,009 | 45% | $579,148 | 5% | $6,153,157 | 50% | $6,747,991 |
| Admin | $912,728 | $26,400 | 3% | $459,496 | 50% |  |  | $459,496 | 50% | $453,232 |
| Marketing | $220,000 |  |  | $110,962 | 50% |  |  | $110,962 | 50% | $109,038 |
| DI | $10,867,272 | $12,289 | 0% | $5,003,551 | 46% | $579,148 | 5% | $5,582,699 | 51% | $5,863,721 |
| EM&V | $322,000 |  |  |  |  |  |  |  |  | $322,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,514 |  |  | 4,511 | 47% | 522 | 5% | 5,033 | 53% | 5,003 |
| Annual kWh | 55,670,889 |  |  | 26,220,164 | 47% | 3,040,436 | 5% | 29,260,600 | 53% | 29,450,726 |
| Lifecyc kWh | 334,025,336 |  |  | 157,320,982 | 47% | 18,242,616 | 5% | 175,563,599 | 53% | 176,704,354 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Encourage program participation from the "hard-to-reach" (HTR) customer segment as defined by the CPUC in the Energyb Policy Manual | 57% of all customer participation | 0% | n/a | 51% | n/a | 0% | n/a | 51% | n/a |  |

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

- SCE continues to await a final resolution to their Petition to Modify Decision 03-12-060 filed in May 2004 regarding the new age restriction on refrigerators and freezers. The program’s new refrigerator/freezer age restriction has significantly impacted the program’s ability to reach its targets. See Program Challenges below for more specific information as it relates to the impact on the program.

- A meeting was held with various SCE and recycling contractor representatives to review the 2004 program year and to discuss 2005 program plans (marketing) and proposed program changes/enhancements.  These included enhancements to the online scheduling capabilities, improved tracking of customer incentive checks, improved contract compliance reporting and the potential to add measures (Room A/C Recycling) to the RARP portfolio for 2006 and beyond.

    - Marketing -

- Continued to promote RARP using POP materials strategically positioned in the appliance retail stores located throughout the SCE service territory.  In January, placed new materials or replenished existing materials at 223 stores.

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in January |
| --- | --- |
| Refrigerators | 0 |
| Freezers | 0 |

      - Calculated and Actual Payment Reconciliation -

The calculated rebate amount shown in the program’s corresponding workbook does not reflect the cost to pick-up and recycle the refrigerator/freezer.

    - EM&V

By approval of the Energy Division staff and its evaluation consultants, one portion of the 2004-5 EM&V is moving ahead in advance of the remainder of the study.  Work is now underway to meter two samples of refrigerators recycled through the program.  One sample is metered under controlled Department of Energy testing procedures, and the other sample is metered at the sites from which the refrigerators are to be collected.  The RFP for the remainder of the study is in the process of development.

- Program Challenges

- The contractor has handled many customer calls that have resulted in rejections for pick up appointments due to the new age restriction on refrigerators and freezers.  Through January 31, 2005 close to 5,000 customers were rejected over the phone due to the new age restriction. These rejections do not take into consideration those customers who knew their unit did not qualify (by reviewing program literature or the web site) and, therefore, did not call or sign up over the Internet to schedule a pick up appointment.

- Since using the drivers to verify the age of units at the time of pick up, 124 customers have been denied participation in the program.  In these cases, the driver verifies the unit age by finding the manufacturers label which the customer could not find when scheduling the appointment. This has resulted in an increase in customer complaints and recycling contractor costs.

- Due to a lack of industry standard on identifying the age of manufacture on refrigerators and freezers, it is very difficult and, in some instances, impossible to verify the specific age of manufacture on all units turned in through the program.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which requires that all refrigerators and freezers be manufactured prior to 1990.

Conducting random on-site inspections at the contractor’s recycling facility, ride alongs with recycling contractor drivers, and customer surveys to verify customer participation and ensure program compliance.

- Coordination Activities

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

The PGC-funded Appliance Recycling program underwent a fundshift in December that transferred $350k from DI Incentives to the DI Incentives budget of the PGC-funded Single Family EE Rebates program.