| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Residential Appliance Recycling Program - PGC |
| Program Number: | 1232-04 |
| Month: | January 2004 |

- Program Status

Program Description

The Statewide Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.  The program is offered to customers within the investor-owned utilities’ (IOUs) service territories of Pacific Gas and Electric (PG&E), Southern California Edison (SCE), and San Diego Gas & Electric (SDG&E).

Activities/Accomplishments

- Executed the 2004-05 Residential Appliance Recycling Agreement (RARP) Agreement and Purchase Order with XXXXX (recycling services vendor).

- Updated the SCE RARP web site to incorporate the changes to the program and developed/scheduled a bill message to appear in the February SCE billing cycle.

- Initiated the design and development of new marketing literature to include information on the increased energy savings associated with older, spare units and information on the new program restrictions regarding the age of refrigerators and freezers (effective July 1, 2004).

- Held discussions with the Energy Division to finalize specific guidelines and timelines for RARP and submitted a revised Program Implementation Plan (PIP) based on these discussions.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

SCE submitted updated Program Implementation Plans (PIP) to the CPUC’s Energy Division on February 2, 2004.  On February 26, 2004, SCE submitted revision on the updated PIP to the CPUC.

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Training

There were no activities beyond what may be described in the monthly reporting tables.

- Rebate and Direct Install Expenditure Adjustments

Due to actual incentives paid to customers are capped at maximum program rebate level or measures that are qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may be differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Marketing

There were no activities beyond what may be described in the monthly reporting tables.

- Additional Items

None