| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Single Family Energy Efficiency Rebates Program - PGC |
| Program Number: | 1234-04 |
| Month: | April 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,437,999 | $539,619 | 5% | $1,238,188 | 12% | $989,722 | 9% | $2,227,910 | 21% | $9,199,811 |
| Admin | $2,149,125 | $69,023 | 3% | $296,714 | 14% |  |  | $296,714 | 14% | $1,852,411 |
| Marketing | $594,000 | $24,422 | 4% | $48,584 | 8% |  |  | $48,584 | 8% | $545,416 |
| DI | $7,256,874 | $446,175 | 6% | $892,890 | 12% | $989,722 | 14% | $1,882,612 | 26% | $6,363,984 |
| EM&V | $438,000 |  |  |  |  |  |  |  |  | $438,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 21,969 | 1,859 | 8% | 2,798 | 13% | 3,875 | 18% | 6,673 | 30% | 19,171 |
| Annual kWh | 74,664,923 | 7,265,032 | 10% | 8,396,591 | 11% | 24,554,401 | 33% | 32,950,992 | 44% | 66,268,332 |
| Lifecyc kWh | 815,046,340 | 70,694,629 | 9% | 87,499,922 | 11% | 272,087,595 | 33% | 359,587,517 | 44% | 727,546,418 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Single Family Rebate Program Hard-To-Reach: Achieve 34% of the program's applications from zip codes designated as hard-to-reach | 34% | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |
| 15% of Incentives to go to geographical HTR areas outside L.A. Basin. | 15% | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |
| 10% of Incentives to go to customers through grocery or drug retailers. | 10% | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Continued discussions with Home Depot regarding the expansion of point-of-sale rebates to include Room Air Conditioners.

- Posted programmable thermostat materials in all Home Depot stores for point-of-sale delivery of this measure.

- Fully implemented point-of-sale rebates for programmable thermostats at Lowe’s Home Improvement Center.

- Began discussions with Lowe’s for the implementation of point-of-sale rebates for both room air conditioners and electric water heaters.

- Completed lighting promotion initial allocations.

- The Summer/Fall lighting promotion began on April 15, 2004.

- Initial lighting allocations were set at target achievement levels

- Earth Day promotions took place with two grocery retailers, covering 8 locations.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Measures Installed in April |
| --- | --- |
| Pool Measures | 492 |
| Room ACs | 16 |
| Electric Water Heaters | 4 |
| Programmable Thermostats | 1,365 |
| Attic Insulation | 1,950 |
| Whole House Fan | 236 |
| Evaporative Coolers | 156 |
| HVAC | 140 |
| Lighting Measures | 106,284 |

      - Calculated and Actual Payment Reconciliation -

There were three incorrect charges that resulted in a discrepancy between the financial incentives paid in Tab 1A – Expenditures Worksheet and the calculated financial incentives in Tab 2A – Recorded EE Activities Worksheet.  1) Three Desert A/C units were incorrectly processed and paid with PGC funds instead of Procurement funds resulting in an overcharge of $600, 2) A processing error resulted in an over payment of $20 for one programmable thermostat, 3) IT costs were incorrectly charged to the incentive function number in the amount of $1,302.23.  The discrepancy is being corrected and will be accurately reflected in next month’s report.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None