| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Single Family Energy Efficiency Rebates Program - PGC |
| Program Number: | 1234-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $15,009,392 | $87,433 | 1% | $4,818,605 | 32% | $244,200 | 2% | $5,062,805 | 34% | $10,190,787 |
| Admin | $2,149,126 | $35,230 | 2% | $747,430 | 35% |  |  | $747,430 | 35% | $1,401,696 |
| Marketing | $594,000 | $3,053 | 1% | $208,818 | 35% |  |  | $208,818 | 35% | $385,182 |
| DI | $11,828,266 | $49,149 | 0% | $3,862,357 | 33% | $244,200 | 2% | $4,106,557 | 35% | $7,965,909 |
| EM&V | $438,000 |  |  |  |  |  |  |  |  | $438,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 31,517 | 12 | 0% | 12,705 | 40% | 910 | 3% | 13,615 | 43% | 18,812 |
| Annual kWh | 158,297,755 | 12,272 | 0% | 46,081,004 | 29% | 8,041,174 | 5% | 54,122,178 | 34% | 112,216,752 |
| Lifecyc kWh | 2,005,035,882 | 232,338 | 0% | 503,567,363 | 25% | 97,193,104 | 5% | 600,760,466 | 30% | 1,501,468,519 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Single Family Rebate Program Hard-To-Reach: Achieve 34% of the program's applications from zip codes designated as hard-to-reach | 34% |  | n/a | 41% | n/a | 0% | n/a | 41% | n/a |  |
| Lighting: 15% of Incentives to go to geographical HTR areas outside L.A. Basin. | 15% |  | n/a | 30% | n/a | 0% | n/a | 30% | n/a |  |
| Lighting: 10% of Incentives to go to customers through grocery or drug retailers. | 10% |  | n/a | 34.4% | n/a | 0% | n/a | 34.4% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Program has achieved its goals for 2004.  The program is in the process of transitioning completely over to procurement.

- All original annual PGC lighting targets were achieved in September. $200,000 was transferred from the administrative budgets and $167,000 from another program to lighting incentives for the November lighting season.  Targets were raised commensurately.  Efforts are underway to determine if any budgeted administrative funds should be shifted to lighting incentives, or otherwise go unspent in December based on unforeseen administrative efficiencies.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Measures Installed in November |
| --- | --- |
| Pool Pump | 13 |
| Room ACs | 0 |
| Electric Water Heaters | 4 |
| High Performance Windows | 199 |
| Programmable Thermostats | 6 |
| Wall Insulation | 0 |
| Whole House Fans | 0 |
| Evaporative Coolers | 0 |
| HVAC | 10 |
| Lighting Measures | 62,820 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

The EM&V activity is being done as a supplement to the 2004-05 EM&V study of statewide Single Family Energy Efficiency Rebate program that is being managed by PG&E.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The PGC-funded Singlefamily EE Rebates program underwent a fundshift in the month of October that took $80k from Administrative, $30k from Marketing, and $90k from Direct Implementation and put it into the Incentives budget.