| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | July 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,969 | $56,999 | 1% | $687,887 | 16% | $728,203 | 17% | $1,416,090 | 33% | $3,548,581 |
| Admin | $563,300 | $27,258 | 5% | $163,959 | 29% |  |  | $163,959 | 29% | $398,841 |
| Marketing | $88,800 | $14,314 | 16% | $24,313 | 27% |  |  | $24,313 | 27% | $64,487 |
| DI | $3,347,900 | $15,427 | 0% | $499,615 | 15% | $728,203 | 22% | $1,227,818 | 37% | $2,848,285 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 |  |  | 279 | 14% | 520 | 26% | 799 | 39% | 1,758 |
| Annual kWh | 12,111,695 |  |  | 1,991,611 | 16% | 2,814,289 | 23% | 4,805,900 | 40% | 10,120,084 |
| Lifecyc kWh | 139,723,639 |  |  | 21,038,642 | 15% | 33,106,828 | 24% | 54,145,469 | 39% | 118,684,997 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The HTR target is to have 36 percent of all rebate applications come from HTR customers. | 36% | 63% | n/a | 63% | n/a | 0% | n/a | 63% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

    - Marketing -

- MFEER program monthly advertisements submitted to a fourth monthly journal that is sent to all property owners and managers in the circulations service area to be published in August.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in July1 | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 0 | 30,895 |
| Fluorescent Fixtures | 0 | 16,930 |
| T8/T5 Lamps | 0 | 4,746 |
| Low E Windows | 0 | 4,975 sq ft. |
| Prog. Thermostats | 0 | 1,324 |
| Sensors | 0 | 25 |
| Exit Signs | 0 | 78 |
| Ceiling Fans | 0 | 37 |
| Room A/Cs | 0 | 36 |
| Package Terminal HP | 0 | 5 |

1 System constraints required a temporary accounting distribution adjustment resulting in all program measures being assigned to the Procurement budget in July.  The system has been corrected and necessary adjustments will be shown in August’s report.

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None