| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,969 | -$178,787 | -4% | $3,672,397 | 87% |  |  | $3,672,397 | 87% | $564,572 |
| Admin | $563,300 | $29,016 | 5% | $507,312 | 90% |  |  | $507,312 | 90% | $55,988 |
| Marketing | $88,800 | $670 | 1% | $29,304 | 33% |  |  | $29,304 | 33% | $59,496 |
| DI | $3,347,900 | -$208,472 | -6% | $3,135,781 | 94% |  |  | $3,135,781 | 94% | $212,119 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 | -34 | -2% | 2,085 | 102% |  |  | 2,085 | 102% | -49 |
| Annual kWh | 12,111,695 | -260,462 | -2% | 12,988,620 | 107% |  |  | 12,988,620 | 107% | -876,925 |
| Lifecyc kWh | 139,723,639 | -3,937,296 | -3% | 144,450,518 | 103% |  |  | 144,450,518 | 103% | -4,726,879 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The HTR target is to have 36 percent of all rebate applications come from HTR customers. | 36% |  | n/a | 55% | n/a |  | n/a | 55% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2005 program year.

- As of March 2005, the MFEER program met the two-year energy and demand savings targets based on cumulative and committed figures.

    - Marketing -

- Ongoing advertisements in four monthly publications sent directly to apartment owners and managers.

- Exhibitor at two apartment association trade shows.  Attendees were property owners and managers and industry vendors.  Roughly 5,000 attendees between the two shows. These trade shows hold a special opportunity to meet with past and current MFEER program customers and receive their feedback on their program experience.  Exhibiting at the trade shows also presents the valuable opportunity to present program offerings to customers not yet aware of the MFEER program.  And finally, our presence helps solidify leveraged vendor relationships within the multifamily industry.

- The MFEER program manager met with a major property management firm in regards to a sizeable retrofit project currently in progress.  The program manager needed to go on-site with the company’s project manager to assess product eligibility and to suggest ways to participate in the program of this multi-phased project.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in September | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 0 | 92,536 |
| Fluorescent Fixtures | 0 | 35,327 |
| T8/T5 Lamps | 0 | 15,288 |
| Low E Windows | 0 | 7,430 sq ft. |
| Prog. Thermostats | 0 | 6,842 |
| Exit Signs | 0 | 449 |
| Room A/Cs | 0 | 55 |
| Ceiling Fan | 0 | 5 |
| Central HVAC/HP | 0 | 6 |
| Photocells/Sensors | 0 | 2 |
| Showerheads | 0 | 6 |
| Faucet Aerators | 0 | 12 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.  In September, there were  minor post-period adjustments made which are reflected in the current figures.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Throughout the program term, MFEER program management has leveraged new and existing industry relationships with various market actors such as vendors, associations, installation contractors, SCE account executives and the like.  This vital network of vested parties helps ensure program awareness and participation in the multifamily sector.

Demonstrating the effectiveness of coordinating with market actors, in August, MFEER program management met with a large property management company owning and managing roughly 30,000 dwelling units in Orange County through the efforts of an independent contractor and a manufacturer in establishing a meeting of all parties.  As a result of this meeting, this customer has decided to retrofit all units with fluorescent technology as opposed to incandescent lighting over the next two to three years.

In September, MFEER management met with another major property management firm, providing direct assistance for program participation during a sizeable retrofit project.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None