| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | October 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,969 | $87,832 | 2% | $1,068,577 | 25% | $686,284 | 16% | $1,754,861 | 41% | $3,167,892 |
| Admin | $563,300 | $27,161 | 5% | $252,253 | 45% |  |  | $252,253 | 45% | $310,547 |
| Marketing | $88,800 |  |  | $26,563 | 30% |  |  | $26,563 | 30% | $62,237 |
| DI | $3,347,900 | $60,671 | 2% | $789,760 | 24% | $686,284 | 20% | $1,476,045 | 44% | $2,558,140 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 | 16 | 1% | 446 | 22% | 411 | 20% | 858 | 42% | 1,590 |
| Annual kWh | 12,111,695 | 164,130 | 1% | 2,883,215 | 24% | 2,602,471 | 21% | 5,485,687 | 45% | 9,228,480 |
| Lifecyc kWh | 139,723,639 | 1,693,223 | 1% | 32,909,941 | 24% | 30,696,712 | 22% | 63,606,652 | 46% | 106,813,698 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The HTR target is to have 36 percent of all rebate applications come from HTR customers. | 36% |  | n/a | 63% | n/a | 0% | n/a | 63% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

- Within the SCE service territory, there are several independent lighting installation contractors participating with their customers through the MFEER program.  Since the beginning of 2004, the MFEER program has seen a marked increase in the number of these installation contractors.  From a core of roughly ten contractors participating in previous years, there are now roughly 45 private installation contractors now involving their customers in the MFEER program.

- The year 2004 has also seen a marked increase in the number of property managers and owners initiating rebate requests without prompting of a private installation contractor.  MFEER program awareness has increased significantly in this targeted customer segment as illustrated by roughly a  four-fold increase in the number of self-initiated rebate requests from property owners and managers.

- Statewide MF Team met in San Francisco, October 11th, to synchronize on-going program implementation into 2005.  Also, reviewed program refinement items and planned topics and agendas to discuss and present the planned participating contractors meeting to be held November 15th in San Francisco.

    - Marketing -

- Ongoing advertisements in four monthly publications sent directly to apartment owners and managers.

- Presentation of MFEER program given at the Apartment Association of Orange County’s “Nights of the Roundtable” meeting October 19th.

- Mailed promotional postcard to over 30,000 apartment managers and/or owner accounts promoting the energy savings of CFLs.  This is the third consecutive year of promoting CFL savings coincident with the setting of the clocks back to standard time and the on-set of longer night-time hours.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in October | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 1,326 | 34,719 |
| Fluorescent Fixtures | 973 | 19,218 |
| T8/T5 Lamps | 0 | 5,713 |
| Low E Windows | 0 | 3,235 sq ft. |
| Prog. Thermostats | 16 | 2,474 |
| Exit Signs | 21 | 236 |
| Ceiling Fans | 5 | 5 |
| Room A/Cs | 0 | 63 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None