| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | June 2005 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $63,802 | 2% | $1,809,637 | 58% |  |  | $1,809,637 | 58% | $1,318,743 |
| Admin | $532,446 | $15,063 | 3% | $393,090 | 74% |  |  | $393,090 | 74% | $139,356 |
| Marketing | $538,000 | $1,134 | 0% | $305,216 | 57% |  |  | $305,216 | 57% | $232,784 |
| DI | $1,929,554 | $47,604 | 2% | $1,111,331 | 58% |  |  | $1,111,331 | 58% | $818,223 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 27,000 | 3,737 | 13.8% | 31,263 | 115.8% | 0 | 0% | 31,263 | 115.8% | 0 |
| On-Line Energy Surveys | 18,000 | 2,522 | 14.0% | 15,850 | 88.1% | 0 | 0% | 15,850 | 88.1% | 2,150 |
| In-Home Energy Surveys | 8,000 | 220 | 2.8% | 5,824 | 72.8% | 0 | 0% | 5,824 | 72.8% | 2,176 |
| Telephone Energy Surveys | 1,000 | 20 | 2.0% | 831 | 83.1% | 0 | 0% | 831 | 83.1% | 169 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 78% |  | 78% |  | n/a |  | 78% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved processing of 3,737 mail-in surveys.  This brings program total to 31,263 completed and processed surveys in the 2004-2005 program year.  Of these completed surveys, 1,457 were completed and processed in Spanish, 2,455 in Chinese, and 327 in Vietnamese.

- Updated saving recommendations with changes to the incentive amounts and the elimination of the age restriction for the refrigerator/freezer recycling program.

- Continue to work with Asian Pacific American Community Service Center, a local community-based organization, to promote the program to the Chinese- and Vietnamese-speaking communities.  This collaboration achieved 500 Chinese and 300 Vietnamese completed surveys.

- Completed work with Resource Action Programs to target sixth grade classrooms by distributing the LivingWise® activities kits containing electric and water measures.  The pilot program distributed over 3,000 kits to South Bay elementary and Torrance middle schools’ students.  Each kit includes a survey for completion by the student’s parents.  This pilot generated over 100 completed surveys.

- Finalized translations of the survey packages from English to Korean.

- Scheduled mailing of Spanish, Vietnamese, Chinese and Korean surveys in 3rd quarter.

On-Line Survey

- Achieved processing of 2,522 on-line surveys.  This brings program total to 16,175 completed and processed surveys in the 2004-2005 program year.  Of the completed surveys, 64 took the survey in Spanish and 94 took the survey in Chinese.

- Continue to run the Target GiftCard marketing campaign to increase survey participation.  Eligible SCE customer will receive a $5 Target Giftcard when they complete the survey online.  Campaign sent out over 350,000 English e-mails to L.A. Times subscribers.  There were over 3,600,000 English on-line banner ads appeared in AOL Network, Tribal Fusion and L.A. Newsgroup.  There were also about 250,000 Chinese and 200,000 Spanish on-line banner ads appeared in Sina.com and Terra.com.

- Enhanced survey site to collaborate with SCE’s 20/20 Summer Savings Program.  SCE is encouraging customers to practice greater energy conservation during the summer to help maintain a stable electrical supply.  Qualifying residential and commercial customers will save by using 20% less and SCE will give a 20% credit on the first winter bill.  The enhancements provide last summer’s usage, and tips to save energy during this year’s hot summer months.  Customers are able to click on the links provided in the survey results, and be instantly connected to 20/20 web site to obtain more information.

- Updated saving recommendations with changes to the incentive amounts and the elimination of the age restriction for the refrigerator/freezer recycling program.

- Continue planning for development of the Vietnamese on-line interactive survey to be launched in 3rd quarter.

In-Home Survey

- Achieved 240 completed surveys.  This brings program total to 6,655 surveys conducted in the 2004-2005 program year.  Of these completed surveys, 1,526 surveys (23%) were conducted in Spanish.  Of these completed surveys, 5,201 customers (78%) are defined by the Energy Efficiency Policy Manual as in hard-to-reach segments.

- Completed 108 SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  This brings total joint surveys conducted to 1,124 surveys in the 2004-2005 program year.

- Scheduled mailing of 50,000 solicitation cards to customers in San Bernardino and Coachella valley areas.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 31,263 Mail-In Surveys | $12.30 | Same |
| 16,175 On-Line Surveys | $11.31 | Same |
| 5,824 In-Home Surveys | $81.81 | $91.46 |
| 831 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January 2004 through June 2005, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August as a result of the competitive bid issued in May 2004.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Continue to participate in the 2006-2008 HEES program planning process, and coordinate program planning with the statewide team members in SoCalGas, PG&E and SDG&E.

- Continue to work with the statewide team in soliciting ideas for 2006-2008 program year and draft statement of work, Request for Information and Request for Proposal.

- Mail-In Survey

  - Continue to promote the appliance recycling program by inserting a brochure with all survey packages and energy report mailed.

- On-Line Survey

  - Continue to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

  - Enhanced survey site to collaborate with SCE’s 20/20 Summer Savings Program.  Customers are able to click on the links provided in the survey results, and be instantly connected to 20/20 web site to obtain more information.

- In-Home Survey

  - Provide all survey participants with a bilingual 20/20 Summer Savings Program flyer to encourage customers to save energy this summer.  Energy auditors also provide information on increase incentive amounts and elimination of age restriction of refrigerator and freezer recycling program.

  - Continue the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Provided contractor with new program offerings, rebates applications, and rate increase information, in order to answer customers’ inquiries.

  - Continue to provide customers with two CFLs after completion of the survey, for immediate energy savings.

  - Continue to provide survey contractor with CARE applications for the low- and moderate-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None