| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | February 2005 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $88,383 | 3% | $1,284,930 | 41% |  |  | $1,284,930 | 41% | $1,843,450 |
| Admin | $532,446 | $17,373 | 3% | $287,819 | 54% |  |  | $287,819 | 54% | $244,627 |
| Marketing | $538,000 | $1,967 | 0% | $189,419 | 35% |  |  | $189,419 | 35% | $348,581 |
| DI | $1,929,554 | $69,043 | 4% | $807,692 | 42% |  |  | $807,692 | 42% | $1,121,862 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 27,000 | 390 | 1.4% | 18,177 | 67.3% | 0 | 0% | 18,177 | 67.3% | 8,823 |
| On-Line Energy Surveys | 18,000 | 123 | .68% | 10,514 | 58.4% | 0 | 0% | 10,514 | 58.4% | 7,486 |
| In-Home Energy Surveys | 8,000 | 278 | 3.5% | 4,864 | 60.8% | 0 | 0% | 4,864 | 60.8% | 3,136 |
| Telephone Energy Surveys | 1,000 | 23 | 2.3% | 518 | 51.8% | 0 | 0% | 518 | 51.8% | 482 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 75% |  | 75% |  | n/a |  | 75% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved processing and mailing of 390 mail-in surveys.  This brings program total to 18,177 completed and processed surveys in 2004-2005 program year.  Of these completed surveys, 2,400 were completed and processed in Chinese, 197 in Vietnamese and 1,451 in Spanish.

- Scheduled and mailed 39,900 English survey packages in February to 100 percent customers in hard-to-reach segments.

- Began work with Resource Action Programs to deliver a school-based energy efficiency educational program within SCE’s service territory.  This school-based program is a joint effort with the Southern California Water Company.  This program targets sixth grade classrooms by distributing the LivingWise® activities kits containing electric and water measures.  Each kit includes SCE’s HEES Mail-In Energy survey for completion by the student’s parents.

- Continue to work with Asian Pacific American Community Service Center, a local community-based organization, to promote the program to the Chinese- and Vietnamese-speaking communities.

- Continue to work with the statewide team and coordinated translations of the survey packages from English to Korean.

On-Line Survey

- Achieved processing of 123 completed surveys.  This brings program total to 10,514 completed and processed surveys in 2004-2005 program year.  Of the completed surveys, 38 took the survey in Spanish and 37 took the survey in Chinese.

- Started planning of the on-line marketing campaign to increase survey participation.  Campaign to be launched in 2nd Quarter.

- Continue planning for development of the Vietnamese on-line interactive survey to be launched in 3rd quarter.

In-Home Survey

- Achieved 276 completed surveys.  This brings program total to 5,382 surveys conducted in 2004-2005 program year.  Of these completed surveys, 1,361 surveys were conducted in Spanish.

- Completed one SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  This brings total joint surveys conducted to 790 surveys.  SoCalGas will participate in the solicitation card mailing in March to 10,000 customers reside in Los Angeles and Orange County coastal areas.

- Coordinated and conducted 18 surveys in Delano.  Customers were referred by the Bakersfield/Kern County Partnership and participated in the program led by PG&E.

- Developed two new solicitation cards in 2005, one was designed to target the coastal communities and the other was designed to target the desert communities.  New artwork and texts should generate higher response rate to survey participation.

- First mailing is scheduled in March to 10,000 customers reside in Los Angeles and Orange County coastal area.

- Second mailing is scheduled two weeks after the first mailing to 40,000 customers who reside in Visalia/Tulare and Glendora/West Covina areas.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 18,177 Mail-In Surveys | $12.30 | Same |
| 10,514 On-Line Surveys | $11.31 | Same |
| 4,864 In-Home Surveys | $81.81 | $91.46 |
| 518 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January 2004 through February 2005, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August as a result of the competitive bid issued in May.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Presented the 2004-2005 HEES program status to the Energy Efficiency Call Center staffs on 2004 completed surveys numbers and summary, 2005 goals, on-line survey promotion campaign, marketing materials.  The staffs are interested in ride-along with the in-home survey in 2005.

- Created the first draft of the 2006 Request for Proposal to be presented to the statewide team members.  This solicitation will seek proposals from potential bidders for 2006-2008 program year work in the Mail-In and On-Line Surveys.

- Continue to participate in the 2006-2008 HEES program planning process.

- Started dialogues with survey vendors in soliciting ideas for new program year.

- Mail-In Survey

  - Continue to promote the appliance recycling program by inserting a brochure with every energy report mailed.  Expand promotion plan to include program insert in all survey packages mailings in 2005.

- On-Line Survey

  - Promoted the Home Online Energy Survey to customers attending the South Bay Partnership event.

  - Continue to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Coordinated efforts with the marketing group to certified RMK as a qualified Minority Business Enterprise.  RMK will develop and print the solicitation cards for the 2005 marketing material.

  - Continue the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Provided survey contractor with English and Spanish Medical Baseline Applications to be given to customers that use electrically operated life support equipment in their homes for a reduced rate.

  - Continue to provide survey contractor with CARE applications to be handed out to low- and moderate-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None