| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $109,936 | 4% | $2,293,995 | 73% |  |  | $2,293,995 | 73% | $834,385 |
| Admin | $532,446 | $31,472 | 6% | $474,163 | 89% |  |  | $474,163 | 89% | $58,283 |
| Marketing | $538,000 | $9 | 0% | $350,161 | 65% |  |  | $350,161 | 65% | $187,839 |
| DI | $1,929,554 | $78,456 | 4% | $1,469,670 | 76% |  |  | $1,469,670 | 76% | $459,884 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 27,000 | 2,441 | 9.0% | 36,243 | 134% | 0 | 0% | 36,243 | 134% | 0 |
| On-Line Energy Surveys | 18,000 | 957 | 5.3% | 22,315 | 124% | 0 | 0% | 22,315 | 124% | 0 |
| In-Home Energy Surveys | 8,000 | 355 | 4.4% | 6,918 | 86.5% | 0 | 0% | 6,918 | 86.5% | 1,082 |
| Telephone Energy Surveys | 1,000 | 242 | 24.2% | 1,494 | 149% | 0 | 0% | 1,494 | 149% | 0 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 80% |  | 80% |  | n/a |  | 80% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved processing of 2,441 mail-in surveys.  This brings program total to 36,243 completed and processed surveys in the 2004-2005 program year, which exceeded 34% of the survey goal.  Of these completed surveys, 2,518 were completed and processed in Spanish, 3,923 in Chinese, 1,409 in Vietnamese, and 602 in Korean.

On-Line Survey

- Achieved processing of 957 on-line surveys.  This brings program total to 22,315 completed and processed surveys in the 2004-2005 program year, which exceeded 24% of survey goal.  Of the completed surveys, 65 took the survey in Spanish and 109 took the survey in Chinese.

- Concluded the Target GiftCard marketing campaign.  Eligible SCE customer received a $5 Target GiftCard when they complete the survey online.  The campaign proved to be extremely successful and generated 89 percent of surveys completed in 2005.

- Finalize testing of the Vietnamese on-line interactive survey to launch in October.

In-Home Survey

- Achieved 597 completed surveys.  This brings program total to 8,412 surveys conducted in the 2004-2005 program year.  Of these completed surveys, 6,689 (80%) customers are defined by the Energy Efficiency Policy Manual as in hard-to-reach (HTR) segments, which exceeded the 50% goal.  Of these completed surveys, 1,761 surveys (21%) were conducted in Spanish.

- Completed 90 SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  This brings total joint surveys conducted to 1,535 surveys in the 2004-2005 program year.

- Mailed 40,005 solicitation cards to customers in Coachella valley.

- Schedule mailing of 10,000 solicitation cards to customers in Apple Valley, Hesperia and Victorville areas to increase survey participation in inland empire areas.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 36,243 Mail-In Surveys | $12.30 | Same |
| 22,315 On-Line Surveys | $11.31 | Same |
| 6,918 In-Home Surveys | $81.81 | $91.46 |
| 1,494 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January 2004 through September 2005, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August 2004 as a result of the competitive bid issued in May 2004.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- 2006-2008 Program Planning

  - Continue to participate in the 2006-2008 HEES program planning process, and coordinate program planning with the statewide team members in SoCalGas, PG&E and SDG&E (IOUs).

  - Evaluated 15 responses to the HEES Request for Information.  Seven companies are approved to proceed to Stage II.  Shared evaluation results with the statewide team.

  - Coordinated inputs from the IOUs and prepared the issuance of HEES Request for Proposal.

  - Coordinated issuance of the HEES Request for Proposal to seven bidders.  Proposals are due back 10/26/05.

  - Continue discussion with representative from SoCalGas and SoCal Water Company to incorporate gas and water conservation tips in surveys.

- Mail-In Survey

  - Continue to promote the appliance-recycling program by inserting a brochure with all survey packages and energy reports mailed.

- On-Line Survey

  - Continue to work with IT, CSBU PMO and Contractor to establish requirements for a secured FTP process to transmit customer usage data.  Project started in August/September with estimated completion date in November 2005.

  - Continue to meet with project team, monitor progress and ramping down of the Target GiftCard campaign.

  - Continue to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Continue to coordinate outreach effort in marketing and conducting water audits in Catalina Island.  Outreach is scheduled on 10/13/05 and 10/14/05.

    - Coordinated and scheduled residential and commercial water efficiency training with SoCal Water Company and LADWP representatives to conduct water audits.  Training was conducted on 09/01/05 at SCE facility.

    - Developed the marketing plan and designed the mailer for the outreach.

    - Met and coordinated outreach effort with commercial audit group, Energy Management Assistance and Refrigerator/Freezer Recycling program.

  - Continue to provide all survey participants with a bilingual 20/20 Summer Savings Program flyer to encourage customers to save energy this summer.  Energy auditors also provide information on increase incentive amounts and elimination of age restriction of refrigerator and freezer recycling program.

  - Continue the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Continue to provide customers with two CFLs after completion of the survey, for immediate energy savings.

  - Continue to provide survey contractor with CARE applications for the low- and moderate-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None