| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | November 2005 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $163,104 | 5% | $2,571,526 | 82% |  |  | $2,571,526 | 82% | $556,853 |
| Admin | $532,446 | $22,747 | 4% | $520,777 | 98% |  |  | $520,777 | 98% | $11,669 |
| Marketing | $538,000 | $63,279 | 12% | $461,413 | 86% |  |  | $461,413 | 86% | $76,587 |
| DI | $1,929,554 | $77,078 | 4% | $1,589,337 | 82% |  |  | $1,589,337 | 82% | $340,217 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 27,000 | 91 | 0.3% | 37,207 | 137% | 0 | 0% | 37,207 | 137% | 0 |
| On-Line Energy Surveys | 18,000 | 146 | 0.8% | 22,646 | 125% | 0 | 0% | 22,646 | 125% | 0 |
| In-Home Energy Surveys | 8,000 | 354 | 4.4% | 7,661 | 95.7% | 0 | 0% | 7,661 | 95.7% | 339 |
| Telephone Energy Surveys | 1,000 | 43 | 4.3% | 1,699 | 169% | 0 | 0% | 1,699 | 169% | 0 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 79% |  | 79% |  | n/a |  | 79% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved processing of 91 mail-in surveys.  This brings program total to 37,207 completed and processed surveys in the 2004-2005 program year, which exceeded survey goal by 38%.  Of these completed surveys, 2,664 were completed and processed in Spanish, 4,042 in Chinese, 1,536 in Vietnamese, and 1,077 in Korean.

On-Line Survey

- Achieved processing of 148 on-line surveys.  This brings program total to 22,646 completed and processed surveys in the 2004-2005 program year, which exceeded survey goal by 26%.  Of the completed surveys, 65 survey were completed in Spanish and 113 surveys were completed in Chinese.

In-Home Survey

- Achieved 397 completed surveys.  This brings program total to 9,360 surveys conducted in the 2004-2005 program year, which exceeded survey goal by 4%.  Of these completed surveys, 7,406 (79%) customers are defined by the Energy Efficiency Policy Manual as in hard-to-reach (HTR) segments, which exceeded the 50% goal.  Of these completed surveys, 2,068 surveys (22%) were conducted in Spanish.

- Completed 238 SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  This brings total joint surveys conducted to 1,883 surveys in the 2004-2005 program year.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 37,207 Mail-In Surveys | $12.30 | Same |
| 22,646 On-Line Surveys | $11.31 | Same |
| 7,761 In-Home Surveys | $81.81 | $91.46 |
| 1,699 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January 2004 through November 2005, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August 2004 as a result of the competitive bid issued in May 2004.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- 2006-2008 Program Planning

  - Continue the 2006-2008 HEES program planning process, and coordinate program planning with the statewide team members in PG&E, SoCalGas and SDG&E (IOUs).

  - Finalized evaluation of the four responses to the HEES Request for Proposal.  Evaluation team consists of members from SCE, SoCalGas and PG&E.

  - Conducted clarification meeting with a bidder on proposal submitted in response to the HEES RFP.

  - Continue discussion with representative from SoCalGas and SoCal Water Company to incorporate gas and water in survey program.

  - Met with the Law Department to discuss the 2006-08 HEES program and purchase order requirements.

- Mail-In Survey

  - Continue to promote the appliance-recycling program by inserting a brochure in energy reports mailed.

  - Worked with Contractor to ramp down 2005 program.

- On-Line Survey

  - Finalizing work with IT and Contractor to establish requirements for a secured FTP process to transmit customer usage data.  Transmission of the test data from SCE to Contractor’s site was successful.  Project went into production on 11/17/05 for testing in December.

  - Continue to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

  - Worked with Contractor to ramp down 2005 program.

- In-Home Survey

  - Continue to provide all survey participants with information on incentive programs and appliance recycling program.

  - Continue the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Continue to provide customers with two CFLs after completion of the survey, for immediate energy savings.

  - Continue to provide survey contractor with CARE applications for the low- and moderate-income customers that participated in the survey.

  - Worked with Contractor to ramp down 2005 program.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None