| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide CA Energy Star New Homes – Single Family, Multifamily Programs - PGC |
| Program Number: | 1239-04 |
| Month: | March 2004 |

- Program Status

Program Description

The California Energy Star® New Homes Program will influence the design and construction of single family and multifamily residential new construction. Working together with single and multifamily builders, architects, energy analysts, and other building industry professionals, this program will increase energy savings which will be achieved through a combination of education, design assistance and financial incentives. Single family and low-rise multifamily builder projects meeting the program requirements will also meet the requirements of the U. S. Environmental Protection Agency (EPA) Energy Star Homes Program. (The EPA does not currently recognize high rise construction with the Energy Star label.)

The program is offered by the four investor owned California utilities: Pacific Gas & Electric (PG&E), San Diego Gas & Electric (SDG&E), Southern California Edison (SCE) and Southern California Gas (SoCalGas). Program participation is available on a statewide basis, managed locally by each utility. All applications, procedures and program requirements are consistent throughout all four utility service areas.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,018,569 | $69,827 | 1% | $159,261 | 2% | $385,700 | 4% | $544,961 | 6% | $8,859,309 |
| Admin | $1,209,000 | $58,306 | 5% | $140,099 | 12% |  |  | $140,099 | 12% | $1,068,901 |
| Marketing | $428,200 | $9,299 | 2% | $9,299 | 2% |  |  | $9,299 | 2% | $418,901 |
| DI | $6,952,600 | $2,221 | 0% | $9,862 | 0% | $385,700 | 6% | $395,562 | 6% | $6,942,738 |
| EM&V | $428,769 |  |  |  |  |  |  |  |  | $428,769 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,855 |  |  |  |  | 700 | 7% | 700 | 7% | 9,855 |
| Annual kWh | 7,491,632 |  |  |  |  | 525,811 | 7% | 525,811 | 7% | 7,491,632 |
| Lifecyc kWh | 134,849,376 |  |  |  |  | 9,464,602 | 7% | 9,464,602 | 7% | 134,849,376 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CHEERS Training | 5 | 0 | 0% | 0 | % | 0 | 0% | 0 | 0% | 5 |
| Multifamily builder, architect, Title 24 consultant, design team - targeted training | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| x % direct implementation costs are allocated to HTR customers |  |  |  |  |  |  |  |  |  |  |

  - Activities/Accomplishments

    - Administrative -

- Continued providing 2004 applications to builders and builder agents for both the MF and SF programs.

    - Marketing -

- SCE’s Corporate Communications group finalized the statewide CESNHP brochures.

- SCE attended several building industry events to provide outreach in support of the CESNHP, including:

-BIA/Southern California – Inland Empire, monthly lunch meeting

-BIA/Southern California – Orange County, Builder Showcase event

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SCE’s Residential New Construction team is increasing our efforts to leverage the relationships various organizations within the company have with the building industry outside of Energy Efficiency programs.  In the month of March a meeting attended by SCE’s Energy Efficiency (new construction) team, Public Affairs, and Transmission and Distribution, was held to discuss the various outreach and networking activities and opportunities available through a collaboration of these internal organizations.

Additionally, SCE continues to promote the CESNHP to those cities currently participating in SCE’s Local Government Initiative’s Community Energy Efficiency Program.

- Changes to Subcontractors or Staffing

SCE has begun using CHEERS as the plan check agency in support of the CESNHP.  Initially, SCE had identified SolData and Aero Energy as plan check agencies for 2004.  However, due to workload of both of these organizations, SCE has turned to CHEERS, a third party verification and rating agency, and their compliance subcontractor, XXXXX.

- Additional Items

- SCE is working with Flex Your Power on collaborating on outreach and marketing opportunities.  FYP has included links to SCE’s website and has also included reference to SCE in their consumer brochures.  Additionally, SCE is working on adding FYP to the Residential New Construction website as well as including FYP’s logo on various marketing materials and outreach activities (possible trade show alliances, etc.)

- SCE, along with PG&E, SoCalGas, and SDG&E were honored by the Environmental Protection Agency in Washington D.C. on March 2, 2004 for our successful efforts behind the CESNHP.  The utilities were given an award highlighting “Regional, State, and Community Leadership in Energy Efficiency.”  As a result of this award SCE’s CESNHP was written up in an article in the LA Times, Builder and Developer Magazine, interviewed on KOCE-TV (local Orange County news station) and California State University Northridge’s campus radio station, as well as being featured on a new KCBS (Los Angeles) news show called “Your New Home” -- the feature aired on March 27, 2004 right after the NCAA’s “March Madness.”