- Marketing Materials

| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide CA Energy Star New Homes – Single Family, Multifamily Programs - PGC |
| Program Number: | 1239-04 |
| Month: | August 2004 |

- Program Status

Program Description

The California Energy Star® New Homes Program will influence the design and construction of single family and multifamily residential new construction. Working together with single and multifamily builders, architects, energy analysts, and other building industry professionals, this program will increase energy savings which will be achieved through a combination of education, design assistance and financial incentives. Single family and low-rise multifamily builder projects meeting the program requirements will also meet the requirements of the U. S. Environmental Protection Agency (EPA) Energy Star Homes Program. (The EPA does not currently recognize high rise construction with the Energy Star label.)

The program is offered by the four investor-owned California utilities: Pacific Gas & Electric (PG&E), San Diego Gas & Electric (SDG&E), Southern California Edison (SCE) and Southern California Gas (SoCalGas). Program participation is available on a statewide basis, managed locally by each utility. All applications, procedures and program requirements are consistent throughout all four utility service areas.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,018,569 | $253,341 | 3% | $898,956 | 10% | $2,620,820 | 29% | $3,519,776 | 39% | $8,119,614 |
| Admin | $1,209,000 | $39,961 | 3% | $393,201 | 33% |  |  | $393,201 | 33% | $815,799 |
| Marketing | $428,200 | $13,115 | 3% | $96,529 | 23% |  |  | $96,529 | 23% | $331,671 |
| DI | $6,952,600 | $200,265 | 3% | $409,226 | 6% | $2,620,820 | 38% | $3,030,046 | 44% | $6,543,375 |
| EM&V | $428,769 |  |  |  |  |  |  |  |  | $428,769 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,855 |  |  | 4 | 0% | 4,827 | 49% | 4,830 | 49% | 9,851 |
| Annual kWh | 7,491,632 |  |  | 2,868 | 0% | 3,613,018 | 48% | 3,615,886 | 48% | 7,488,764 |
| Lifecyc kWh | 134,849,376 |  |  | 51,624 | 0% | 65,034,331 | 48% | 65,085,955 | 48% | 134,797,752 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CHEERS Training | 5 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5 |
| Multifamily builder, architect, Title 24 consultant, design team - targeted training | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| 20% direct implementation costs are allocated to HTR customers | 20% |  |  |  |  |  |  |  |  |  |

  - Activities/Accomplishments

    - Administrative -

- SCE continues to issue 2004 applications to builders and builder agents for both the MF and SF programs.

- Purchase Orders were approved and issued to three vendors to provide program implementation services for the Multifamily CESNHP.  These vendors were awarded contracts based on their bid response to a competitive bid.

    - Marketing –

SCE continued monthly builder and consumer media advertisements in local industry trade and homebuyer magazines marketing the program as well as participating homebuilder subdivisions.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measures | Installed in August | Paid & Committed |
| --- | --- | --- |
| SF Home 15% Inland | 0 | 1,385 |
| SF Home 20% Inland | 0 | 2,575 |
| MF Home 15% | 0 | 533 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SCE, PG&E, and Sempra Utilities met August 18 to discuss and coordinate program changes and activities for the 2005 program year.  At this time, the IOUs are anticipating no major changes for the CESNHP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None