| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency - PGC |
| Program Number: | 1243-04 |
| Month: | July 2005 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all investor owned utility (IOU) small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficiency. The program will continue its focus on customers who are defined as hard-to-reach (HTR), who traditionally are less likely to install energy efficient technologies due to geographic, ethnic and other market barriers.  To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program and with other, community based organizations. Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,501,000 | $411,906 | 3% | $8,186,966 | 65% | $2,129,893 | 17% | $10,316,859 | 83% | $4,314,034 |
| Admin | $2,840,200 | $93,261 | 3% | $1,902,818 | 67% |  |  | $1,902,818 | 67% | $937,382 |
| Marketing | $1,303,200 | $41,447 | 3% | $679,489 | 52% |  |  | $679,489 | 52% | $623,711 |
| DI | $7,856,600 | $277,197 | 4% | $5,604,658 | 71% | $2,129,893 | 27% | $7,734,552 | 98% | $2,251,941 |
| EM&V | $501,000 |  |  |  |  |  |  |  |  | $501,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 46,407 | 1,070 | 2% | 22,335 | 48% | 8,529 | 18% | 30,863 | 67% | 24,072 |
| Annual kWh | 210,382,163 | 5,907,303 | 3% | 110,890,823 | 53% | 43,949,509 | 21% | 154,840,332 | 74% | 99,491,340 |
| Lifecyc kWh | 2,131,457,383 | 53,187,979 | 2% | 1,273,874,810 | 60% | 517,639,028 | 24% | 1,791,513,838 | 84% | 857,582,573 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard-to-reach customer participation as a percentage of total rebate applications paid | 40% |  | n/a | 39% | n/a |  | n/a | 39% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Held monthly telephone conference with the statewide team to discuss program implementation status, performance, delivery strategy, and issues.

    - Marketing –

- Completed printing and distribution of energy savings calculation brochures for CFL retrofit, T-8 lighting retrofit, HID lighting retrofit and high bay lighting retrofit projects.

- Continued planning for an SCE booth at the Western Foodservice and Hospitality Show to be held at the Los Angeles Convention Center in August.

- Continued planning for a statewide booth at the National Association of Foodservice Equipment Manufacturer’s Show to be held at the Anaheim Convention Center in September.  The theme of this show will be “Hot Rebates, Cool Savings”-- California Utilities Partnering for Energy Efficiency.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in June) | Average Cost Per Site |
| --- | --- |
| 175 | $1,395 |

| Types of Measures | Measures Installed in July |
| --- | --- |
| Lighting | 9,033 |
| HVAC* | 17,651 |
| Refrigeration** | 630 |
| Food Service | 0 |
| Agricultural | 40 |

* Includes window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation -

Underpayments:

1. (2) “Setback Programmable Thermostats”, less $.21.03 per unit to account for the purchase price being less than the rebate amount.

2. (124) “Screw-in Compact Fluorescent Lamp, 14-26 watt with reflector”, less $2.76 per unit to account for the purchase price being less than the rebate amount.

Overpayments:

1. (396) “Reflective Window Film-Inland”, overpaid by $.218181 per square foot due to incentive payment processing error.

Adjustments:

1. Cost transfer for $4,010.00 for one payment mistakenly charged to incentive budget in July.

2. One customer payments were returned to SCE (Reference number 440754) and cancelled/voided for a total of $ 1126.25 in July.

- EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None