| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Energy Audits Program – PGC |
| Program Number: | 1248-04 |
| Month: | April 2004 |

- Program Status

Program Description

The Statewide Nonresidential Energy Audits program offered by Pacific Gas and Electric Company, Southern California Edison, San Diego Gas and Electric and Southern California Gas Company provides a full range of professional technical assistance to educate customers on how to implement no cost, low cost measures and cost-effective energy-efficiency retrofits in their buildings to increase long term annual energy savings and capture electric peak demand reduction while lower their energy bills.  The energy audit recommendations are based on the customer’s recent billing history and/or customer-specific information regarding equipment and building characteristics.  This program also addresses the California Public Utilities Commission’s goals regarding equitable program access to the hard-to-reach business sector.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,067,200 | $208,536 | 5% | $540,160 | 13% |  |  | $540,160 | 13% | $3,527,040 |
| Admin | $412,980 | $22,052 | 5% | $67,688 | 16% |  |  | $67,688 | 16% | $345,292 |
| Marketing | $221,520 | $3,095 | 1% | $5,399 | 2% |  |  | $5,399 | 2% | $216,121 |
| DI | $3,138,700 | $183,389 | 6% | $467,073 | 15% |  |  | $467,073 | 15% | $2,671,627 |
| EM&V | $294,000 |  |  |  |  |  |  |  |  | $294,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy audits (including 8200 HTR) | 14200 | 1212 | 8.5% | 2827 | 19.9% | 0 | 0% | 2827 | 19.9% | 11373 |

  - Activities/Accomplishments

    - Administrative -

- Maintained budget expenditures for the Nonresidential Energy Audit Program.

- Refined master audit tracking system.

- Held internal discussions regarding coordination of energy audit activity.

- Met with field implementation team to discuss program activity tracking and delivery of completed audit reports.

    - Marketing –

In addition to the list in Attachment A:

- Printed 5,000 NR Audit program brochures.

- Catalina Island outreach brochures with NR audit information.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| Audit types Total ytd audits | Cost Per Site |
| --- | --- |
| Online 63 | $430 |
| Mail-in 17 | $29 |
| CD-ROM 92 | $196 |
| Over-the phone 750 | $29 |
| Onsite 1,905 | $138 |
| Total Energy Audits 2,827 | $109 |

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Coordinated audit requests with Express Efficiency, SPC incentive programs

- Coordinated with the statewide IOUs on future meetings

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None