| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Building Operator Certification Program – PGC |
| Program Number: | 1252-04 |
| Month: | August 2004 |

- Program Status

Program Description

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,048,000 | $12,890 | 1% | $52,763 | 5% |  |  | $52,763 | 5% | $995,237 |
| Admin | $155,600 | $3,545 | 2% | $39,044 | 25% |  |  | $39,044 | 25% | $116,556 |
| Marketing | $60,000 |  |  | $2,234 | 4% |  |  | $2,234 | 4% | $57,766 |
| DI | $784,400 | $9,345 | 1% | $11,485 | 1% |  |  | $11,485 | 1% | $772,915 |
| EM&V | $48,000 |  |  |  |  |  |  |  |  | $48,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals –

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host 5 Level I BOC full-course sessions, with an average student enrollment of 20 per course | 5 courses - 100 students | 0 | 0% | 4 courses –96 students | 80% | 0 | 0% | 4 courses – 96 students | 80% | 1 courses - 4 students |
| Host 1 Level II BOC full-course session, with a student enrollment of at least 15 | 1 course - 15 students | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 course - 15 students |

  - Activities/Accomplishments

    - Administrative -

- Invoices for start-up costs and sessions 1 & 2 of the first 4 Level 1 classes received and processed.  Total costs $63,586, less student tuition fees of $36,465, leaving a balance due to NEEC of $27,121.

- Student Performance Goal for 2004 of 115 students, registered to date 107 = 93% of goal.

- Research plan being developed by Research Into Action for 2004 M&E results.

- On track to meet goals.

    - Marketing -

- Memo was distributed to all SCE customer account representatives in the Torrance/South Bay area about a BOC Information Meeting that was held in Torrance on August 18, 2004.

- Arrange for 5,000 pieces of information and training session materials to be mailed for the Torrance Information Meeting.

- Mailing sent August 23, 2004 to inform potential students they can register for BOC Level 1 class in Torrance starting September 29 and a Level 2 class to be held in Anaheim in October 2004.

- CTAC prepared e-mail notice to former students for registration in the Level 1 class being held in Torrance as well as a Level 2 class to be held in Anaheim in October 2004.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None