| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Building Operator Certification Program – PGC |
| Program Number: | 1252-04 |
| Month: | February 2005 |

- Program Status

Program Description

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,048,000 | $2,425 | 0% | $238,523 | 23% |  |  | $238,523 | 23% | $809,477 |
| Admin | $155,600 | $1,810 | 1% | $60,275 | 39% |  |  | $60,275 | 39% | $95,325 |
| Marketing | $60,000 |  |  | $2,234 | 4% |  |  | $2,234 | 4% | $57,766 |
| DI | $784,400 | $615 | 0% | $176,015 | 22% |  |  | $176,015 | 22% | $608,385 |
| EM&V | $48,000 |  |  |  |  |  |  |  |  | $48,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Feb- 05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host 5 Level- I BOC full-course sessions, with an average student enrollment of 20 per course | 10 courses - 200 students | 1 course – 31 students | 10% 16% | 6 courses – 145 students | 60% 73% | 0 | 0% | 6 courses – 145 students | 60% 73% | 4 courses – 55 students |
| Host 1 Level- II BOC full-course session, with a student enrollment of at least 15 | 1 course - 15 students | 0 | 0% | 1 course - 15 students | 50% 50% | 0 | 0% | 1 course – 15 students | 50% 50% | 0 |

  - Activities/Accomplishments

    - Administrative –

- Student Performance Goal for 2004-2005: 230 students enrolled.

  - Enrolled and attended to date: 160, or 70%

- Class Performance Goal for 2004-2005: 10 Level - 1; 2 Level - 2

  - Classes offered to date: 6 Level-I courses and one Level-II course, or 70%

    - Marketing –

- Conducted three informational meetings to encourage class registration: Oxnard, Los Angeles and Temecula.

- To encourage further enrollments, mailed the BOC bulletin to 500 BOC graduates and their employers.

- Participated with a BOC exhibit and presentation at the Southern California Plant Engineering & Maintenance Show in Anaheim on February 23 and 24.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None