| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Building Operator Certification Program – PGC |
| Program Number: | 1252-04 |
| Month: | December 2004 |

- Program Status

Program Description

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,048,000 | $13,936 | 1% | $172,008 | 16% |  |  | $172,008 | 16% | $875,992 |
| Admin | $155,600 | $6,907 | 4% | $58,542 | 38% |  |  | $58,542 | 38% | $97,058 |
| Marketing | $60,000 |  |  | $2,234 | 4% |  |  | $2,234 | 4% | $57,766 |
| DI | $784,400 | $7,030 | 1% | $111,232 | 14% |  |  | $111,232 | 14% | $673,168 |
| EM&V | $48,000 |  |  |  |  |  |  |  |  | $48,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host 5 Level I BOC full-course sessions, with an average student enrollment of 20 per course | 5 courses - 100 students | 0 | 0% | 5 courses –114 students | 100% | 0 | 0% | 5 courses – 114 students | 100% | 0 |
| Host 1 Level II BOC full-course session, with a student enrollment of at least 15 | 1 course - 15 students | 0 | 0% | 1 course - 15 students | 100% | 0 | 0% | 1 course - 15 students | 100% | 0 |

  - Activities/Accomplishments

    - Administrative –

- Student Performance Goal for 2004: 115 students. Registered to date: 129.  Goals met.

- Class Performance Goal for 2004: 5 Level 1; 1 Level 2.  Goals met.

    - Marketing -

- Prepared and issued informational meeting notices for Irwindale (January 11, 2005), and Bakersfield (January 12, 2005).  A total of 3,000 informational pieces were mailed.  Received nine RSVPs for the Irwindale meeting.

- Prepared an informational luncheon meeting notice for distribution by BOMA/GLA to its members.  The meeting will be held February 10, 2005.

- Completed the 2005 BOC class schedule for six Edison-sponsored locations including Irwindale, Bakersfield, Riverside, Oxnard, Temecula, and Anaheim.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None