| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Emerging Technologies Program - PGC |
| Program Number: | 1255-04 |
| Month: | October 2004 |

- Program Status

Program Description

The Statewide Emerging Technologies (ET) program is an information-only program that seeks to accelerate the introduction of innovative energy efficient technologies, applications, and analytical tools that are not widely adopted in California.  There are a daunting amount of market barriers a new energy efficient product must overcome to gain acceptance.  During initial marketing efforts, energy efficient products accepted by “innovators” may fail to gain wider acceptance with more risk adverse customers.  The intent of the ET program is to help accelerate a product’s market acceptance through a variety of approaches, but mainly by reducing the performance uncertainties associated with new products and applications.   The program targets all market segments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,679,000 | $21,367 | 1% | $373,813 | 10% | $347,700 | 9% | $721,513 | 20% | $3,305,187 |
| Admin | $981,000 | $15,932 | 2% | $212,893 | 22% |  |  | $212,893 | 22% | $768,107 |
| Marketing | $20,000 |  |  | $114 | 1% |  |  | $114 | 1% | $19,886 |
| DI | $2,599,000 | $5,435 | 0% | $160,806 | 6% | $347,700 | 13% | $508,506 | 20% | $2,438,194 |
| EM&V | $79,000 |  |  |  |  |  |  |  |  | $79,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings goals.

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Emerging Technologies Applications Assessments initiated in PY2004 | 10 | 2 | 0% | 0 | 0% | 8 | 80% | 8 | 80% | 2 |
| ETCC ET Database PY2004 update | 1 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 |
| PY2004 ETCC meetings | 4 | 0 | 0% | 3 | 75% | 0 | 0% | 3 | 75% | 1 |

  - Activities/Accomplishments

    - Administrative -

- No Activity

    - Marketing -

During October, program staff participated in the Emerging Technologies Summit in San Francisco.  Program staff chaired a summit panel on “LEED and Energy Star: Drivers for Emerging Technology Adoption.” In addition, staff made five separate presentations over the course of the two day summit in the Tactics, Policy, and Tech Tracks:

- Development and Performance Evaluation of Advanced Rooftop Air Conditioning Units,

- Leadership in Energy and Environmental Design (LEED) Rating – A Driver for Emerging Technology Adoption,

- Showcasing Energy Efficient Emerging Refrigeration Technologies,

- Compressed Air Supply Efficiency – CASE Index, and

- Emerging Technologies Energy Efficiency Programs - Roles & Linkages.

During the evening reception, staff manned a booth with a poster highlighting of several of SCE’s ET projects in the commercial, industrial, agricultural, and residential sectors.  Also during October, program staff worked with SCE’s Account Management staff for the Hotels/Motels segment and Education and Training program staff, to organize, develop and present a seminar entitled: “Wake Up! With Energy Efficiency.”  The seminar provided hotel segment customers an overview of energy usage in hotels and information on energy efficient technologies along with the results from several emerging technology projects, including new controls for guest room bathroom lights, smart thermostats, parking lot lighting, kitchen ventilation, guest room card key control systems, signage lighting, and efficient food service equipment.  Fifty-five customers attended the seminar at CTAC.  Preliminary review of customer feedback rated the seminar as “above average” to “excellent” with requests for further targeted seminars.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Emerging Technologies Coordinating Council

The Emerging Technologies Coordinating Council (ETCC) did not meet during the month.  The ETCC has met three times this calendar year:  January 15, April 23, and September 13.

2004 Emerging Technology Application Assessments

The 2004 program has committed and initiated a total of eight assessment projects this year.  During the month of October, two new assessment projects were committed:

- Optical Demand Defrost.  This assessment project will determine the potential energy savings of using new sensor technologies and computer software to control the defrost cycle of a refrigeration system.  The project will be conducted at SCE’s Refrigeration and Thermal Test Center.  Existing practices for demand defrost technologies rely on either delicate instrumentation or indirect measurements to start and stop the defrost periods.  New sensor technologies and computer software can be used to initiate defrosting only when it is needed and only long enough to remove the ice build-up on the evaporator coils.  The assessment project will evaluate the use of optical sensors to provide demand defrost control.

- Wireless Power Meters & Sensors.  This assessment project will assist in the development of wireless power meters and remote sensors for use in energy management systems (EMS) for monitoring and control of HVAC, lighting, and process systems.  The project will collect and publish customer needs and wants for wireless EMS components.  The project is a partnership with the U.S. Department of Energy and the Pacific Northwest National Laboratory in the development and evaluation of both hardware and software systems.

The following assessment projects were committed and initiated earlier this year:

- Light Emitting Diode (LED) Outdoor Lights.  This past month several LED street lights and their support hardware were procured and delivered.

- LED Task Lights.  Program staff continues to work on the detailed plans for this assessment. There was no other significant progress for this project.

- Residential Economizer Cycle Retrofits.  An agreement with a second homeowner was signed and an economizer retrofitted.  As part of this assessment project, economizers have been retrofitted into two homes.  End-use data monitoring is underway at both sites.

- Advanced Heuristic Thermostatic Control System for Hotels. Program staff continued the end-use monitoring at the site.  In addition, staff performed a preliminary data review and analysis.

- Occupancy Sensor Nightlight Wall Switches for Hotel Guest Room Bathrooms.  End use monitoring continued at two hotel sites.  The verification of hotel room occupancy rates based on the monitored data was initiated and preliminary analyses were presented at a seminar for hotel segment customers.

- California Kitchen Down-Lights.  The homes are awaiting occupancy next month for end use monitoring to begin.

In addition, program staff continues to consider several possible technology application assessment projects for 2004 and 2005.  Assessment projects initiated in prior program years continue as summarized in the following sub-sections.

2003 Statewide Emerging Technology Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Rapid Start “Super” T-8 Fluorescent Lamp/Ballast.  Project staff continued to work on the final report and project fact sheet.

- Instant Start “Super” T-8 Lamp/Ballast.  Project staff continued to work on the final report and project fact sheet.

- Stairwell Lighting Bi-Level Switching.  Equipment installation continued at the retrofit sites.

- Network Management of Computer Power Option Settings.  The project manager continued to solicit different SCE department’s participation in the large scale pilot test.  As of the end of October, over 50 computers had been committed to the companywide large scale pilot.

- Electrochromic Glazing.  Project staff is seeking a suitable site within SCE’s facilities where to perform this assessment project.

- Displacement Ventilation. The engineering contractor measured existing air flows in SCE’s Daylighting Center and continued to work on the final design.  The assessment project manager is preparing to bid the retrofit work once the final design is completed.

- Advanced Classroom Lighting System.  During the month, the Dual-mode PIER advanced lighting system is moved to a computer classroom at CTAC.  Follow-on PIER derivative special demonstration fixtures were installed into the Daylighting Center classroom to replace the original classroom system.  The center now exhibits two advanced lighting systems: a T5-HO system with dimming controls and a Super T-8 system with stepping controls.

- Anti Corrosion Coatings for Condenser Coils.  End use data monitoring of the packaged air-conditioning equipment continued this month.

- Voltage Reducer System for Dimming Control.  Based on the review of test data, project staff concluded that additional performance tests are needed for this assessment project.

2003 Local Demonstration and Information Transfer ET Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Professional Wet Cleaning.  The assessment project contractor, Occidental College, continued to work on the draft final report.

- Cold Storage Refrigeration Control.  The new control system and sensors were tested during the month.

- Salt Reduction of Waste Water Precipitation of Salts for Fluid Bed/Lime Process.  The consultant has completed the final report and will submit it to SCE for final review and approval.

- Petroleum Dry Cleaning.  With testing underway at some sites, the assessment project continues with test site selection.

- Silicone Dry Cleaning.  With testing underway at some sites, the assessment project continues with test site selection.

- Carbon Dioxide Dry Cleaning.  With testing underway at some sites, the assessment project continues with test site selection.

- Advanced Control for Plastic Granulators.  During the month, project staff attended a national plastics conference and exposition.  At the show, staff found a controller that is more affordable and suitable for retrofits.  Also, a decision was made to forgo customer site tests and pursue a side-by-side controlled environment test at SCE’s CTAC facilities.

2002 Statewide Emerging Technologies Assessments

The program staff worked on the following projects that were initiated in 2002:

- Integrated Design for New Children’s Museum, and Underfloor Air Distribution.  The customer continued to seek a new site for the museum.

- T-5 High Output Lighting System for High Bay Workshop and Variable Geometry Reflector System for HID Lighting.  Project staff continued to work on the final report and fact sheet.

- Integrated Efficiency Improvements for Small Grocery Stores.  Project management staff completed its review of the draft report.  Staff worked on incorporating the review comments into a second draft of the report.

- Integration of Energy Efficiency Improvements in a Small Sit-Down Restaurant.  The new refrigeration system was installed and a new two-door freezer unit was procured.

- Integrated Hood Exhaust Backwall Make-Up Air System for Hood Exhaust.

There was no progress during the month for this assessment project.  The project manager continued to work with the restaurant chain to select a suitable site.

- Perforated Supply Plenum Make-Up Air System for Hood Exhaust.  End-use monitoring and data collection continued at the site.

- Variable Frequency Drive for Commercial Kitchen Hood Exhaust and Make-Up Air System.  End-use data monitoring continued at the site.

2002 Local Demonstration & Information Transfer ET Application Assessments

The program staff working on the following projects that were initiated in 2002:

- Integrated Design for Non-Residential Retrofit Buildings. Contractors continued the verification and pre-functional test work.  In addition, program staff worked on the development and planning of an Integrated Design Seminar targeting school district personnel and designers, and began to work on a project fact sheet.

- Low-E Pigment for Stucco and Paints for Residential and/or Small Commercial Buildings.  Program staff worked on revising the draft report.

- Spray-on Radiant Barrier for Existing Residential and/or Small Commercial Buildings.  Program staff worked on revising the draft final report.

2001 Emerging Technologies Showcases

The program staff worked on the following project that was initiated in 2001:

- Southeast Learning Center – Natural Ventilation, High Efficiency HVAC, and Daylighting Controls.  The contractor has started the commissioning work at the site.

2000 Emerging Technologies Showcases

The program staff worked on the following projects that were initiated in 2000:

- National Resource Defense Council (NRDC) Santa Monica Headquarters Natural Ventilation, High Efficiency HVAC, Daylighting Control, Water Recovery System, Occupancy Sensors, and Photovoltaic System.  Program staff started work on a project fact sheet this month and end-use monitoring at the site continues.

- Pomona Unified School District – Portable Classroom.  The skylight reflector was installed and end use monitoring was started.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None