| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Emerging Technologies Program - PGC |
| Program Number: | 1255-04 |
| Month: | February 2004 |

- Program Status

Program Description

The Statewide Emerging Technologies (ET) program is an information-only program that seeks to accelerate the introduction of innovative energy efficient technologies, applications, and analytical tools that are not widely adopted in California.  There are a daunting amount of market barriers a new energy efficient product must overcome to gain acceptance.  During initial marketing efforts, energy efficient products accepted by “innovators” may fail to gain wider acceptance with more risk adverse customers.  The intent of the ET program is to help accelerate a product’s market acceptance through a variety of approaches, but mainly by reducing the performance uncertainties associated with new products and applications.   The program targets all market segments.

Activities/Accomplishments

- Emerging Technologies Coordinating Council

The Emerging Technologies Coordinating Council (ETCC) did not meet during the month of February.

- Emerging Technology Application Assessments

The program committed and initiated one (1) new assessment project during the month of February.  In addition, program staff continues to work on a list of 34 potential technology application assessments for 2004 and 2005.  Projects initiated this month include:

- Occupancy Sensor Nightlight Wall Switch for Hotel Guest Room Bathrooms.

This assessment project will determine the potential demand and energy savings, as a function of hotel room occupancy rates, for replacing existing guest room bathroom wall switches with wall switches with a built-in occupancy sensor and LED nightlight.  This new energy efficiency product was developed through the California Energy Commission’s PIER program under Contract No. 500-01-041.  SCE’s assessment project will monitor and retrofit forty guest rooms divided among four hotel facilities in Southern California.  During the month of February, final customer agreements were negotiated and signed with each hotel.  A project kick-off meeting with two of the participating hotels was held during the month.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

SCE filed a revised Program Implementation Plans (PIP) for this program on February 2, 2004.  The revised PIP addresses the following items:

Public Input and ETCC Meetings

SCE clarified in the PIP how the program obtains public input and that a portion of the quarterly ETCC meetings are open to interested public entities.  However, due to the sensitive nature of certain information, customer and proprietary data, portions of the ETCC meetings are necessarily limited to the utilities ET program staff and the California Energy Commission PIER program managers.

Specific Costs for Projects Planned to be Undertaken

Specific costs for planned projects will be provided in upcoming monthly reports.  SCE is working with the statewide ET program utility program managers to develop a consistent format for reporting planned project specific costs.

Ongoing Projects and Products Incorporated into Utility Energy Efficiency Programs

SCE is working with the statewide ET program utility program managers to develop a consistent format for reporting progress on ongoing projects initiated in prior program years. In upcoming monthly reports, ongoing project progress will be provided as well as final project results as they become available.  Also, in upcoming monthly reports, SCE will report which project associated products have been incorporated into other energy efficiency programs.

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Training

There were no activities beyond what may be described in the monthly reporting tables.

- Rebate and Direct Install Expenditure Adjustments

Due to actual incentives paid to customers are capped at maximum program rebate level or measures that are qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may be differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Marketing

There were no activities beyond what may be described in the monthly reporting tables.

- Additional Items

None