| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Savings By Design – PGC |
| Program Number: | 1261-04 |
| Month: | September 2005 |

- Program Status

Program Description

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incntives as well as design team incentives.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,310,596 | $241,748 | 1% | $4,841,588 | 26% | $23,634,510 | 129% | $28,476,098 | 156% | $13,469,008 |
| Admin | $1,739,600 | $79,793 | 5% | $1,260,673 | 72% |  |  | $1,260,673 | 72% | $478,927 |
| Marketing | $205,200 |  |  | $24,496 | 12% |  |  | $24,496 | 12% | $180,704 |
| DI | $15,855,200 | $161,954 | 1% | $3,556,418 | 22% | $23,634,510 | 149% | $27,190,929 | 171% | $12,298,781 |
| EM&V | $510,596 |  |  |  |  |  |  |  |  | $510,596 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 17,557 | 143 | 1% | 3,083 | 18% | 24,856 | 142% | 27,939 | 159% | 14,474 |
| Annual kWh | 88,042,706 | 1,200,346 | 1% | 26,014,839 | 30% | 181,024,865 | 206% | 207,039,704 | 235% | 62,027,867 |
| Lifecyc kWh | 1,452,700,830 | 21,394,687 | 1% | 479,391,736 | 33% | 3,326,078,144 | 229% | 3,805,469,881 | 262% | 973,309,094 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies | 5 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5 |
| 2004 Title 24 Seminars | 2 | 0 | 0% | 2 | 100% | 0 | 0% | 2 | 100% | 0 |
| eQUEST Training | 2 | 0 | 0% | 8 | 400% | 0 | 0% | 8 | 400% | 0 |
| Demystifying the Whole Building Approach to Energy Effic. Design | 2 | 0 | 0% | 5 | 250% | 0 | 0% | 5 | 250% | 0 |
| Cool Roofs (SBD Presentation) | 2 | 0 | 0% | 1 | 50% | 0 | 0% | 1 | 50% | 1 |
| 2005 Title 24 Seminars | 2 | 0 | 0% | 3 | 150% | 0 | 0% | 3 | 150% | 0 |
| Other Seminars (PY 2005) | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Integrated School Building Design | 3 | 0 | 0% | 2 | 67% | 0 | 0% | 2 | 67% | 1 |
| Design Strategies for High Performance Glass | 1 | 0 | 0% | 1 | 100% | 0 | 0% | 1 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing –

1.2.3	Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures | kWh Committed YTD | kWh Installed in September |
| --- | --- | --- |
| Whole Building Approach |  |  |
| Whole Building - Owner Incentive | 51,479,329 | 0 |
| Whole Building - DTI | 3 | 0 |
| System Approach |  |  |
| HVAC: Energy Reduction | 11,791,247 | 310,958 |
| Daylighting Controls | 7,207,432 | 0 |
| LPD Reductions | 16,336,115 | 407,714 |
| Supermarket Systems | 0 | 0 |
| Process Systems | 116,848,172 | 650,037 |

      - Calculated and Actual Payment Reconciliation –

In the month of September 2005, financial incentives in the amount of $80,113 (Tab 1A, Direct Implementation Section) were paid to customers.  “Tab 2A – RecordedEEActivities” calculates that $126,782 in financial incentives was paid to customers.  The difference is the result of the following situation: 1) projects (from the previous month as well as the current month) being “status” changed as completed in the New Construction Information System (NCIS).

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

New Construction Services has updated Savings By Design to reflect the 2005 version of California’s Title 24 energy code, which applies to any buildings submitted to the building department for permit on or after October 1, 2005. The new Title 24 Standards significantly change the baselines used to calculate energy savings resulting from energy efficiency measures recommended and incentivized by New Construction Services through the Savings By Design program. New Construction Services closely coordinated with a consultant to update the software used to calculate energy savings to incorporate the new baselines.

- Coordination Activities

None

- Changes to Subcontractors or Staffing

No changes to subcontractors or staffing during this month.

- Additional Items

New Construction Services completed an analysis of a new compressed air plant in Adelanto.  The 100,000 square foot facility will utilize high efficiency, variable speed compressors in the manufacturing of their pipes.  The project will reduce energy use by an estimated 23.8 kW and 126,000  kWh when it is completed in January of 2006.

New Construction Services completed an energy efficiency analysis with a hospital in Vasalia.  The planned new central plant is part of a 105 million dollar expansion project for the Visalia health care district.  The new facility will include VFD control of all pumps and cooling tower fans and two 1200-ton high efficiency centrifugal chillers with VFD control.  The central plant is estimated to reduce energy use by 267 kW and 1.315 million kWh when completed at the end of May 2006.

New Construction Services has begun working with the USPS which is designing an 11,000 square foot mail sorting facility in Tulare.  The new facility will be completed in June of 2006 and will include high efficiency lighting.  The annual energy savings are estimated to be 14,000 kWh and 6 kW.

New Construction Services met with a Lancaster Baptist Church to discuss their plans to build an academic building.  The new building will be 40,000 square foot and will be part of a larger expansion plan which will eventually include the addition of a central plant.  The academic building will likely include a wide range of energy efficiency measures and will be completed in December of 2006.  The energy savings are estimated to be 100,000 kWh annually and 33 kW.

New Construction Services met with  college in Chaffey to discuss their Visual and Performing Arts Center.  The Center will include 40,000 square feet of new space and 21,000 of gut rehab.  Energy efficiency measures will include high efficiency lighting and daylighting.  The expected completion date for the Center is June 2008.  The energy savings are estimated to be 150,000 kWh annually with a demand reduction of 50 kW.

New Construction Services has updated Savings By Design to reflect the 2005 version of California’s Title 24 energy code, which applies to any buildings submitted to the building department for permit on or after October 1, 2005. The new Title 24 Standards significantly change the baselines used to calculate energy savings resulting from energy efficiency measures recommended and incentivized by New Construction Services through the Savings By Design program. New Construction Services closely coordinated with a consultant to update the software used to calculate energy savings to incorporate the new baselines.