| ++Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Savings By Design – PGC |
| Program Number: | 1261-04 |
| Month: | December 2004 |

- Program Status

Program Description

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,310,596 | $676,689 | 4% | $2,322,184 | 13% | $16,021,896 | 88% | $18,344,080 | 100% | $15,988,411 |
| Admin | $1,739,600 | $72,435 | 4% | $744,917 | 43% |  |  | $744,917 | 43% | $994,683 |
| Marketing | $205,200 |  |  | $21,057 | 10% |  |  | $21,057 | 10% | $184,143 |
| DI | $15,855,200 | $604,254 | 4% | $1,556,210 | 10% | $16,021,896 | 101% | $17,578,106 | 111% | $14,298,989 |
| EM&V | $510,596 |  |  |  |  |  |  |  |  | $510,596 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 17,557 | 79 | 0% | 849 | 5% | 16,420 | 94% | 17,269 | 98% | 16,708 |
| Annual kWh | 88,042,706 | 409,965 | 0% | 6,065,965 | 7% | 115,097,292 | 131% | 121,163,257 | 138% | 81,976,741 |
| Lifecyc kWh | 1,452,700,830 | 6,590,159 | 0% | 111,710,417 | 8% | 2,096,212,352 | 144% | 2,207,922,769 | 152% | 1,340,990,413 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies | 5 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |
| 2004 Title 24 Seminars | 2 | 0 | 0% | 2 | 100% | 0 | 0% | 2 | 100% | 0 |
| eQUEST Training | 2 | 0 | 0% | 5 | 250% | 0 | 0% | 5 | 250% | 0 |
| Demystifying the Whole Building Approach to Energy Effic. Design | 2 | 0 | 0% | 4 | 200% | 0 | 0% | 4 | 200% | 0 |
| Cool Roofs (SBD Presentation) | 2 | 0 | 0% | 1 | 50% | 0 | 0% | 1 | 50% | 1 |
| 2005 Title 24 Seminars | 2 | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 0% | 2 |
| Other Seminars (PY 2005) | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Integrated School Building Design | 3 | 0 | 0% | 2 | 67% | 0 | 0% | 2 | 67% | 1 |
| Design Strategies for High Performance Glass | 1 | 0 | 0% | 1 | 100% | 0 | 0% | 1 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing –

1.2.3	Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures | kWh Committed | kWh Installed in December |
| --- | --- | --- |
| Whole Building Approach |  |  |
| Whole Building - Owner Incentive | 40,137,145 | -- |
| Whole Building - DTI | 1 | -- |
| System Approach |  |  |
| HVAC: Energy Reduction | 10,628,665 | 69,598 |
| Daylighting Controls | 2,041,060 | 49,271 |
| LPD Reductions | 7,259,590 | 354,325 |
| Supermarket Systems | -- | -- |
| Process Systems | 70,045,526 | 23,347 |

      - Calculated and Actual Payment Reconciliation –

In the month of December, financial incentives in the amount of $487,632 were paid to customers.  “Tab 2A – RecordedEEActivities” calculates that $33,917 in financial incentives was paid to customers. The difference was the result of the following two situations: 1) Two invoices totaling $257, 567 paid to J.J. Hirsh which had no kWh value in the RecordedEEActivities section, and 2) seven projects not being “status” changed as completed in the New Construction Information System (NCIS) database at the end of the month.  The actual financial incentives will appear in next month’s report.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Statewide:

- Held December Statewide Savings By Design meeting.

- Changes to Subcontractors or Staffing

No changes to subcontractors or staffing during this month.

- Additional Items

- Statewide Achievements

  - 3,581 subscribers to the E-News option on the Energy Design Resources website in 2004 (www.energydesignresources.com).

- SCE Savings By Design activities:

  - Held Savings By Design Program staff meeting

  - Presented “Lighting for Architecture and Interiors” class at CTAC.

- SCE customer project activity:

  - Savings By Design is building on a long time relationship with a major restaurant chain to influence the energy efficient design of 4 proposed new restaurants.  Each has the potential to save 188,900 kWh and a potential 44 kW reduction.

  - Two 55,000 square feet warehouse supermarkets are adopting SCE energy recommendations.  On average each facility will save 300,000 kWh and reduce load by 44 kW when completed.

  - A major water reclamation facility is planning to expand their existing facility.  SCE is recommending variable speed drives and drive controls.  These measures will save the water reclamation plant operators 2,400,000 kWh annually and reduce load by 6.6 kW.

  - New Construction Services representatives met with a Los Angeles Community College to assist the energy design for their new language arts center.  SCE will provide technical assistance to assist the school in meeting the district’s goal of exceeding Title 24 by 20 percent.