| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Savings By Design – PGC |
| Program Number: | 1261-04 |
| Month: | August 2004 |

- Program Status

Program Description

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,310,596 | $208,046 | 1% | $1,143,773 | 6% | $5,167,229 | 28% | $6,311,002 | 34% | $17,166,822 |
| Admin | $1,748,200 | $24,864 | 1% | $453,465 | 26% |  |  | $453,465 | 26% | $1,294,735 |
| Marketing | $1,285,000 |  |  | $2,658 | 0% |  |  | $2,658 | 0% | $1,282,342 |
| DI | $14,766,800 | $183,183 | 1% | $687,651 | 5% | $5,167,229 | 35% | $5,854,880 | 40% | $14,079,149 |
| EM&V | $510,596 |  |  |  |  |  |  |  |  | $510,596 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

- In September, $372,950 will transfer from Marketing to Direct Implementation ($366,950) and Administration ($6,000).  This action will rectify the original distribution of these labor dollars in the budget.

    - Energy Effects

| Energy Effects | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 17,557 | 34 | 0% | 217 | 1% | 5,854 | 33% | 6,072 | 35% | 17,340 |
| Annual kWh | 88,042,706 | 117,165 | 0% | 839,865 | 1% | 41,677,863 | 47% | 42,517,729 | 48% | 87,202,840 |
| Lifecyc kWh | 1,452,700,830 | 1,871,601 | 0% | 13,429,768 | 1% | 744,801,064 | 51% | 758,230,832 | 52% | 1,439,271,062 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| 2005 Title 24 Seminars | 2 - 6 | 0 | 0% | 2 | 33% - 100% | 0 | 0% | 2 | 33% - 100% | 0 – 4 |
| eQUEST Training | 2 - 4 | 0 | 0% | 3 | 75% - 100% | 0 | 0% | 3 | 75% - 100% | 0 – 1 |
| Demystifying the Whole Building Approach to Energy Effic. Design | 2 - 4 | 1 | 25% -50% | 4 | 100% | 0 | 0% | 4 | 100% | 0 |
| Cool Roofs (SBD Presentation) | 2 - 4 | 1 | 25% -50% | 1 | 25% -50% | 0 | 0% | 1 | 25% -50% | 1 - 3 |
| Integrated School Building Design | 9 | 1 | 11% | 1 | 11% | 0 | 0% | 1 | 11% | 8 |

  - Activities/Accomplishments

    - Administrative -

- In August, an additional 20 committed projects where the customer received agreements with energy measure and incentive commitments were recorded.  These projects represent a potential of over 2.8 million kWh of energy savings when completed.

- Three hundred and twenty-one “Pipeline” or potential customer projects were officially recorded in the tracking system.  These projects are in the various states of project development and represent a potential of 63.4 million kWh of energy savings if development of these projects proceeds.

    - Marketing –

None

1.2.3	Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures | kWh Committed | kWh Installed in August |
| --- | --- | --- |
| Whole Building Approach |  |  |
| Whole Building - Owner Incentive | 8,308,367 | -- |
| Whole Building - DTI | 1 | -- |
| System Approach |  |  |
| HVAC: Energy Reduction | 7,920,316 | 3,704 |
| Daylighting Controls | 2,789,324 | 133,706 |
| LPD Reductions | 6,061,730 | 5,474 |
| Supermarket Systems | -- | -- |
| Process Systems | 22,460,083 | -- |

      - Calculated and Actual Payment Reconciliation –

In the month of August, financial incentives in the amount of $81,764 were paid to customers.  Tab 2A – RecordedEEActivities calculates, given the measure data recorded, that $6,121 in incentives were paid to customers.  The difference is the result of two projects not being recorded as completed in the New Construction Information System (NCIS) at the end of the month.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Statewide:

- Held a statewide conference call with its partners to discuss shared activities such as statewide-sponsored events, 2005 brochure requirements, updating the energy-modeling software tool (CaNCcalc), input towards the scoping of future Evaluation and Measurement studies, and future year program design

- Met with Consortium for Energy Efficiency (CEE) to review application of national activities and offerings to California

- Continued discussions related to adoption of Thermal Energy Storage components/baseline values in relation to 2005 Title 24 Energy Code, Investor Owned Utilities’ procurement requirements, and the California Energy Commission

- Initiated development of updated statewide collaterals for 2005

- Changes to Subcontractors or Staffing

No changes to subcontractors or staffing during this month.

- Additional Items

Statewide Savings By Design Activities:

  - Tracking reports for Energy Design Resources Web site recorded 38 online courses were taken in August 2004.

  - Savings By Design Web site had over 68,094 hits in August 2004; the Energy Design Resources site had over 163,521 hits during this same time period

  - Participated in Collaborative for High Performance Schools Commissioning Charette

- SCE Savings By Design

  - Held Savings By Design Program staff meeting

  - Held Savings By Design Monthly Implementation staff meeting

  - Supported “Cool Roofs” seminar at SCE’s Customer Technology Application Center.

  - Supported California High Performance Schools’ Integrated School Building Design seminar by presenting Savings By Design opportunities.

  - Here is a sampling of customer project participation in August:

    - A major hospital’s new Diagnostic and Treatment facility in Santa Monica.  Preliminary estimates show SBD will save the hospital 120,000 kWh per year.

    - SBD is assisting in the designing of energy efficiency measures for the prototype store for a major office and supply company.  The prototype will lower energy reductions by 34% less than a comparable minimally compliant Title 24 building

    - Services are assisting a county sanitation district with their plans to rehabilitate a water treatment plant.  The combined major renovation phases of their plant will save over 2,000,000 kWh annually

    - Recommending high efficiency modifications to a pumping facility, SBD has influenced an oil production company to reduce their potential annual energy use by over 430,000 kWh