| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | August 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $309,841 | 3% | $7,893,812 | 81% |  |  | $7,893,812 | 81% | $1,911,932 |
| Admin | $1,905,210 | $61,396 | 3% | $1,282,902 | 67% |  |  | $1,282,902 | 67% | $622,308 |
| Marketing | $3,055,234 | $68,484 | 2% | $2,607,511 | 85% |  |  | $2,607,511 | 85% | $447,723 |
| DI | $4,648,300 | $179,961 | 4% | $4,003,399 | 86% |  |  | $4,003,399 | 86% | $644,901 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Aug-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 696 | 1.1% | 88,391 | 144% | 0 | 0% | 88,391 | 144% | 0 |
| CTAC/AGTAC event seminars | 352 | 13 | 3.6% | 333 | 94.6% | 0 | 0% | 333 | 94.6% | 19 |
| Outreach events | 170 | 7 | 4.1% | 175 | 103% | 0 | 0% | 175 | 103% | 0 |

  - Activities/Accomplishments

    - Administrative

- In August, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | Handout | 50 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during August of 2005 include:

Energy Centers:

Following are accomplishments from August 1st – August 31th 2005.

EE Events completed August = 13

Attendance at those events August  = 416

EE Events completed YTD = 130

Attendance at those events YTD = 2902

EE HTR Events completed August  = 5

Attendance at those events August  = 61

EE HTR Events completed YTD = 55

Attendance at those events YTD = 769

Joint Utility events completed August  = 6

Joint Utility events YTD = 47

EE consultations August = 47

Attendees in those consultations August =  69

EE consultations YTD =  351

Attendees in those consultations YTD = 821

EE equipment demonstrations August =  35

Attendees at those demonstrations August = 78

EE equipment demonstrations YTD = 704

Attendees at those demonstrations YTD =  655

New displays developed include:

- AGTAC

Lighting Design Room Upgrade – Phase II--AGTAC has completed phase II of the Lighting Design Room upgrade. The HID (High Intensity Discharge) display has been upgraded to match CTAC, promoting 12 types of lamps and ballasts.  The latest technologies in HID, induction, and compact fluorescents are demonstrated.

- CTAC

CTAC has installed new High/Low Bay Induction lamp fixtures in the Industrial Center.   Each fixture has a 120, 80, and 40 watt induction lam that will operate with the existing daylight harvesting system in the Center.  These induction lamp/fixtures replaced the existing compact fluorescent lamp/fixtures and provide superior color and efficacy.

RTTC:

The summary description of activities which took place at the RTTC in August of 2005 is as follows:

EE Information Dissemination

- Tours

- Toured representatives of XXXXX though the RTTC and SCLTC. BC

- Toured XXXXX staff though the RTTC and SCLTC.  BC

- Publications

  - None.

- Customer Care

  - None.

EE Program Support

- Hosted XXXXX of the XXXXX program at the RTTC.  Discussed establishing a connection for transfer of RTTC’s test results to interested parties in the Commission.  As a result of this meeting, we have a greater understanding of the Title 20 process and are in a better position to support their activities.

Attended the CEC’s T-20 workshop to share concerns regarding the regulation of vending machines in 2006.

Information Services Program:

There were 696 EE contacts reported in the month of August, bringing the cumulative two year total of energy efficiency (EE), contacts to 88,391 – 145%.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None