| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to 1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, 2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $374,421 | 4% | $1,755,459 | 18% |  |  | $1,755,459 | 18% | $8,050,285 |
| Admin | $1,905,150 | $66,015 | 3% | $329,091 | 17% |  |  | $329,091 | 17% | $1,576,059 |
| Marketing | $408,600 | $4,088 | 1% | $19,080 | 5% |  |  | $19,080 | 5% | $389,520 |
| DI | $7,294,994 | $304,318 | 4% | $1,407,288 | 19% |  |  | $1,407,288 | 19% | $5,887,706 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 18,319 | 60.1% | 20,670 | 67.8% | 0 | 0% | 20,670 | 67.8% | 9,830 |
| CTAC/AGTAC event seminars | 176 | 16 | 9% | 77 | 43.8% | 0 | 0% | 77 | 43.8% | 99 |
| Outreach events | 85 | 17 | 20% | 43 | 50.6% | 0 | 0% | 43 | 50.6% | 42 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element - continued program administration tasks including management of activity and budget status reporting.

    - Marketing

In addition to the list in Attachment A:

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| 2nd Quarter Calendar of Events | Calendar | US Mail Hand Deliver | 26,755 7160 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during May of 2004 include:

Energy Centers:

Following are accomplishments from May 1st – May 31st 2004.

EE Events completed May = 16

Attendance at those events May = 351

EE Events completed YTD = 77

Attendance at those events YTD = 2154

EE HTR Events completed May = 5

Attendance at those events May = 56

EE HTR Events completed YTD = 31

Attendance at those events YTD = 628

Joint Utility events completed May = 6

Joint Utility events YTD = 34

EE consultations May = 53

Attendees in those consultations May = 106

EE consultations YTD = 323

Attendees in those consultations YTD = 742

EE equipment demonstrations May = 183

Attendees at those demonstrations May = 181

EE equipment demonstrations YTD = 443

Attendees at those demonstrations YTD = 539

New displays developed include:

- AGTAC

  - VSD Match 5 hp Exhibit upgrade – incorporated VFD feedback controls, improved instrumentation and replaced worn water tank.

- CTAC

  - No new displays at CTAC in May

RTTC:

The following provides a summary description of activities which took place at the RTTC in May 2004:

EE Information Dissemination

- Provided a tour of the RTTC for Electro Industries.

- Developed a food service refrigeration seminar based on the RTTC’s test results.

The RTTC presented this seminar at CTAC.

- Developed an air conditioning maintenance seminar based on the RTTC’s test results.  The RTTC presented this seminar at AgTAC.

Information Services Program:

- There were 18,319 EE contacts conducted in the month of May 2004; bringing the YTD total EE contacts to 20,670.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

AGTAC established seminar dates with CEC/DOE on the following classes: July - ‘Fundamentals of Compressed Air Systems, August - ‘Electric Motor Systems’ and September - ‘Pumping Systems Assessment Tool’.

- Changes to Subcontractors or Staffing

None

- Additional Items

AGTAC held its fifth annual Power-Up Event competition.  In cooperation with the Tulare City School District and other local school districts, 353 participants involving 69 student teams gave presentations to a panel of judges on energy use, electricity safety and water/energy conservation.

A number of Outreach Events that were not included in the previous monthly reports are currently listed in Section F of the Supporting Documentation.