| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | July 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to 1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, 2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $324,373 | 3% | $2,636,028 | 27% |  |  | $2,636,028 | 27% | $7,169,716 |
| Admin | $1,905,210 | $60,273 | 3% | $459,204 | 24% |  |  | $459,204 | 24% | $1,446,006 |
| Marketing | $3,055,234 | $157,154 | 5% | $917,618 | 30% |  |  | $917,618 | 30% | $2,137,616 |
| DI | $4,648,300 | $106,946 | 2% | $1,259,207 | 27% |  |  | $1,259,207 | 27% | $3,389,093 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 10,992 | 36.0% | 36,991 | 121.3% | 0 | 0% | 36,991 | 121.3% | 0 |
| CTAC/AGTAC event seminars | 176 | 17 | 9.7% | 108 | 61.4% | 0 | 0% | 108 | 61.4% | 68 |
| Outreach events | 85 | 5 | 5.9% | 60 | 70.6% | 0 | 0% | 60 | 70.6% | 25 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In July, continued program administration tasks including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| U.S. Department of Energy Best Practices Series | Flyer | US Mail | 410 |
| Cool Roofs | Email Invite | Email | 5764 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during July of 2004 include:

Energy Centers:

Following are accomplishments from July 1st – July 31st 2004.

EE Events completed July = 17

Attendance at those events July = 399

EE Events completed YTD = 108

Attendance at those events YTD = 2975

EE HTR Events completed July = 7

Attendance at those events July = 86

EE HTR Events completed YTD = 44

Attendance at those events YTD = 790

Joint Utility events completed July = 5

Joint Utility events YTD = 43

EE consultations July = 56

Attendees in those consultations July = 167

EE consultations YTD = 440

Attendees in those consultations YTD = 1099

EE equipment demonstrations July = 151

Attendees at those demonstrations July = 105

EE equipment demonstrations YTD = 723

Attendees at those demonstrations YTD = 713

New displays developed include:

- AGTAC

  - Ground Source Heat Pump Display enclosure for AGTAC’s GSHP Exhibit was completed

  - Upgrade to the Low Pressure Pumping Exhibit included the addition of a Replogle Flume structure, as a way to accurately determine water flow compared to other traditional flow meters

- CTAC

  - No new displays at CTAC in July

RTTC:

The following provides a summary description of activities which took place at the RTTC in July 2004:

EE Information Dissemination

- Performed four RTTC and Lighting Center tours for “Bring Your Kids to Work Day” kids, total of about 80 guests

- Performed RTTC tour for the VP and the staff of Architectural Energy Corporation

- Performed RTTC tour for members of the Cryostatic Technologies Company

Energy Efficiency Guide Fact Sheet

- In response to a request from CSBU’s Market Management and Communications, 	and Business Solutions, the RTTC developed a comprehensive Refrigeration 	Energy Efficiency Guide, which contains simple energy efficiency tips for SCE’s 	small and medium size customers.

Tool Development

Door Gasket Replacement Energy Savings Tool

  - In response to MCD Business Solutions’ request, the RTTC started development of PDA based tool.  The tool will assist SCE’s field staff in meeting their 5,000 audits goal for this summer.

Walk-in Cooler/Freezer Energy Savings Tool

  - The RTTC developed a user-friendly energy analyses tool for calculating the energy savings associated with the implementation of several energy efficiency measures on walk-in boxes.  This tool was developed for MCD’s field engineering staff.

Customer EE Support

  - Massachusetts Mutual Life Insurance, Orange, CA – Performed a series of computer simulations to evaluate the impact of a high efficiency chiller system for this customer in City of Orange.  Based on the RTTC’s analyses, the new system can provide 205,000 kWh savings annually for the customer.

Publications

  - The RTTC’s energy efficiency technology evaluation initiatives received an in-depth coverage in the July issue of Platts ET Currents.  Platts research and consulting, formerly, E-Source featured the RTTC’s display case efficiency evaluation project in its July issue.

Information Services Program:

There were 10,992 EE contacts conducted in the month of July 2004; bringing the YTD total EE contacts to 36,991.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

AGTAC partnered with the CEC and the DOE to hold a Compressed Air Systems workshop at AGTAC on July 29th.

- Changes to Subcontractors or Staffing

On July 13, 2004, AGTAC replaced XXXXX (a supplemental employee) with XXXXX, a part-time SCE Administrative Analyst.

- Additional Items

New Exhibit Building – AGTAC received capital approval to proceed with construction. This 3200 square foot building will be a state-of-the-art technology exhibit building, 	serving as a “living display” of the most current energy efficient technologies in roofing, wall insulation and lighting systems while providing needed space for showcasing existing and future technology exhibits.