| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | May 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $366,020 | 4% | $6,777,119 | 69% |  |  | $6,777,119 | 69% | $3,028,625 |
| Admin | $1,905,210 | $48,783 | 3% | $1,088,761 | 57% |  |  | $1,088,761 | 57% | $816,449 |
| Marketing | $3,055,234 | $127,399 | 4% | $2,291,240 | 75% |  |  | $2,291,240 | 75% | $763,994 |
| DI | $4,648,300 | $189,838 | 4% | $3,397,118 | 73% |  |  | $3,397,118 | 73% | $1,251,182 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 10,458 | 17.1% | 72,116 | 118.2% | 0 | 0% | 72,116 | 118.2% | 0 |
| CTAC/AGTAC event seminars | 352 | 14 | 3.9% | 286 | 81.3% | 0 | 0% | 286 | 81.3% | 66 |
| Outreach events | 170 | 26 | 15.3% | 155 | 91.2% | 0 | 0% | 155 | 91.2% | 15 |

  - Activities/Accomplishments

    - Administrative

- In May, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| CTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail Hand Deliver | 31,592 7,500 |
| Cook, Chill and Retherm | Flyer | US Mail | 936 |
| Commercial & Industrial Lighting/How to Manage Your Business’ Energy Costs | Crafton College Newsletter | Newsletter | n/a |
| CTAC June Classes | Email | Email | 4394 |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail | 9500 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during May of 2005 include:

Energy Centers:

Following are accomplishments from May 1st – May 31st 2005.

EE Events completed May = 14

Attendance at those events May = 270

EE Events completed YTD = 83

Attendance at those events YTD = 1896

EE HTR Events completed May = 6

Attendance at those events May = 79

EE HTR Events completed YTD = 30

Attendance at those events YTD = 443

Joint Utility events completed May = 6

Joint Utility events YTD = 36

EE consultations May = 47

Attendees in those consultations May = 135

EE consultations YTD = 204

Attendees in those consultations YTD = 658

EE equipment demonstrations May = 154

Attendees at those demonstrations May = 87

EE equipment demonstrations YTD = 411

Attendees at those demonstrations YTD = 422

New displays developed include:

- AGTAC

No new displays at AGTAC in May.

- CTAC

CTAC has purchased a table top day lighting controls simulator.  This 	simulator is capable of demonstrating the performance of skylights, side 	lighting and electric lighting systems in a building space.  The simulator 	will be used to support our seminars, training and technical consultation 	activities.

RTTC:

The summary description of activities which took place at the RTTC in May of 2005 is as follows:

EE Information Dissemination

- Tours

- Performed RTTC tour for HVAC industry members.

- Performed RTTC and SCLTC tours for Cal Poly Pomona Engineering Tech. class.

- Performed RTTC and SCLTC tours for XXXXX division staff member.

- Performed RTTC and SCLTC tours for XXXXX staff members.

EE Program Support

  - Developed intermediate refrigeration certification test for BCD’s staff

  - Provided technical support to SPC consultants and assisted them with an evaluation of their engineering algorithm for walk-ins and cold storages

  - Participated in a three-day review process of all the proposed measures for 2006-2008 EE Programs. Additionally, all the pertaining back up documentation of refrigeration measures for 2006-2008 EE Programs were reviewed and commented

Information Services Program:

There were 10,458 EE contacts conducted in the month of May of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 72,116.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None