| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | April 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $364,824 | 4% | $6,411,100 | 65% |  |  | $6,411,100 | 65% | $3,394,644 |
| Admin | $1,905,210 | $70,547 | 4% | $1,039,978 | 55% |  |  | $1,039,978 | 55% | $865,232 |
| Marketing | $3,055,234 | $125,412 | 4% | $2,163,841 | 71% |  |  | $2,163,841 | 71% | $891,393 |
| DI | $4,648,300 | $168,865 | 4% | $3,207,281 | 69% |  |  | $3,207,281 | 69% | $1,441,019 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 8,043 | 13.2% | 61,658 | 101% | 0 | 0% | 61,658 | 101% | 0 |
| CTAC/AGTAC event seminars | 352 | 22 | 6.3% | 272 | 77.3% | 0 | 0% | 272 | 77.3% | 80 |
| Outreach events | 170 | 18 | 10.6% | 129 | 75.9% | 0 | 0% | 129 | 75.9% | 41 |

  - Activities/Accomplishments

    - Administrative

- In April, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Green Buildings Events | Email | Email | 2764 |
| CTAC Workshops May classes | Email | Email | 3025 |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| AGTAC Workshops April classes | Email | Email | 400 |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | Hand Deliver | 50 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during April of 2005 include:

Energy Centers:

Following are accomplishments from April 1st – April 30th 2005.

EE Events completed April = 22

Attendance at those events April = 501

EE Events completed YTD = 69

Attendance at those events YTD = 1626

EE HTR Events completed April = 7

Attendance at those events April = 105

EE HTR Events completed YTD = 24

Attendance at those events YTD = 364

Joint Utility events completed April = 9

Joint Utility events YTD = 30

EE consultations April = 42

Attendees in those consultations April = 155

EE consultations YTD = 157

Attendees in those consultations YTD = 523

EE equipment demonstrations April = 101

Attendees at those demonstrations April = 58

EE equipment demonstrations YTD = 257

Attendees at those demonstrations YTD = 335

New displays developed include:

- AGTAC

Lighting Design Room Technology Upgrade Phase I - The installation of our newly refurbished and upgraded Trilon units has been completed.  Trilons are rotating three-sided units that display lighting technologies.

- CTAC

No new displays at CTAC in April.

RTTC:

The summary description of activities which took place at the RTTC in April of 2005 is as follows:

EE Information Dissemination

- Tours

- Performed tours for staff members from XXXXX

- Performed tours for the XXXXX

- Performed tours for XXXXX staff members

- Performed tours for XXXXX staff

EE Program Support

  - Worked with BCD team to develop training curriculum for project managers

  - Performed an investigation to assess the qualifications for four different models of a glass door reach-in frozen food display case.  These types of display cases are equipped with either standard or special glass doors that require minimum to low anti-sweat heater.  These special glass doors fall under measures “G” and “H” in 2005 Express Efficiency refrigeration program.

  - Set up an energy advisory meeting with the management team of Jack in the Box Corporation to address their energy efficiency challenges in the areas of refrigeration and air conditioning.

  - Provided technical assistance in the area daylighting modeling and analyses to staff of XXXXX using Heliodon system.

Information Services Program:

There were 8,043 EE contacts conducted in the month of April of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 61,658.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None